## Sheet1
WORK PROGRAM
ON IMPLEMENTATION OF MEASURES ENVISAGED WITHIN THE PUBLIC FINANCE SYSTEM REFORMS ACTION PLAN FOR 2019-2023
Number of Measure | Measure | Phase | Outcome | Term (start-end) | Responsible body | Development Partner Organization / Program * | Actual performance
Work actually done
1 | 2 |  | 4 | 5 | 6 | 7 | 8
1.1 | Elaboration of final versions of the DSGE model (s) | Done | DSGE model availability | 01/2019-12/2019 | Macroeconomic Policy Department |  | DSGE model is elaborated
1.2 | Introduction and full operation of DSGE modules | 1.2.1 Testing and finalization of DSGE mode (Working discussions with IMF experts) | Availability of a practically tested version of the DSGE model | 02/2020-09/2020 | Macroeconomic Policy Department | IMF (Working discussions with IMF experts on DSGE model testing and finalization) | Discussions on the development of a working document, elaboration of separate sections were carried out jointly with IMF experts.
|  | 1.2.2 Documentation of related analytical and evaluation work carried out during the elaboration of the elaborated model, development of a manual for the use of the model | Availability of documents և usage manual | 02/2020-12/2020 |  | IMF | Preliminary versions of the relevant documents have been developed.
|  | 1.2.3 Elaboration and publication of working paper jointly with IMF and RA MoF (IMF Working paper) | Published working document | 04/2020-12/2020 |  | IMF (Elaboration and publication of working paper jointly with IMF and RA MoF (IMF Working paper) | Discussions on the development of a working document, elaboration of separate sections were carried out jointly with IMF experts.
|  | 1.2.4 Application of a new model (s) in the development of policy scenarios during the elaboration stages of the State Budget և MTEF | Presentation of model based macro-fiscal framework in budget and MTEF processes | Beginning from April, 2020 |  |  | With the help of the model, the effects of the coronavirus epidemic on the Armenian economy of the multifaceted fiscal measures taken on the were assesse
|  | 1.2.5 Evaluation of the impact of planned fiscal policy changes through a new set of tools | Availability of comprehensive assessments of fiscal policy impacts | Implemented per instructions during the elaboration of new policies and reforms |  |  | With the help of the model, the effects of the coronavirus epidemic on the Armenian economy of the multifaceted fiscal measures taken on the were assessed, on the basis of the results, the 2021-2023 MTEF macro-fiscal framework has been drawn up. The preliminary version of the model has already assessed the impact of the tax reforms that came into force this year, as well as other policies (raising the minimum wage, the introduction of a comprehensive health insurance system).
2.1 | Detection of deviations between planned and actually implemented fiscal policy and Impact assessment | 2.1.1 Monitoring of ongoing fiscal policy, comparative analysis of planned and actually implemented policies, detection of deviations | Revealed causes of deviations and factors | Beginning from 2021, within 10 days after the publication of information on the annual indicators of the state budget | Macroeconomic Policy Department
|  | 2.1.2 Assessing the impact of fiscal policy deviations on the economy | Availability of comprehensive deviation impact assessments | Beginning from 2021, within 20 days after the publication of the annual GDP
3.1. | Implementation of measures aimed at raising the qualification of the staff | 3.1.1 Continuous development of professional skills | Availability of personnel with required qualifications and skills | 2019-2023 | Macroeconomic Policy Department |  | In connection with the cancellation of previously available courses due to the epidemic in 2020. During the first half of the year, only one employee of the department was trained within the framework of the trainings organized in Vienna (JVI). Employees participated in other available online courses, including regular webinars initiated by JVI.
|  | 3.1.2 Participation in trainings and practical work organized by international organizations |  | 2019-2023 |  |  | Encouragement through the remuneration fund provided to the department and application of other incentive methods.
3.1.3 Participation in localized country-specific trainings organized by international organizations
|  | 3.1.4 Ensuring competitive renumeration and application of of other incentive methods | Prevention of outflow of qualified personnel | Ongoing
4․1 | Expansion of fiscal risk assessment coverage, improvement of methodology | 4.1.1 Assessment of fiscal risks of state-owned companies operating in sectors other than energy, transport and water management | Fiscal risk assessments include an expanded range of fiscal risk sources | 2020-2023 | Financial Statistics and Risk Department | ADB | Fiscal risk assessments related to the activities of 20 organizations operating in the infrastructure (energy, transport, water economy) sectors were carried out, which also included the analysis of contingent liabilities arising from the contracts of public-private partnership companies. The latter were reflected in the document RA 2021-2023 MTEF (link: http://www.minfin.am/en/page/petakan_mijnazhamket_tsakhseri_tsragre/). At the same time, the work on expanding the scope of assessment of fiscal risk sources continues.
|  | 4.1.2 Analysis of contingent liabilities arising from public-private partnership programs. | Improved fiscal risk methodology |  |  | ADB/IMF Analysis of contingent liabilities arising from public-private partnership programs. | With the support of ADB Consultants, RA Government draft decision "On approving the methodology for calculating and evaluating the contractual obligations of the Republic of Armenia on n terms of public-private partnership projects"has been elaborated and submitted to the Office of the RA Prime Minister.
|  | 4.1.3 Assessment of fiscal risks arising from natural and man-made disasters. |  |  |  | ADB Assessment of fiscal risks arising from natural and man-made disasters.
|  | 4.1.4 Assessment of fiscal risks arising from litigation against the state: |  |  |  | ADB Assessment of fiscal risks arising from litigation against the state
|  | 4.1.5 Assessment of fiscal risks arising from environmental liabilities. |  |  |  | ADB Assessment of fiscal risks arising from environmental liabilities.
|  | 4.1.6 Assessment of fiscal risks arising from the financial system. |  |  |  | ADB Assessment of fiscal risks arising from the financial system.
|  | 4.1.7 Approval of developed methodology and application, elaboration of relevant guidelines. |  |  |  | Approval of developed methodology and relevant guideline development by ADB
5․1 | Capacity development | 5.1.1 Capacity development within the framework of consulting activities. | Specialists with improved analytical skills in assessing fiscal risks | 2020-2023 | Financial Statistics and Risk Department | ADB/IMF | 2020 During the first half of the year, one employee of the department was trained within the framework of the courses organized in Vienna (JVI). The employees also participated in the trainings organized by the World Bank in Yerevan. In addition, training is provided as part of ADB's consulting work.
5.1.2 Participation in trainings organized by international organizations.
2020-01-07 | Elaboration of the RA draft law "On Making Amendments to the RA Tax Code" | 7.1.1 Carrying out studies to identify low-efficiency, non-targeted tax benefits, including with the involvement of experts from international donor organizations | Low-efficiency, non-targeted tax benefits are eliminated | 3rd ten days of June, 2021 | Revenue Policy and Administration Methodology Department | ADB/IMF | An agreement has been reached with ADB to receive technical assistance for the implementation of the activities in this area
|  | 7.1.2 Discussion woth the stakeholders on the expediency of reducing low-efficiency benefits based on the conducted studies |  | 3rd ten days of December, 2021
|  | 7.1.3 In accordance with the agreements reached as a result of the discussions, elaboration of RA draft law "On Making Amendments to the RA Tax Code" addressed to reducing low-efficiency benefits and submission for consideration |  | 3rd ten days of June 3, 2022
8․1 | Elaboration of the RA draft law "On Making Amendments and supplements to the RA Tax Code" | 8.1.1 Carrying out studies studies for reviewing tax burden of tunover tax including with the involvement of specialists from international donor organizations | As a result of the conducted studies, the turnover tax burden has been revised | 3rd ten days of June, 2021 | Revenue Policy and Administration Methodology Department | ADB/IMF | An agreement has been reached with ADB to receive technical assistance for the implementation of the activities in this area
|  | 8.1.2 Elaboration of proposals for reviewing turnover tax rates based on the conducted studies and submitting to stakeholders and business circles for consideration |  | 3rd ten days of December, 2021
|  | 8.1.3 Based on the results of the discussions, elaboration of RA draft law "On Making Amendments and supplements to the RA Tax Code" addressed to reviewing turnover tax rates and submission for consideration |  | 3rd ten days of June, 2022
9․1 | Elaboration of the RA draft law "On Making Amendments and supplements to the RA Tax Code" | 9.1.1 Development of proposals for the settlement of problems related to the documentation of transactions of the sale of agricultural products and submitting for consideration | Problems with documenting transactions are settled | 3rd ten days of October, 2020 | Revenue Policy and Administration Methodology Department |  | Suggestions for resolving issues related to the documentation of transactions in the sale of agricultural products have already been developed and will be submitted for discussion in the near future.
|  | 9.1.2 Based on the results of the discussions, elaboration of RA draft law "On Making Amendments and supplements to the RA Tax Code" and submitting for consideration. Settlement of issues related to transaction documentation. |  | 3rd ten days of March, 2021
10․1 | Elaboration of the RA draft law "On Making Amendments and supplements to the RA Tax Code" | 10.1.1 Carrying out relevant analyzes based on the values approximated to the market value of real estate and submission of proposals to the RA Prime Minister's Office on real estate tax rates and non-taxable thresholds | Visible wealth or property is taxed adequately | (3rd ten days of February, 2020) | Revenue Policy and Administration Methodology Department |  | The mentioned measured is already implemented. In particular, on June 25, 2020, the RA National Assembly adopted the RA Law "On Making Amendments and Supplements to the Tax Code of the Republic of Armenia" aimed at reviewing the real estate tax system.
|  | 10.1.2 Elaboration of the draft law envisaging amendments to the RA Tax Code on the basis of the analyzes and the decisions made as a result of the discussions on them and considerations with stakolder state bodies |  | (3rd ten days of March, 2020)
|  | 10.1.3 Submission of the final version of the draft law envisaging amendments to the RA Tax Code for the consideration of the RA Government |  | (3rd ten days of April, 2020)
11․1 | Elaboration of the RA draft law "On Making Amendments and supplements to the RA Tax Code" | 11.1.1 Approval of the action plan required for the introduction of the personal income declaration system | The legal basis for the introduction of a revenue declaration system based on economic incentives is ensured | 2nd ten days of April, 2020 | Revenue Policy and Administration Methodology Department |  | The action plan required for the introduction of the personal income declaration system was approved by the RA Minister of Finnce Order N 104-Լ, dated April 6, 2020 Studies of the international experience of the personal income declaration system were carried out and the results were presented for discussion, The RA draft law “On Making Amendments and Supplements to the RA Tax Code” aimed at the introduction of personal income declaration system has been elaborated
|  | 11.1.2 A study of international experience in the implementation of the so-called "social credit" system, which is widely used in international practice |  | 3rd ten days of May, 2020
|  | 11.1.3 Elaboration of legal acts envisaging relevant changes in the tax legislation for the introduction of the income declaration system. |  | 3rd ten days of June, 2021
12.1. | Assessing the tax potential and gap for the three major types of taxes (VAT, profit tax, income tax) | 12.1.1 Collection and processing of information necessary for the assessment of tax potential |  | Continuous since 2020. It depends on the process of reaching an agreement with the RA State Revenue Committee and data provision | Macroeconomic Policy Department |  | In the framework of tax potential gap assessment, the RA Ministry of Finance, in cooperation with the RA State Revenue Committee and the RA Central Bank, assessed the tax potential of the Republic of Armenia, the results of which were discussed with the RA Deputy Prime Minister in December 2019. Based on this, agreements were reached and the RA State Revenue Committee was instructed to conduct a study and present its assessments on the tax potential. During the first half of 2020, the RA MoF did not carry out any work on assessing the tax potential gap. Further activity on assessing the tax potential gap depends on the progress of the work to be carried out by the RA State Revenue Committee.
|  | 12.1.2 Estimation of last year's tax potential and gap for three major types of taxes using the tax gap assessment methodology, developed by the RA MoF | Availability of tax potential: gap assessment | Continuous since 2020. It depends on the process of reaching an agreement with the RA State Revenue Committee and data provision |  |  | Further work on assessing the tax potential gap depends on the progress of the work to be carried out by the RA SRC
|  | 12.1.3 Improving the elaborated methodology and application | Improved estimates of tax potential and gap | Continuous since 2020.
13․1 | Publication of data on tax refunds from the state budget on a quarterly basis |  | Relevant published information |  | Operational Department |  | In accordance with the RA SRC Chairman order N 267-A, dated 17.04.2019, the relevant information is published on a monthly basis in the RA SRC official website (http://www.petekamutner.am) in the section "Tax Information", sub-section "Tax Statistics" , part "Tax Statistics data"
16․1․ | Review/develop budget programs in line with policies being carried out by existing strategic documents | 16.1.1 Study / evaluation of compliance of budget programs with the policies defined by the strategic documents | Availability of conformity assessment | 01/2021-06/2021 | Budget Process Organization Department | Support is needed, but the development partner organization is not clear | By RA Prime Minister By Recommendation No. 02 / 08.5 / 35060-2020, dated 21.07.2020, all SBs were asked to harmonize the financial assessments of the sector strategies with the MTEF. As of 13.08.2020, the measure is implemented i in 18 out of 37 SB having submitted the report on PFMSR progress report and the presented budget programs correspond to the policy directions defined by the main strategies of the PA. Work is underway in 12 bodies to implement the measure: analysis of budget programs from the point of view of compliance with existing strategic documents is carried out. 2 There is a process of reviewing strategies / policy directions in connection with the reorganization and legislative changes in the SB.
|  | 16.1.2 Elaboration of institutional, legislative and procedural regulations and mechanisms necessary to ensure the compliance of budget programs with the policies defined by the strategic documents. | All the programs included in the 2023 state budget are in line with the existing strategies | 06/2021-10/2021 |  | Support is needed, but the development partner organization is not clear
|  | 16.1.3 Determination of measures and schedule for correction of inconsistencies by separate state bodies | 2023 Budget programs fully cover all existing strategies that affect budget revenues and expenditures All programs included in the 2023 state budget (except for administrative programs) have program passports which are submitted to the RA National Assembly attached to the 2023 draft state budget | 06/2021-08/2021 |  | Support is needed, but the development partner organization is not clear
|  | 16.1.4 Review the programs of state bodies and complying with the requirements of the policy according to the established schedule |  | In accordance with the schedule of measures approved by point 16.1.3, no later than 12/2022
16․2 | Identification and regulation of practical issues related to program budgeting existing methodology and its application | 16.2.1 Study of existing gaps and problems related to program budgeting methodology and its application | Availability of a report on the study of the PB methodology and existing gaps and problems related to its application | 01/2021-06/2021 | Budget Process Organization Department | After discussions with the IMF an agreement has been reached on the possibility to be provided with technical assistance for implementing studies on problems and gaps related to PB methodology introduction and its application | The possibility of providing external technical assistance for the implementatio of studies related to introduction of the PB methodology problems and gaps related to its application is currently being discussed with partner international organizations. In parallel, it is envisaged that by the end of the year, self-assessments will be carried out on introduction of the PB methodology and the existing gaps and problems related to its application.
|  | 16.2.2 Elaboration of measures for improving program budgeting methodology and its application | Draft of list of measures and schedule for improving the PB methodology and its application | 06/2021-08/2021
|  | 16.2.3 Discussions with stakeholders on the measures for improving program budgeting methodology and its application | Availability list of measures and schedule for improving the PB methodology and its application | 08/2021-09/2021
|  | 16.2.4 Approval of measures for improving program budgeting methodology and its application | Measures for improving the PB methodology are implemented in accordance with the schedule | 09/2021-10/2021
|  | 16.2.5 Implementation of measures for improving program budgeting methodology and its application in accordance with the measures list and schedule |  | In accordance with the schedule of measures approved in point 16.2.4, no later than 12/2022
16․3․ | Human resource development activities | 16.3.1 Assess institutional capacity for existing human resources in line with the requirements of the introduced program budgeting | Institutional Capacity Assessment Report(s) for existing human resources in line with the requirements of the PB embedded system | 01/2021-06/2021 | Budget Process Organization Department | Support is needed, but the development partner organization is not clear | The possibility of being provided with external technical assistance for the implementation of the institutional capacity assessment of the existing human resources and for the implementation of the elaboration of capacity development program in accordance with the requirements of the embedded PB, is currently being discussed with partner international organizations. It is envisaged that in parallel, internal assessments of relevant capacities in state bodies will be carried out by the end of the year. Based on the results of the above-mentioned external-internal evaluations, an appropriate capacity building program will be developed.
|  | 16.3.2 Elaboration of capacity building program | Availability of an up-to-date capacity building program | 06/2021-09/2021 |  | Support is needed, but the development partner organization is not clear
|  | 16.3.3 Implement capacity building measures in accordance with the approved program | Capacity building activities are implemented in accordance with the approved program | In accordance with the schedule of measures approved by point 16.3.2, no later than 12/2023
17․1․ | Elaboration of budget program evaluation guidelines | 17.1.1 Elaboration of the concept of monitoring and evaluation of budget programs | The concept of monitoring and assessment of budget programs is available | 09/2020-12/2020 | Budget Process Organization Department | (GIZ) | An agreement was reached with the German International Cooperation Agency (GIZ) to provide technical assistance to the MoF in the activities for elaboration of the budget program monitoring, evaluation concept, methodology, as well as the system introduction measure schedule. In this regard, the terms of reference of the above-mentioned activities has already been discussed, the relevant consultant is expected to be selected, the actual works will start this year in September.
|  | 17.1.2 Elaboration of methodological guidelines for monitoring and evaluation of budget programs | Measures for introduction of the monitoring and evaluation functions of the budget programs and draft schedule | 09/2021-02/2021
|  | 17.1.3 Elaboration of the draft for monitoring budget programs and evaluation concept, measures for introduction of functions and schedule |  | 09/2021-03/2021
|  | 17.1.4 Discussion with stakeholders of schedule for monitoring budget programs and evaluation concept, measures for introduction of functions and schedule | Minutes of the results of the discussions and revised drafts | 03/2021-04/2021
17․2․ | Introduce a process of regular evaluation of budget programs | 17.2.1 Revision and approval of the draft for monitoring budget programs and evaluation concept, measures for introduction of functions and schedule | Availability of a schedule and measures for the implementation of budget program evaluation functions | 04/2021-05/2021 | Budget Process Organization Department |  | The activities to be carried out within the framework of the event are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure.
|  | 17.2.2 Organizing a program monitoring and evaluation process in the state bodies responsible for budget programs | As of the end of the 2023 budget year, each state body responsible for budget programs has a regular program evaluation process. | In accordance with the schedule of measures approved by point 17.2.1, no later than 12/2022
|  | 17.2.3 Carrying out pilot monitoring and evaluation of budget programs in the state bodies responsible for budget programs in accordance with the approved guidelines | As of the end of the 2023 budget year, at least 1 budget program implemented by each state body responsible for budget programs has been piloted in accordance with the approved guidelines. | In accordance with the schedule of events measures by point 17.2.1, no later than 12/2023
18․1 | Identification and registration of programs/measures arising from the mandatory liabilities of the state | 18.1.1 Elaboration of methodology for identification and registration of programs/measures arising from the mandatory liabilities of the state | Relevant methodology is available | 09/2020-12/2020 | Budget Process Organization Department |  | 2021-2023 MTEF and 2021 The methodological instructions for preparing and submitting budget applications already contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. However, the latter needs further clarification or revision in practical terms. In this regard, discussions are currently underway with partner international organizations to provide external advisory support for the implementation of the above-mentioned methodological work.
|  | 18.1.2 Identification and registration of state liabilities in the framework of the 2022 budget process | Procedures are developed in the framework of the 2022 budget process, the obligatory obligations of the state are identified and registered | 01/2021-10/2021
19.1․ | Creation of legal bases and development of methodology for ensuring a single process of preparing the MTEF and annual budget | 19.1.1 The work on the preparation of the MTEF and annual budget is carried out by a single process | Activities on the preparation of the MTEF and annual budget is carried out by a single process | 01/2021-06/2021 | Budget Process Organization Department |  | The action is actually done. Starting from 2020, the activitoes of drafting the MTEF and annual budget is already carried out by a single process, for which the legal basis is the schedule set by the decision of the RA Prime Minister on starting the 2021.budget process. After summarizing the results of the 2021 budget process, the expediency of making relevant amendments to the Law "On RA Budget System" will be considered. Accordingly, if necessary, a package of relevant changes will be elaborated and submitted for approval.
20․1 | Elaboration and publicity of simplified version of state budget and state budget execution report | 20.1.1 Preparation of 2021 simplified budget | The simplified budget for 2021 is published on the official website of the RA MoF | Within one month after the adoption of the 2021 RA state budget | Budget Process Organization Department |  | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021: For this purpose, with the support of the GIZ the methodological instructions for the preparation of sectoral budget projects by the state bodies within the framework of the drafting of the RA 2021 draft state budget and MTEF 2021-2023 were posted on the official website of the MoF link: http://www.minfin.am/website/images/website/documents/Metodakan2021%20(2).docx), as well as it was officially provided to the public authorities.
|  | 20.1.2 Preparation 2021 of simplified version of stat budget execution report | The simplified report on the execution of the 2021 budget is published on the official website of the RA MoF | Within one month after the adoption of 2021 state budget execution report |  |  | The measure on the 2021 budget process has been implemented According to the schedule approved by the RA Prime Minister's decision N 5-A, dated January 9, 2012 "On starting the RA 2021 budget process", clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. Within the framework of the 2021 budget process, the budget proposals of the requesting state bodies were published on their websites, in a place accessible to CSOs.
|  | 20.1.3 Holding discussions with CSOs on simplified budget and budget execution report | Discussions with CSOs on simpified budget and simplified report on the execution of the budget have been organized (at least twice a year) | Within one month after the adoption of 2021 RA State Budget (in terms of simplified budget) and 2021 RA State budget execution report (in terms of simplified budget performance report) |  |  | Discussions with CSOs on the simplified version of the State Budget և State Budget Execution Report will be conducted within the schedule set by the working paln.
21.1. | Publicizing information on budget proposals | 21.1.1 By the RA Prime Minister decision on starting the annual budget process setting the requirements for posting the budget proposals of the RA state bodies on their websites, providing access for CSOs, and holding discussions on budget applications with the latter. | Decision of the RA Prime Minister on starting the budget process of each year | Term for adopting the RA Prime Minister Decision on starting annual budget process | Budget Process Organization Department |  | he measure on the 2021 budget process has been implemented According to the schedule approved by the RA Prime Minister's decision N 5-A, dated January 9, 2012 "On starting the RA 2021 budget process", clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. Within the framework of the 2021 budget process, the budget proposals of the requesting state bodies were published on their websites, in a place accessible to CSOs.
|  | 21.1.2 Posting the budget proposls of the RA state bodies on their websites, providing access for CSOs | Budget proposals of RA state bodies are posted on their websites and are available for CSOs | Within the timeframe set by the RA Prime Minister's decision on starting annual budget process | State bodies-Budget Process Organization Department |  | Within the framework of the 2021 budget process, the budget proposals of the requesting state bodies were published on their websites, in a place accessible to CSOs.
21.2. | Establishment of a platform (s) for discussing budget proposals with CSOs | 21.2.1 RA state bodies have platforms to discuss budget proposals with CSOs | Platforms for discussing budget proposals of RA state bodies | 01/2021 -12/2022 | State bodies-Budget Process Organization Department | GIZ | According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9 "On starting the budget process of the Republic of Armenia for 2021", a requirement was set by state bodies to place their budget applications on their official websites. In order to ensure the process of public discussions on budget proposals of state bodies, with the support of GIZ the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF 2021-2023 and 2021 state budgets (link http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA MoF and provided to all state bodies. At the same time, according to the preliminary agreement, within the framework of the GIZ support, it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the state budgeting process. According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. Nevertheless, conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process.
|  | 21.2.2 Inclusion of information on the results of the discussions with CSOs in the budget proposals of the RA state bodies | The budget proposals of the RA state bodies include the results of the discussions on the applications with the CSOs. | Within the timeframe set by the RA Prime Minister's decision on starting annual budget process | State bodies-Budget Process Organization Department |  | According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. Nevertheless, conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process.
22.1 | Phased introduction of an automated budget programs costing system | 22.1.1 Piloting and introduction of budget programs costing system | The automated budget program costing system has been piloted and is ready for introduction | Within one month after the adoption of 2021 RA State Budget execution report | Budget Process Organization Department |  | The elaboration and testing of the automated budget expenditure planning system by the RA Ministry of Finance (Authorized Body) has already been completed in December 2019. The system allows applicant bodies to submit online cost-benefit calculations online as part of budget funding bids, using pre-designed batch և quota agreed with the Authorized Body in formats preliminary elaborated by applicant bodies and agreed with authorized body , as well as enables the respective competent users of the applicant body and the authorized body approve / reject, as well as summarize the data of the received proposals according to the program, operational-economic classifiers, allowing to receive the necessary details of the openings of the numbers of programs / measures In the first half of 2020, professional meetings were held with the representatives of the applicant bodies on the elaboration of templates for the calculation and substantiation of expenditures on the programs and measures included in the budget proposals for the importing into the system after which the RA MoF together with the applicant bodies, started the work of elaborating samples of budget programs and measures calculation of cost-measures to be included in the budget proposals and submitting to the RA MoF which were planned to be completed by February 20, 2020. All samples agreed and approved by the RA MoF have already been imported into the System, and based on the data provided by the Applicating Bodies, users have been created in the system, defining the relevant authorities. In accordance with the RA Prime Minister recommendation the applicant bodies were istructed to submit to the RA MoF within 5 days incomplete or rejected samples of budget programs and measures calculation of cost-measures to be included in the budget proposals (It has already been submitted by 37 bodies, which are being studied by the employees of the Ministry of Defense of the Republic of Armenia, and about 11 bodies have not yet submitted a response letter) and data of employees authorized to work with the System to organize training in order to use the System. It should also be mentioned that on 03.08.2020 a training on system operation (filling / sending data) has already been organized for the RA Police, and in the near future it is planned to organize a training for other law enforcement agencies (RA Ministry of Defense, National Security Service, State Security Service, etc.)The trainings are continuous (Trainings will be organized for the relevant employees of the RA Ministry of Finance (approval / rejection)).
|  | 22.1.2 Through automated costing system implementation of budget programs costing within 2023 budget process | Within the framework of the 2023 budget process, the budget programs costing were carried out through an automated budget program costing system. | Within one month after the adoption of 2021 RA State Budget execution report | Budget Process Organization Department
23․1 | Adaptation of electronic budget reporting system to program budgeting requirements | Adaptation of electronic budget reporting system to program budgeting requirements | Availability of reports on the implementation of the RA state budget by program classification | 2019 December | Budget Execution Reporting Department | - | The measure is completed, and the reports on the execution of the first quarter of the RA 2019 state budget in program format on the execution of both financial and performance indicators have been submitted by the bodies responsible for the execution of the programs through the electronic budget reporting system. Before that, the system was tested, on April 1-3, 2019 trainings were organized for 64 specialists responsible for preparing report, the system was introduced in all state bodies, and the latter were assisted in the introduction and operation of the system. As a result, the quarterly (incremental) reports on the execution of the RA 2019 state budget were submitted to the RA Prime Minister's Office in program format. During the year, activities hav been carried out to solve the problems identified during the operation of the system.
24․1 | Expenditure arrears accounting | Collection and analysis on expenditure arrears in terms of performance monitoring of financial programs envisaged by quarterly (incremental) budget allocations, analysis of the causes of failure, as well as obligations assumed by the authorities | The RA public authorities and territorial administration bodies carry out the accounting of arrears Information on arrears is included in the reports on the execution of the RA state budget | 2020-2023 | Expenditures financing department | - | The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses. Each year the chief budget executive body submits to the Budget Execution Department information on the absence of arrears on state budget expenditures, which is recorded in the reports on the exeution of the RA state budget. (link: http://www.minfin.am/hy/page/byujei_operativ_hashvetvutyunner/): During the reporting period, there were no cases of insufficiency of funds or non-payment due to other unjustified reasons, which in turn will lead to accumulation of budget expenditure arrears.
Inclusion of information on arrears in the quarterly reports on the RA state budget execution
In the RA Government draft decision "On measures to ensure the execution of the 2021 RA state budget" make an addition in the point addressed to the heads of the public authorities and territorial administration bodies of the Republic of Armenia, provide summary information on expenditure arrears, together with the analysis of the programs implemented by the Chief Budget executors, the monitoring of the implementation of quarterly (incremental) thresholds, and the reasons for failure in the explanations to br submitted to the RA Ministry of Finance
25․1 | Development of a system for integration with the electronic accounting software modules of the human resources database | 25.1.1.In all state bodies, where the transfer of human resources data is not carried out through the accounting information program, the inventory of the current situation regarding the transfer of personnel data to the accounting | Terms of reference for integration of Human Resources Database with Accounting Information Program Modules has been developed and approved | 09/2020-09/2021 | Expenditures financing department |  | In most of the SBs the system is embedded, all the processes related to the personnel registration and salary fund data are carried out through the system. Work is being done to identify the state bodies where the transfer of human resources data is not carried out through the accounting information program, and an inventory of the current state of transfer of personnel data to the accounting is made
|  | 25.1.2. Development of an implementation plan in each state body, elaboration of a detailedterms of reference and approval |  | 09/2021-09/2022
|  | 25.1.3. System design and development |  | 09/2022-12/2023
25․2 | System introduction and maintenance | 25.2.1 Budgeting based on approved terms of reference | The system is embedded and all the processes related to personnel records and payroll data are carried out through the system | 09/2020-09/2021 | Budget Process Organization Department |  | Start of technichal assistance design for system implementation
|  | 25.2.2․ training Implementation |  | 09/2021-09/2022
|  | 25.2.3․ System introduction |  | 09/2022-09/2023
|  | 25.2.4. Continuous system maintenance |  | 09/2023-12/2023
26․1 | Conducting audit of salary by internal audit | 26.1.1 Internal audit departments of all public administration bodies will carry out studies on the current state of data transfer from personnel management to accounting departments. | The reports provide recommendations on wage control | 2021-2023 | Financial and Budgetary Supervision Department |  | During 2019, a payroll audit was conducted in 1 SB
|  | 26.1.2 Identification of weaknesses of data transfer, comparison gaps and control | Defects in data transfer and comparison are identified | 2023 December
27.1 | Notification to employees of data on calculation of received salary and equivalent payments and received income | 27.1.1 Implementation of changes in the remuneration calculation program in order to provide monthly notifications on the received incomes to the employees of the RA Ministry of Finance | Monthly, providing notifications to employees on the income received in the previous month (for employees who wish to receive notifications) | 03.2020-04.2020 | Project Implementation Department |  | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries during the first half of 2020.
|  | 27.1.2 Inform the state bodies and ՔՑԳ to take measures to ensure the relevant notifications to the employees in the process of calculation of remuneration by the letter of the RA Minister of Finance. | Launch of relevant processes by state bodies and ՔՑԳ to ensure the implementation of the measure | 09.2020-10.2020
|  | 27.1.3 State bodies and ՔՑԳ should take measures to ensure the relevant notifications to the employees in the process of calculation of remuneration | Monthly, providing notifications on the income received in the previous month to employees of state bodies and ՔՑԳ | 01.2021-12.2021
|  | 27.1.4 Monitoring of taken measures by state bodies and ՔՑԳ / together with Financial and Budgetary Supervision Department | Recording the results of the implementation of the processes envisaged by the measure | 01.2022-12.2023
|  | 27.1.5 If necessary, initiate the instruction of the RA Prime Minister to ensure the measure | Ensuring the implementation of the measure | 01.2022-12.2023
28․1 | Conformity of the RA Law "On Public Debt" to the standards applied by international financial institutions | 28.1.1 Elaboration of a new draft law "On Making Amendments and/o8 Supplements to the RA Law "On Public Debt" | Draft law | 10/06/2020 -28-02-2021 | Public Debt Management Department | Support is needed, but the development partner organization is not clear | Discussions are underway with international financial institutions to obtain technical assistance for the implementation of the measure
|  | 28.1.2 Draft agreement with CBA | Opinion of the RA Central Bank on the Draft | 01/03/2021 - 30/03/2021
|  | 28.1.3 Draft expertise with WB and IMF | Expertise conclusion / report | 01/04/2021 - 30/05/2021
|  | 28.1.4 Draft circulation and ensuring public discussions | Summary of the results of the public discussion | 01/06/2021 - 30/07/2021
|  | 28.1.5 Summary of proposals, draft revision and submitting to the RA Government for consideration | Revised draft law | 01/08/2021 - 28/10/2021
29․1 | Increasing the share of deficit financing in the state budget each year at the expense of net domestic borrowing | 29.1.1 Introducing at least 50.0% deficit financing share in the draft 2021 RA State Budget at the expense of net domestic borrowing | 2021 budget proposal | According to the term defined by the decision of the RA Prime Minister on starting the 2021 budget process. | Public Debt Management Department |  | The share of deficit financing at the expense of net domestic borrowing was forecasted and presented at 94.5% for 2021 in the MTEF 2021-2023
|  | 29.1.2 Introducing at least 50.0% deficit financing share in the draft 2022 RA State Budget at the expense of net domestic borrowing | 2022 budget proposal | According to the term defined by the decision of the RA Prime Minister on starting the 2022 budget process. |  |  | 2021-2023The share of deficit financing at the expense of net domestic borrowing was forecasted and presented at 82.4% for 2022 in the MTEF 2021-2023.
|  | 29.1.3 Introducing at least 50.0% deficit financing share in the draft 2023 RA State Budget at the expense of net domestic borrowing | 2023 budget proposal | According to the term defined by the decision of the RA Prime Minister on starting the 2023 budget process. |  |  | The share of deficit financing at the expense of net domestic borrowing was forecasted and presented at 100.0% for 2023 in the MTEF 2021-2023:
30․1 | Monitoring the financial statements of public sector organizations by the MoF | The measure is on regular basis. The monitoring of the financial statements of the public sector organizations is carried out by the Accounting and Audit activity Regulations, Reporting Monitoring Department, as a result of which, a "Professional Directory" periodical is provided to public sector organizations to clarify the identified problems and inaccuracies. | Financial statements in accordance with the RA Public Sector Accounting Standard (IAS) | 3rd ten days of each year 2019-2023 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | In April 2020, a letter was sent to public sector organizations to submit their 2019. 2019 transaction log and financial statements for monitoring purposes. The already submitted financial statements are monitored, and after summarizing the results, they are submitted in writing to the relevant public sector organizations. At the same time, based on the monitoring results the 9th և 10th issues of the Professional Directory were prepared in 2020 and sent to the public sector organizations.
30․2 | Methodology review (as needed) | 30.2.1 The review of the public sector accounting methodology will be carried out in case of necessity. | Improved regulatory framework | 2019-2023 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | The draft law "On Making Amendments to the Law on Accounting of Public Sector Organizations" has been developed by the Ministry of Finance. The draft has already been approved by the RA NA Standing Committee on Finance and Credit, has been included in the agenda of the regular sittings of the RA NA for discussion in the first reading, which will take place in autumn, 2020.
2020-03-30 | Implementation of the qualification process for chief accountants of public sector organizations | 30.3.1 The qualification process for chief accountants of public sector organizations is on regular basis. It is envisaged to organize and conduct qualification examinations for public sector accountants at least 4 times a year. | Qualified Chief Accountants of Public Sector Organizations | 3rd ten days of each year 2019-2023 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | The qualification procedure of the public sector accountant, the list of questions included in the questionnaire և the composition of the qualification commission were approved by the orders of the RA Minister of Finance. About 25 applications have been received to participate in the Public Sector Accountant qualification examination, but due to the state of emergency, no examination has been conducted yet. After the end of the state of emergency, the planned examinations will be held as soon as possible.
31․1 | Development of a methodology for consolidating financial statements | 31.1.1 The draft consolidation methodology has been elaborated and will be reviewed by international experts within the activitis on GFMIS introduction | Consolidation methodology is available | 3rd ten days of December, 2020 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | The draft consolidation methodology has been developed and will be reviewed by international experts as part of the activity on the introductionof the GFMIS. The tender of international experts involved in the GFMIS consolidation methodoloogy review is not over yet, no expert has been selected.
31․2 | Elaboration or acquisition of a joint software program for the purpose of consolidation | 31.1.2 The software required for consolidation can be obtained with the appropriate financial resources | Software program necessary for consolidation | 3rd ten days of December, 2023 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | This operation is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS.
31․3 | Preparation of interim consolidated financial statements at the ministries level | 31.3.1 In case of existence of software program, preparation of consolidated financial statements at the level of at least one ministry, including the ministry and its subordinate SNCOs. | Interim consolidated financial statements are submitted at the ministerial level | 3rd ten days of December, 2023 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 և 31.2.
32․1 | Completion of the necessary sub-legislative field | 32.1.1 Elaboration of draft legal acts deriving from the RA laws ՀՕ-282-Ն "On Accounting", ՀՕ-283-Ն"On Auditing activity", ՀՕ-284-Ն "On Accounting and auditing activity regulation and public control", adopted by the RA National Assembly on December 4, 2019 and submitting for approval. | 1. New specialized structures for regulation and control of sectors - Public oversight board model, 2. An effective quality control system, 3. Adjusted scope of entities subject to compulsory audit | 3rd ten days of May, 2020 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | Currently, the RA Government draft decision "On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Computer Software Enabling Accounting" has been submitted to the expert opinion of the RA Ministry of Justice. The draft minimum list of data included in the register of expert accountants, auditors and auditing companies has been developed, which must be approved by the Public Oversight Board in accordance with the Law.
|  | 32.1.2 Implementation of the accreditation process of specialized structures |  |  |  |  | By the RA Minister of Finace order 119-A, dated April 20, 2020 AAAA is accredited as a specialized body accredited within the meaning of the RA Law on Accounting և Regulation of Auditing Activities and Public Control.
|  | 32.1.3 Organizing the process of establishing a public control council (elaboration of a charter and necessary legal acts, formation of public control council) |  |  |  |  | The public oversight board has been formulated in accordance with the Orders of the RA Minister of Finance, dated June 30, 2020 . The schedule of the latter was approved by the RA Minister of Finance order No. 196-L, dated July 8, 2020 No. 196-L.
32․2 | Staff training | 32.2.1 Organizing the staff training process, ensuring the appropriate level of skills. | Appropriate level of capacity | 3rd ten days of each year for the period of 2020-2021 | Accounting and Audit activity Regulations, Reporting Monitoring Department |  | In April-May, 2020, online seminars-discussions were organized for the employees of the Accounting and Auditing Activity Regulation Department on the requirements of the main provisions of the 3 new laws regulating the areas of accounting and auditing activities.
33․1 | Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | 33.1. Since 2010 for the purpose of implementing reforms in the public financial management system, a system of fiduciary control of state non-commercial organizations has been developed in the field of financial management and control of state organizations. In order to pilot the elaborated system in practice and elaborate an effective fiscal control system, the RA Government with the support of the WB inititated "SNCO Fiduciary Control syetem pilot program" in 2010. At this stage, the elaborated system is being studied, work is being done to modernize it and bring it in line with the current system of SNCO activities. | Existence of an up-to-date system for monitoring the financial and economic activities of SNCOs | 2020-2021 | Accounting and Audit activity Regulations, Reporting Monitoring Department | Support is needed, but the development partner organization is not clear | In April-May, 2020, online seminars-discussions were organized for the employees of the Accounting and Auditing Activity Regulation Department on the requirements of the main provisions of the 3 new laws regulating the areas of accounting and auditing activities.
|  | 33.1.2 Development of non-financial (productive) indicators of SNCO activities |  | 2021-2022 |  |  | At the same time, discussions were held with a number of authorized bodies.
|  | 33.1.3 . Introduction of non-financial (productive) indicators elaborated for SNCO activities |  | 2022-2023 |  |  | The measure will take place after the implementation of 33.1.1 and 33.1.2 stages
34․1 | Elaboration and introduction of new e-procurement system software | 34.1.1. Elaboration of business model an dterms of reference necessary for introduction of a new e-procurement system | Existence of business model terms of reference for introduction of a new e-procurement system | 2020-12-30 | Procurement Policy Department |  | Activities have been carried out with donor organizations to develop a business model and terms of reference for the introduction of a new e-procurement system. In particular, an agreement was reached with the European Bank for Reconstruction and Development to elaborate a new e-procurement software system with the latter's technical and financial assistance, according to which the it is expected to obtain from EBRD business model rationale for the introduction of the new e-procurement system. Given that there is no response from the bank yet, the technical task of selecting a consultant for the implementation of the consultant in the framework of the introduction of the GFMIS envisages the elaboration of a business model for the introduction of the e-procurement system, provided that it will not be implemented by the consultant. Given that there is no response from the bank yet, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model և technical task for the implementation of the e-procurement system, provided that it will not be implemented by the consultant if they are implemented by the EBRD. The issue related to the substantiation of the business model proposed by the bank is currently being discussed, after the clarification of which the relevant decision will be made.
|  | 34.1.2.Introduction of e-procurement system | New existing e-procurement software | 2020-12-30
35․1 | Elaborate RA Government draft decision on the introduction of a unified system for planning and determining the estimated prices of items with similar characteristics automatically | 35.1.1 Elaborate RA Government draft Decision | Draft decision of the RA Government based on the opinions received from the RA public administration bodies | 2020-12-30 | Procurement Policy Department | - | The relevant proposals for the implementation of the mentioned measure were received and summarized from the RA public administration bodies based on the letter 01/26-1/3308-2020 of the RA Minister of Finance, dated 21.03.2020.
36.1 | Making changes in the RA Law "On Procurement" | 36.1.1. Elaboration of draft law (Draft) | Draft law | 2020-03-30 | Procurement Policy Department | - | The RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Amendments to the RA Law on State Duty", "On Making Amendments an supplements to the RA Civil Procedure Code" have been elaborated and submitted to public government bodies, international donor organizations and civil society for consideration. Discussions with the EU SIGMA Program Expert Group are ongoing.
|  | 36.1.2. Draft circulation and ensuring public discussion | Public discussion summary sheet | 2020-04-30
|  | 36.1.3 Project expertise in terms of compliance with WB-agreed Alternative Procurement Terms | Expertise conclusion / report | 2020-06-30
|  | 36.1.4 Project expertise by EU SIGMA project experts in terms of compliance with the terms of the WTO PPA and Armenia-EU Comprehensive Partnership Agreement | Expertise conclusion / report | 2020-06-30
|  | 36.1.5 Summarizing proposals, revising the draft and submitting to the RA Government for consideration | Revised draft law | 2021-12-30
37․1 | Testing of financial management and control (FMC) system methodology | 37.1.1 Testing of the elaborated FMC system methodology in at least two RA public sector organizations | FMC system piloted methodology | December, 2020 | Financial and Budgetary Supervision Department |  | As of 2019, there are still draft legal acts for the introduction of the FMS, which need to be reviewed once again, considering them from the point of view of the implementation of the PB system, discussing them with the Civil Service Office. In order to test the FMS system, an agreement was reached in 2019 with the RA Ministry of Education and Science (there is an official letter from the Ministry of Finance and an agreement with the pilot ministry) to pilot the above methodology. The second state body that was selected and an agreement reached with the latter's representatives is the RA Ministry of Labor and Social Affairs.
37․2 | Adoption of FMC concept and FMC legal acts | 37.2.1 Elaboration of FMC concept and FMC legal acts based on piloted methodology | FMC adopted concept and legislation | 2021-2022 | Financial and Budgetary Supervision Department |  | During 2018-2019 the draft FMS concept was elaborated with the support of GIZ
37.2.2 Approvall of FMC and FMC legal acts
37․3 | Introduction of FMC system in public sector organizations | 37.3.1 Development and approval of a program of measures for the implementation of the FMC system | The process of embedding the FMC system is carried out according to the set schedule | Beginning from 2022 | Financial and Budgetary Supervision Department |  | As the measure is related to event 37.1, the work related to this event will start after the testing of the FMS system methodology and adoption of FMS concept and relevant legislation
37.3.2 Introduction of FMC system in line with program of measures, besides training of professionals included in FMC system will be implemented
38․1 | Approval of external assessment methodology of internal audit quality | Approval of a proven methodology for conducting an external assessment of the internal audit quality | Order endorsed by the RA Minister of Finance "On approving the procedure for conducting external evaluation of the quality of internal audit" | December, 2019 | Financial and Budgetary Supervision Department |  | In the context of this measure, with the support of the World Bank, an external quality assessment manual was developed, which was piloted in 2 organizations of the RA public sector. RA Minister of Finance draft order has been elaborated. The draft order was discussed with the representatives of state bodies, was finalized and is ready for approval.
38․2 | Implementation of external assessment of internal audit quality | In accordance with the approved methodology | All the public sector organizations where an internal audit system is introduced have been subject to external evaluation by the MoF. Report on the quality of internal audit of the RA public sector | 2020-2022 | Financial and Budgetary Supervision Department
38.2.1 Risk assessment of RA public sector organizations
38.2.2 Preparation of an annual plan for implementation of external assessment plan
38.2.3 Implementation of external assessment
39․1 | Define internal audit and external audit cooperation procedures | 39.1.1 Implementation of joint works with the consent and participation of the MoF and AC to develop and approve the procedure for internal audit և external audit cooperation | Approval of the joint legislatives act of the RA Minister of Finance and Chairman of the RA Audit Chamber "On Approving the Procedure for Internal-External Audit Cooperation" | December, 2023 | Financial and Budgetary Supervision Department |  | The procedure for internal-external audit cooperation has been under development since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version և after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs.
40․1 | Approval of performance auditing methodology | 40.1.1 Revision of the performance auditing manual/guideline, submission to stakeholders, summary and approval | Execution audit procedure approved by the order of the RA Minister of Finance | 2019-2020 | Financial and Budgetary Supervision Department |  | RA Minister of Finance draft order "On approving the performance audit manual" has been developed, which is in the process of revision, within the framework of which it is necessary to ensure the connection of the performance audit with the embedded PB system, which which will provide an opportunity to comprehensively assess the results of the programs of the PBs implementing budget programs considering it not only in the context of financial but also in the context of non-financial performance indicators.
40․2 | Increasing the role of performance auditing in internal audit legislation | 40.2.1 Making changes/supplements to the RA Minister of Finance Order N 143-Ն, dated February 17, 2012 | Requirement stipulated in the Internal Audit legislation, according to which the performance audit will make up 30% of the annual internal audit program | December, 2020 | Financial and Budgetary Supervision Department
40.3 | Development of performance auditing skills of internal auditors operating in RA public sector organizations | 40.3.1 Organizing courses on performance auditing | Internal auditors in RA public sector organizations trained in auditing | 2020-2023 | Financial and Budgetary Supervision Department
41․1 | Elaboration of a program for the development of professional knowledge and skills of internal auditors | 41.1.1 Assess the capacity of internal auditors | Approved program for developing the professional knowledge and skills of internal auditors | December, 2020 | Financial and Budgetary Supervision Department
41.1.2 Identifying the professional needs of internal auditors
41.1.3 Elaboration and approval of program for the development of professional knowledge and skills of internal auditors
41․2 | Optimization of continuous professional training courses for internal auditors | 41.2.1 Evaluation of approaches and program for organizing continuous professional training courses for internal auditors | Internal auditors are aware of the requirements of the RA legislation on internal audit, theoretical knowledge of internal audit and practical skills | 2020-2022 | Financial and Budgetary Supervision Department
41.2.2 If necessary, review according to identified needs
41․3. | Development of an online information system for the continuous professional training of internal auditors | 41.3.1 Design of an online information system for the continuous professional training of internal auditors | Online Information System for Continuous Professional Training of Internal Auditors | 2020-2022 | Financial and Budgetary Supervision Department
41.3.2 Operating of an online information system for the continuous professional training of internal auditors
41․4 | Review of the Public Sector Internal Auditor Qualification Procedure | 41.4.1 Legislation review and making amendments | Improving the quality of public sector internal audit | December, 2021 | Financial and Budgetary Supervision Department
42․1 | CHU personnel recruitment and capacity building | 42.1.1 staff and capacity needs assessment required for the performance of functions | Necessary capacities are available in CHU | 2019-2021 | Financial and Budgetary Supervision Department |  | The relevant subdivision, which was carrying out the functions of the CIA, was dissolved on February 24 of this year and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CIA.
42.1.2 CHU personnel recruitment
42.1.3 CHU Development and implementation of a staff capacity development program
43․1 | Review, update of financial-budgetary supervision legislation, elaboration of new methodology for implementation of financial-budgetary supervision | 43.1.1 Study, evaluation and gap analysis of financial-budgetary supervision legislation | By-laws defining the modern methodology of financial budget control | 2020-2021 | Financial and Budgetary Supervision Department |  | In the context of this group of measures, the main problems in the system of financial-budgetary control were formulated in 2018-2019. The RA Government decision "On defining the procedure of financial and budgetary control of the Republic of Armenia" and declaring null and void the RA Government decisions dated July 11, 2002 N 1112 N and February 23, 2012 N 207 " has been elaborated which is under discussion
43.1.2 Financial-budgetary supervision develop and approve a new methodology for risk-based audits, while highlighting issues related to the performance of Financial-budgetary supervision activities, as well as cooperation with other auditing, oversight or control bodies.
43.2 | Capacity building of specialists in the field of financial-budgetary supervision | 43.2.1 Capacity evaluation of financial-budgetary supervision specialists and elaboration of a development plan | Specialists in the field of financial-budgetary control have professional skills and have relevant knowledge | 2022-2023 | Financial and Budgetary Supervision Department
43.2.2 Training of financial-budgetary supervision specialists according to the directions of the capacity development program
43․3 | Availability of databases necessary for risk assessment | Access to databases available in state bodies | Introduction of a new risk system based on the analysis of complete, substantiated and justified information | 2020-2023 | Financial and Budgetary Supervision Department
44.1․ | Elaboration and approval of public assets management methodology and legal acts necessary for its introduction | 44․1․1. Study of the international experience of government financial and non-financial assets management | Existing methodology on management of financial and non-financial assets of the Government, and legal acts approved in accordance with the RA legislation | 2020-2022 | Budget Process Organization Department | Discussions were held to develop a methodology for managing public assets, and an agreement was reached with the IMF to carry out this work with the support of the latter. | Measures for the introduction of the public asset management system were envisaged by the second PFMS strategy of the RA Government and the relevant action plan, but they were not implemented due to lack of technical assistance during 2016-2018. The elaboration of a public asset management methodology requires the involvement of external experts with relevant experience in the field of public asset management, for the purpose of which discussions are currently underway with partner international organizations to carry out this work with their support.
44.1.2. Development and adoption of legislative acts necessary for the introduction of methodology based on international experience
44.2 | Implementation of trainings on asset management techniques in accordance with the approved legislation | 44.2.1.Organization of trainings on asset management techniques in accordance with the approved legislation | Specialists trained in accordance with the law on public assets | After the approval of the relevant legislation | Budget Process Organization Department | Support is needed, but the development partner organization is not clear
44.3 | Preparation and monitoring of financial and non-financial asset registers | 44.3.1. Piloting of financial և non-financial asset registers in state bodies | Regular reporting on the assets monitoring | After the approval of the relevant legislation | Budget Process Organization Department | Support is needed, but the development partner organization is not clear | The activities to be carried out within the framework of this measure are the implementation of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure
44.3.2. Monitoring of financial և non-financial asset registers
44.3.3. Identification of problems during the monitoring, submission of proposals for their solution
45.1 | The definition of procedures for the sale, transfer, alienation process, and the right to use non-financial assets will be reviewed. | 45.1.1. Procedures for the sale, transfer, alienation of non-financial assets will be reviewed, appropriate procedures will be developed and approved.to define their rights of use | Procedures for the sale, transfer, alienation process and the right to use non-financial assets are approved. Alienation of assets is carried out in accordance with established procedures Asset disposal reports | 01/2022-06/2023 | Budget Process Organization Department | Support is needed, but the development partner organization is not clear | The activities to be carried out within the framework of this measure are the implementation of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure
|  | 45.1.2 Organizing staff training on asset disposal techniques |  | 06/2023-12/2023
48.1 | Practical application of the Public Investment Management (PIM) Manual in the budget process | Compliance of the investment projects included in the budget proposals of state bodies with the standard criteria and requirements for the selection of investment projects reflected in the PIM manual developed by the RA Ministry of Economy | The public investment projects included in the approved 2022 budget have been elaborated in accordance with the requirements of the PIM manual | October, 2021 | Budget Process Organization Department | Discussions were held to ensure the practical application of the PIM manual in the budget process, and an agreement was reached with the IMF to carry out this work with the support of the latter.
49.1 | Monitoring of public investment projects | Analysis of financial and non-financial performance indicators of public investment projects in accordance with the standards and criteria of the PIM manual for the evaluation of investment projects | Published report on the results of the monitoring of public investment projects | 01/2022-06/2023 | Budget Process Organization Department | In order to monitor the implementation of public investment projects, discussions have been carried out and an agreement was reached with the IMF on the implementation of it with their assistance. | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines.
|  | Preparation and publication of a report on the results of the monitoring of public investment projects |  | 06/2023-12/2023
50.1․ | Implementation of public finance management reform program in local self-government bodies | 50.1.2. Pilot evaluation of Public Financial Management Capacities in several local self government bodies | Study reports Transparent and participatory budget process plans at the local level | 09/2020-09/2021 | Budget Process Organization Department, TAM | Support is needed, but the development partner organization is not clear | • Organizing training for the administrative staff of the local self-government bodies of the enlarged communities on program budgeting methodology, its application and raising awareness on PB (about 20 communities in the first half of 2020): • Providing technical assistance և advice to the financial managers of the municipalities and to the staff members involved in the process of preparing the annual program budget: • Providing technical assistance and consulting on the development of a brief annual community program budget and holding public hearings in 52 enlarged communities: • Providing technical assistance and consulting on annual community program budget monitoring and development of evaluation plans in large communities: • Elaboration and publication of a "Residents' Participation in the Local Budgeting Process" participatory budgeting manual (The manual is available): • Elaboration of a manual on “Gender Budgeting at the Community Level” (The manual has been elaborated and is being translated into English):
|  | 50.1.3. Assessment of public investment management capacity in Yerevan Municipality for the purpose of identifying the obstacles to tareted and effective investment execution |  | 09/2021-09/2022
|  | 50.1.4. Determining public financial management reform priorities |  | 09/2022-12/2022
|  | 50.1.5.Capacity building |  | 01/2023-09/2023
|  | 50.1.6. Elaboration of methodology aimed at improving the transparency and participation of the budget process |  | 01/2023-12/2023
50.2․ | Monitoring and full implementation of the public financial management reform program in local self-government bodies | 50.2.1. Pilot implementation of public financial management reforms in selected local self government bodies (program budgeting, PIM, revenue management and etc), testing of methodology | Local self government bodies employees capable of implementing public financial management reforms Transparent-participatory budget process at the local self government bodies | 09/2020-12/2021 | Local self government bodies, Budget Process Organization Department | Support is needed, but the development partner organization is not clear | Study of the preliminary status of the use of IFRS-based accounting manual and standards in large communities, identifying gaps and making recommendations for improving the system Study of the preliminary situation of the property management process of large communities, identification of gaps and submission of proposals for the improvement of the system. Preliminary study of the functions, rights and scope of responsibilities of the administrative heads of the settlements of the enlarged communities and submission of proposals for the improvement of the activities.
|  | 50.2.2. Training and capacity building of the staff of the piloted local self government bodies |  | 01/2022-12/2022
|  | 50.2.3. Improving the methodology based on the accumulated experience and full introduction at the local self government level |  | 01/2022-06/2022
|  | 50.2.4. Introduction of public financial management reforms in all local self government bodies |  | 06/2022-12/2023
|  | 50.2.5. Monitoring the implementation of public financial management reforms |  | 01/2023-12/2023
55.1 | Review of the GFMIS tender document | Creation of GFMIS working group, which will include representatives relevant to each of the functions of each module of the GFMIS, as well as representatives from other state bodies and organizations. | The complete set of tender documents for the elaboration of the GFMIS tender implementation package has been revised and made complete. | 01/2020-06/2020 | GFMIS introduction activities management board established by the MoF order N 696-А, dated 24.12.2019 | WB/RF MoF | On May 7 of this year, the first stage of the two-stage procurement process for the selection of a consultant assisting the Ministry of Finance in the process of introduction of the GFMIS was organized. By the Decision N 1, dated 05․03․2020 of the two-stage tender evaluation commission approved the pre-qualification announcement for the acquisition of consulting services within the framework of the GFMIS introduction program. 7 organizations applied for pre-qualification, of which 5 became pre-qualified participants. The stage of negotiations with them has started, which is in progress.
Review of GFMIS main components and tender documents, finalization
55.2 | GFMIS procurement | Compilation of the complete package of documents for the implementation of GFMIS tender, announcement of the tender | The complete package of documents for the implementation of the GFMIS tender has been drawn up, the tender has been held | 2020-2021 | GFMIS introduction activities management board established by the MoF order N 696-А, dated 24.12.2019 | WB/RF MoF
GFMIS tender implementation
Awarding a contract with the winning organization of the GFMIS tender
55.3 | GFMIS introduction piloting | Elaboration of the GFMIS program implementation plan, clarification of detailed terms of reference | GFMIS embedded in accordance with the terms of reference | December, 2021 | GFMIS introduction activities management board established by the MoF order N 696-A, dated 24.12.2019 | WB/RF MoF
Design and elaboration of GFMIS functional and technical modules
System Testing (Pilot Data Transformation և Migration)
56.1 | GFMIS full introduction | Acquisition of computer equipment, including licenses for operating systems and office packages envisaged for customers computes | GFMIS embedded in accordance with the terms of reference | December, 2022 | GFMIS introduction activities management board established by the MoF order N 696-A, dated 24.12.2019 | WB/RF MoF
System introduction and pilot operation in parallel with existing systems
Final data migration and end of previous systems operation
56.2 | GFMIS users training | Drawing up training plan-schedule for specialists of the MoF, state bodies using GFMIS | GFMIS users are trained | December, 2022 | GFMIS introduction activities management board established by the MoF order N 696-A, dated 24.12.2019 | WB/RF MoF
Implementation of trainings
56.3 | GFMIS maintenance | Elimination of detected defects | Existence of a properly functioning GFMIS automated system | December, 2023 | GFMIS introduction activities management board established by the MoF order N 696-A, dated 24.12.2019
Ongoing system maintenance
* It is filled when the measure has been implemented and/or is being implemented with the support of a Development Partner Organization specifying the name of the measure or the component of the measure or which measure or the component needs the support of development partner organization