## PFM
ANNUAL REPORT FOR 2021 On the implementation of the action plan measures to be implemented in PFMSR 2019-2023
Sector/component | Target | Measures | Performer | Co-performer | Deadline | Deadlines revised by the RA Government Decision N 283 -Լ, dated 04․03․2021 | Deadlines revised by the RA Government Decision N 2189 -Լ, dated 30․03․2021 | Outcome evaluation indicators | Progress of measures and done activities/achievements (30.12.2020) | Progress of measures and done activities/achievements (30.12.2021) | Outcome | Actual execution date | Status (see used terms) | Next steps (activities) | Issues and risks related to measure implementation | Risk management measures | Development partner organization supporting the implementation of the measure present (suggested)
1 | 2 | 3 | 4 | 5 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1․ FORECAST of MACROECONOMIC AND BUDGET INDICATORS, FINANCIAL RISK ACCOUNTABILITY
1. Forecast of macroeconomic and budget indicators | 1. Elaboration of final versions of the model (s), introduction in the Ministry of Finance and full operation | 1.1 relaboration of final versions of DSGE models | MoF | - | December, 2019 |  |  | Availability of up-to-date tools for fiscal policy analysis and medium-term macroeconomic forecasts | DSGE model is elaborated | DSGE model is elaborated | Availability of DSGE model of macroeconomic forecasts | December 2019 | Completed
|  | 1.2 Introduction and full operation of DSGE models |  |  | 2020-2023 |  |  | Introduction of new tools and use in the budget process, more comprehensive and accurate estimates and analysis on impact of fiscal policy on the economy | DSGE model was tested and finalized during 2020 (as a result of joint working discussions with IMF experts) . Preliminary versions of relevant documents have been developed. Discussions on the elaboration of a working document and elaboration of separate sections were carried out jointly with IMF experts. With the help of the model, the effects of the coronavirus multifaceted fiscal measures on the Armenian economy were assessed. Based on the results, the 2021-2023 MTEF macro-fiscal framework was created (including the preliminary version of the draft law on the state budget for 2021). Later, in the conditions of new information available and current developments, re-evaluations were carried out through the model, on the basis of which the macro-fiscal framework underlying the 2021 State Budget was formed. An accompanying analytical and evaluation document and model manual has been developed. Discussions on the development of a working document and elaboration of separate sections were carried out jointly with IMF experts. The model assesses the social, economic and financial impacts of the implemented and to be implemented fiscal measures. Based on the results, the 2021-2023 MTEF macro-fiscal framework was created (including the preliminary version of the draft law on the state budget for 2021). Later, in the conditions of new information available and current developments, re-evaluations were carried out through the model, on the basis of which the macro-fiscal framework underlying the 2021 State Budget was formed | During 2021, the model was used in the process of building the MTEF 2022-2024 and 2022 state budget macro-fiscal framework, a quantitative assessment of the impact of the forecast fiscal measures was carried out, and a forecasting policy scenario was developed. The final documentation of the related analytical-evaluation activities performed during the elaboration of the model, in particular, the article "Estimates of Fiscal Multipliers for Armenia" (Estimates of Fiscal Multipliers for Armenia), as well as elaboration of a manual for using the model was carried out (The article was presented at the 11th annual conference of the Armenian Economic Association). The final editing of the joint working document of the RA Ministry of Finance and the IMF was carried out together with the IMF experts taking into account the comments and suggestions of the reviewers. | Application of DSGE model in 2021 and 2022 budget process | Activities envisaged for 2020 and 2021 are completed | It is a periodic process | It is envisaged to continuously apply the model in budget processes (Formation of macro-fiscal framework underlying the MTEF and budget message) It is envisaged to use the model for the assessment of policy/measures/shock impacts derived from the imperative of time. |  |  | IMF(RF MOF)
| 2. Assessing the effects of deviations between fiscal policies planned and actually implemented on the basis of macro-founders and fiscal rules | 2.1 . Detection of deviations between planned and actually implemented fiscal policy and impact assessment | MoF | - | 2020-2023 |  |  | Improved estimates of fiscal risks at the macroeconomic level. | It is envisaged to implement starting from 2021, within 10 days after the publication of the annual state budget indicators, within 15 days after the publication of the annual GDP. | On the basis of actual data of 2020, the deviations of the planned and actual fiscal policies were assessed, and their macroeconomic impacts were given. The assessment results were presented in the form of a presentation, and were included in the annual report of 2020 state budget. | Assessment of planned and actual fiscal policy deviations and their macroeconomic impact and reflection in the annual report of the 2020 state budget. | The actions planned for 2021 are carried out | It is a periodic process | In the future, it is planned to carry out the activities regularly, each year when the official indicators of the previous year are published during the first of the year. |  |  | IMF
Assessments of the effects of fiscal policy, deviations from the planned ones on the economy
| 3. Ensuring staff with relevant qualifications and skills | 3.1. Implementation of measures aimed at raising the qualification of the staff | MoF | - | 2019-2023 |  |  | Availability of staff with relevant qualification and skills | During 2020, no business trips were carried out due to the limitations caused by the limitations caused by the coronavirus. In January, only one employee of the Macroeconomic Policy Department was trained within the framework of the trainings organized by IMF in Vienna (JVI). However, employees participated in other available online courses, including regular webinars initiated by JVI. Employees were encouraged through the remuneration fund provided to the department, as well as other promotional methods were applied. | Conditioned by the cancellation of the IMF training due to the epidemic and the changes in the training format, six employees of the Macroeconomic Policy Department (Department) was trained in the JVI organized online courses during 2021. Employees also participated in other available online courses, as well as regular webinars initiated by JVI. in the framework of bilateral cooperation between the Financial Research Institute of the Ministry of Finance of the Russian Federation 6 employees of the Department participated in the regular weekly trainings and discussions. 11 employees of the Department took part in the trainings organized by the OGResearch Research Center on the initiative of the Financial Research Institute of the RF Ministry of Finance | Training aimed at capacity building of the staff dealing with macroeconomic forecasting | Activities envisaged for 2020 and 2021 are carried out | It is a periodic process | In the future, it is planned to continue the implementation of measures aimed at raising the professional capacity and qualifications of the staff. |  |  | IMF/RF MOF
| 4. Improving the function of fiscal risk assessment | 4․1 Expanding the coverage of fiscal risk assessment, improving the methodology | MoF | - | 2020-2023 |  |  | Fiscal risk assessments include an expanded range of fiscal risk sources | Fiscal risk assessments related to the activities of 20 organizations operating in the infrastructure (energy, transport, water economy) sectors were carried out, which also included the analysis of contingent liabilities arising from the contracts of public-private partnership companies. The latter were reflected in the document RA 2021-2023 MTEF (link: http://www.minfin.am/en/page/petakan_mijnazhamket_tsakhseri_tsragre/). At the same time, the work on expanding the scope of assessment of fiscal risk sources continues. | Fiscal risk assessment activities related to the activities of organizations operating in infrastructure (energy, transport, water economy) and other sectors, including the analysis of contingent liabilities arising from public-private partnership format, as well as contracts with the right to purchase electricity; which were reflected in the document of RA MTEF 2022-2024. and the state budget for 2022. | Inclusion of analysis in budget documents for 2021 and 2022 on fiscal risk assessments of 20 infrastructure companies and contingent liabilities arising from the contracts of PPP companies ․ |  | In Progress | Expansion of the scope of fiscal risk assessment sources is ongoing |  |  | ADB/IMF
[8 empty] | Improved fiscal risk methodology | The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in terms of public-private partnership projects was approved by RA Government decision N1785-Լ , dated 06․11․2020. With the support of ADB consultants the RA Minister of Finance draft Order "On Approving Methodological Guide for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" | The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in terms of public-private partnership projects was approved by RA Government decision N1785-Լ , dated 06․11․2020 for the implementation of the functions assigned to the RA Ministry of Finance per the RA Law "On Public-Private Partnership". At the same time Decision on setting the maximum permissible limit of public-private partnership obligations of the Republic of Armenia (in terms of contingent liabilities) was approved by the RA Governmnet Decision N955-Լ, dated 10․06․2021. With the support of ADB consultants the RA Minister of Finance draft Order "On Approving Methodological Guideline for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" A brief overview of the assessment of the relevant range of specific fiscal risks was provided. The draft decision of the RA Government defining the maximum limit of direct liabilities of PPPs is being developed. | Approval off the methodology for calculating and evaluating the contingent liabilities of the RA in terms of PPP projects (RA Government Decision N1785-Լ , dated 06․11․2020•) Setting the maximum permissible limit of PPP obligations (RA Governmnet Decision N955-Լ, dated 10․06․2021). RA Minister of Finance draft Order "On Approving Methodological Guideline for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" |  | In Progress
| 5. Development of analytical skills of fiscal risk assessment specialists | 5․1 Capacity building | MoF | - |  |  |  | Specialists with improved analytical skills in assessing fiscal risks | During the second half of the year, 2020, one employee of the department was trained within the framework of the trainings organized in Vienna (JVI). In addition, the relevant specialists of the department (3 specialists) participated in the PFRAM2.0 training course on fiscal risk assessment of PPPs organized by the IMF (developed by the WB և IMF) ։ The employees also took part in the trainings organized by the World Bank in Yerevan. In addition, training is provided as part of ADB's consulting work. | During 2021 in the scope of online JVI organized courses 2 employees of the Department were traimed, Besides employees of the Deparment participated in "Financial Analysis" and "Financial Modeling" courses organized by the International Academy of Business, as well as in the course on public-private partnership in the scope of the Commercial Law Development Program under the US Department of Commerce. | Training aimed at capacity building of the staff dealing with fiscal risk forecasting |  | In Progress | Trainings for the purpose of enhancing the professional capacities and qualifications of the personnel are of continuous nature. |  |  | ADB/IMF
2․ STATE REVENUE POLICY, TAX ADMINISTRATION
| 6. Assessing the needs of the tax environment based on the economic development priorities and opportunities | 6․1 Outline directions for further tax system reforms based on economic development priorities and opportunities | MoE | MoHTI, MoE, MoTAI | May, 2020 |  |  | The directions of further reforms of the tax system are outlined | At present, clarifications are being carried out on the Armenian economic policy, based on which the proposals on further directions of tax reforms will be derived. | As a result of the measure, the RA Ministry of Economy studied the directions of further reforms of the tax system based on the priorities and opportunities of economic development and the directions of the tax system reforms were reflected in the concept of the RA economic policy elaborated by the RA Ministry of Economy, which currently has the status of the RA Government draft decision. | Directions of further reforms of the tax system are outlined in the RA economic development policy | First half of 2021 | Completed |  |  |  | RF MOF
| 7. Reducing the scope of application of tax benefits | 7.1 Elaboration of the RA draft law "On Making Amendments to the RA Tax Code" | MoF | - | 2020-2023 |  |  | Low-efficiency, non-targeted tax benefits are eliminated |  | ADB has submitted the final Report on the reduction of the scope of tax benefits, which presents recommendations, analysis, studies and relevant calculations aimed at reducing low-efficiency, non-targeted tax benefits ADB has introduced a tool for analyzing the impact of tax expenditures, which is under study է: The reference on "Structure of tax expenditures - sectoral value added" has been elaborated, international experience has been studied. | • Elaborate a package of proposals aimed at reducing low-efficiency, non-targeted tax benefits. • Designing a toolkit for tax expenditures impact analysis. |  | In progress | 1. Elaboration of proposals on amendments to the tax legislation to eliminate low-efficiency and (or) non-targeted sectoral tax benefits, 2. Discussion of the submitted proposals with the interested public administration bodies and professional non-governmental organizations, 3. Based on the results of the discussions, development of a draft law envisaging relevant amendments and supplements to the RA Tax Code and submission to the RA Government for consideration |  |  | ADB
| 8․ Review of turnover tax burden | 8․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | 2020-2023 |  |  | As a result of the conducted studies, the turnover tax burden has been revised | The measure is implemented with the technical assistance of ADB, for which relevant international experts were involved, with whom a number of working meetings were held. At the same time, the measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. According to the measures 2 and 3 of the appendix approved by point 1 of that decision, by the third ten days of May 2021, the RA Ministry of Finance must develop draft laws envisaging increase of the turnover tax rates, decrease of the turnover tax threshold. | The first stage of receiving technical assistance for the implementation of the activiteis on the review of the turnover tax burden with ADB is completed Within the framework of ADB technical assistance, a preliminary and final report was submitted, which presented recommendations, analysis, studies and relevant calculations on turnover tax burden References on "Information on the number of economic entities operating in different taxation systems" and "Comparison of the tax burden on the general taxation system and turnover tax system" have been elaborated | Approval of measures to reduce the tax policy gap (RA Government Decision 1455-Լ , dated December 30, 2020). |  | In progress | 1. Elaboration of proposals on changes in tax legislation to determine a comparable, fair tax burden between different tax systems, 2. Discussion of the submitted proposals with the interested public administration bodies and professional-non-governmental organizations, 3. Based on the results of the discussions, development of a draft law envisaging relevant amendments and supplements to the RA Tax Code and submission to the RA Government for consideration |  |  | ADB
| 9․ Settlement of issues related to the documentation of transactions for the sale of agricultural products | 9․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2021 |  |  | Issues related to documenting transactions are settled | Measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to the 6th measure of the appendix approved by point 1 of the same decision, by 3rd ten days of May, 2021 the RA Ministry of Finance should develop a draft law on the regulation of issues related to the documentation of transactions for the sale of agricultural products and submit to the RA Government for consideration. | Activities are underway to resolve issues related to the documentation of transactions for the sale of agricultural products. Analytical work and study of international experience were carried out in the direction of the measure implementation. In the framework of the mentioned measure, 3 working discussions were held with the RA Ministry of Economy, during which the possibilities of documenting different types of both crop and animal products were discussed.: Representatives of the RA State Revenue Committee were also involved in the mentioned discussions. |  |  | In progress | 1. Elaboration of proposals for revision of tax regulations hindering the development of the agricultural sector, 2. Discussion of the submitted proposals with the interested public administration bodies and professional-non-governmental organizations, 3. Based on the results of the discussions, development of a draft law envisaging relevant amendments and supplements to the RA Tax Code and submission to the RA Government for consideration
| 10. Equivalent tax on visible wealth or property | 10․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2020 |  |  | Visible wealth or property is taxed adequately | On June 25, 2020, the RA National Assembly adopted the RA Law "On Making Amendments to the Tax Code of the Republic of Armenia" aimed at reviewing the real estate tax system. |  | Adoption of the RA Law " On Making Amendments and supplements to the Tax Code of the Republic of Armenia" On reviewing the real estate tax system. (2020 June 25) | 2020 | Completed
| 11․ Providing legal bases for the introduction of the income declaration system based on the current economic motives | 11․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2021 |  | 3rd decade of June 2022 | Legal bases for the introduction of the income declaration system based on the current economic motives is ensured | The action plan necessary for the introduction of the individual income declaration system was approved by the order No. 104-L of the RA Minister of Finance, dated April 6, 2020. b. Studies of the international experience of the system of income declaration of individuals were carried out and the results were submitted for discussion, c. The RA draft law “On Making Amendments and Addenda to the RA Tax Code” aimed at the introduction of the system of income declaration of individuals has been elaborated. At the same time, please be informed that measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to the 5th measure of the appendix approved by point 1 of the decision, by the 3rd ten days of September, 2021, the draft law envisaging introduction of the income declaration system based on the current economic motives shoud be elaborated and submitted to the RA Governemnt for consideration. | The study of international analytical experience was carried out in the direction of the implementation of the measure. The work done was discussed with the RA Prime Minister on January 11, 2022. | • Approval of the action plan for the introduction of the system of income declaration of individuals (Order of the Ministry of Finance of the Republic of Armenia 06.04.2020 N 104-L) • RA Draft Law "On Making Amendments and Supplements to the RA Tax Code aimed at introducing the system of income declaration of individuals. |  | In progress | Based on the results of the discussions on the proposals on the amendments to the tax legislation on the introduction of the system of income declaration of individuals, elaboration of the draft law envisaging relevant amendments and supplements to the RA Tax Code and submission to the RA Government for consideration.
4. Revenue Transparency and Compliance | 12. Tax potential and gap assessment | 12.1. Assessment of tax potential and gap for the three major types of taxes (VAT, profit tax, income tax) | MoF | - | 2019-2023 |  |  | Existence of tax potential and gap assessment methodology for three major types of taxes (VAT, profit tax, income tax); Tax potential and gap estimates for the three major types of taxes (VAT, profit tax, income tax) | In the framework of tax potential gap assessment, the RA Ministry of Finance, in cooperation with the RA State Revenue Committee and the RA Central Bank, assessed the tax potential of the Republic of Armenia, the results of which were discussed with the RA Deputy Prime Minister in December 2019. Based on this, agreements were reached and the RA State Revenue Committee was instructed to conduct a study and present its assessments on the tax potential. In this regard, the RA State Revenue Committee in 2020 carried out works on assessing the tax potential on VAT and tax gap, and submitted the results to the Office of the RA Deputy Prime Minister. In order to prove the implementation of the structural benchmark approved in the framework of the program with the IMF, a brief reference on the tax gap assessments and completed activities package of the RA Ministry of Finance and SRC was submitted to the IMF. which were the basis for considering the status of structural benchmarking to be "pending" in the IMF's third review report under the program signed with the IMF and published in December, 2020 . A more comprehensive reference is currently being drawn up on the activities done to assess the tax potential and gap which needs to be submitted to the IMF in order to consider the above structural benchmarl "completed" in future IMF reports. | During 2021 for the purpose of updating tax potential and gap assessment the RA SRC was requested information which was received. The received data have been elaborated and finalized, 2019 and 2020 tax potential and gap assessment has been implemented | 2019 and 2020 tax potential and gap assessment | Activities for 2020 and 2021 are carried out | It is a periodic process | Using the methodology developed by the RA Ministry of Finance, it is envisaged to regularly, every year, carry out tax potential and gap assessment work based on the information received from the RA State Revenue Committee |  |  | IMF
| 13․ Publication of information on tax refunds from the budget to ensure transparency of public finances | 13․1 Publication of data on tax refunds from the state budget on a quarterly basis | SRC | - | 2019-2023 |  |  | Relevant information published | In accordance with the RA SRC Chairman order N 267-A, dated 17.04.2019, the relevant information is published on a monthly basis in the RA SRC official website (http://www.petekamutner.am) in the section "Tax Information", sub-section "Tax Statistics" , part "Tax Statistics data" | Pursuant to the RA SRC Chairman Order №267-A, dated 17.04.2019, the relevant information is published monthly in the part “Tax Statistical Data”, sub-section “Tax Statistics”, section “Tax Information” of the RA SRC official website (http://www.petekamutner.am). | Publication of monthly information on tax refunds on the website of the RA State Revenue Committee | Activities for 2020 and 2021 are carried out | It is a periodic process | Publication of relevant information on a monthly basis.
| 14․ Continuous reduction of the shadow economy, exclusion of privileged taxpayers | 14․1 Expand opportunities for access to third party information and for effective use | SRC | - | 2019-2023 |  |  | Reducing the tax shadow Exclusion of taxpayers with privileged status and creating an equal tax environment for all taxpayers | 1. In order to ensure access to information to the tax authority from third parties on real estate, their owners, property rights, restrictions, limitations and their changes the RA Government draft decision "On making changes and additions to the RA Government decision N 388-N, dated April 6, 2017 " has been elaborated and sirculated since December, 2019. Taking into account the RA MoF standpoint on the draft that these changes should be initiated by drafting the decision of the RA Government Decision "On Making Amendments to the Decision No. 1337-N, dated October 5, 2017", the elaboration of which was initiated in January 2020, however, given that the RA Cadastre Committee developed the draft decision of the RA Government “On making changes in the RA Government Decision No. 388-N, dated April 6, 2017” and put into circulation in February 2020, thus 1337-N draft will be put into circulation once the draft 388-N regulations come into force 2 Within the framework of the draft joint decision of the RA Central Bank and the MoF On approving "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. 3. During the electronic opening of transit declarations for import transactions within the EEU, mistakes are made by the customs authorities of other EEU member states when filling in the transit declarations and in the future, during the closing of declarations in the Republic of Armenia, the information is entered into the "Taxpayer 3" electronic management system with corresponding shortcomings which creates significant inconveniences in the process of comparing and analyzing the information available in the e-management system Given the importance of the issues raised, it was proposed to enable the electronic tax authority to enter accurate data on the import of goods from the EEU countries, in particular, by manually verifying the data in the "Taxpayer 3" e-government system. | 1. The Ra Government draft Decision "On Making Amendments and Supplements to the RA Governmnet Decision N1337-N, dated October 5, 2017" was elaborated by the RA SRC and adopted by the RA Government Decision 159-N, dated 11.02.2021, as a result of which the tax authority will be provided with access to information on real estate owners, cadastral assessment. 2. In the framework of the draft joint decision of the RA Central Bank and the MoF "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. The order was established by the joint decision of the RA Minister of Finance No. 2-N, dated June 16, 2021 and No. 39-N, dated March 30, 2021 according to paragraph 58 of which, financial institutions shall submit information on assets transferred during the year of a legal entity or sole proprietor to the tax authority by February 20 of the following year. 3. In accordance with the Clause 122, Annex 1 of the RA Government Decision 596-Ն, dated 19.03.2015, copies of issued construction or demolition permits shall be submitted to the tax authority by the competent bodies issuing construction permits in the Republic of Armenia (including the Municipality of Yerevan). There are problems with the format and content of the information presented in this process. In order to regulate the receipt of information, the draft decision on making changes to RA Government Decision No. 596-N, dated 19.03.2015 was elaborated ent to the relevant interested bodies of the RA state administration for an opinion by the letter No. 01 / 3-4 / 80262-2021 dated 14.12.2021 . 4․A request was sent to 32 government agencies to assess the scope for expanding information received from third parties and to identify opportunities for further cooperation. Based on the responses received from the authorized bodies, the following directions were outlined for the expansion of the information received from third parties and relevant letters were sent to develop the legal basis for the exchange. a) Information on the owners of vehicles (including legal entities) reflected in the electronic information database of the "Traffic Police" service of the RA Police, as well as the persons operating them (including the addressees of the administrative act) b) Information available in the unified e-government system of civil acts registration in the RA Ministry of Justice c) Fees, dividends and other similar information of citizens submitting declarations in the register of the RA Commission for the Prevention of Corruption d) Information on final acts of public objects approved within the sphere of urban development existing in the RA Urban Development, Technical and Fire Safety Inspection Body, in the field of transport control for taxis of 5-7-seater vehicles, as well as the number of design documents of the objects submitted to the inspection body for the purpose of disclosure. e) RA State Cadastre Committee to get the complete history of real estate transactions: 5. By the letter N01//188-2021, dated 13.04.2021 the Commission for Prevention of Corruption informed on that they can not provide complete data yet, as the database does not provide such an opportunity yet. Work is underway to create a new system. 6․In June, 2021 the tax authority prepared an application for basic interconnection of data belonging to state or local self-government bodies and transfer of personal data for the purpose of using the web services of the Civil Status Acts Registration Agency of the RA Ministry of Justice, the RA Cadastre Committee, and the RA Police. On 25.06.2021, the application was sent to "EKENG" CJSC to ensure the further process. Database interconnection and personal data transfer integration technical manuals of Police, Civil Status Acts Registration Agency and Cadastre were sent to RA SRC by "EKENG" CJSC by email on July 2, 2021. After receiving the answers to the inquiry mentioned in the 5th column of this appendix, measures will be taken to obtain the existing information useful for the tax control process in the databases of the mentioned bodies. 2024 | • Elaboration of a draft decision of the RA Government on ensuring access to information on real estate, its owners, property rights, restrictions and their changes to the tax authority for receiving information from third parties: • Ensuring access to information on cadastral appraisal of property owners (RA Government Decision 159-N, dated 11.02.2021): • Joint decision of the RA Minister of Finance No. 2-N, dated June 16, 2021 and the RA Central Bank Council No. 39-N 30.03.2021 "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" |  | In progress | After receiving the answers to the inquiry in order to assess the scope of the information received from third parties and to identify opportunities for further cooperation, appropriate measures will be taken to obtain information relevant to the tax control process available in the databases of the mentioned bodies.
| 15․ Ensuring timely declaration and fulfillment of tax liabilities by taxpayers in full | 15․1 Modernization and capacity building of tax authority analytical and control tools | SRC | - | 2019-2023 |  |  | The staff of the tax authority has the necessary capacity to enforce tax legislation There is a revised and constantly improving tax control toolkit | 1.The Order 260-A was approved by the RA SRC Chairman on 23.03.2020 , which provides for the development and automation of risk-taking analytical tools. Built-in "Big Data" analytical processing system (Big Data Analytics - Power BI)is installed, which allows analytical work, creating reports with different criteria. At present, a total of 24 reporting items are included in the analytical system of large databases, including 4 on foreign economic activity. New approaches have been used in the risk management system based on large-scale data analysis to more effectively target risks. 2. The automated system for conducting cameralistic studies has been introduced and tested in the e-government system of the tax authority. During the testing, the problems that hindered the operation of the system were identified, and work is underway to solve them. 3. The current procedure of tax risk assessment carried out during tax administration has been studied in detail and the risk assessment and realization procedure, including the toolkit has been completely revised by the Order No. 195-A, dated February 28, 2020. 4. The current procedure of the automatic monitoring system used during the tax administration has been studied in detail in 2020. The procedure for implementing and monitoring risk assessment was completely revised by the Order No. 300-A, dated April 6, 2020, while partially changing the risk assessment toolkit. At the same time, the criteria for assessing risk based on monitoring results, supplementing the system with new criteria characterizing the real risk of taxpayers was revised by the decision No. 1151-A of the RA SRC Chairman dated 08.12.2020 5.The description of the planning process of complex tax inspections based on risk criteria was studied in 2020 and the new procedure was approved by the order No. 460-A of the head of tax authority, dated May 25, 2020, according to which the priority of inclusion in the annual program of inspections was given to the taxpayers who declared the highest sales turnover, as well as to the taxpayers in the high risk zone. 6. A new automated system of inspections has been launched in the information system of the tax authority since March, 2020 as a result of which it has been possible to selectively include inspectors in complex tax inspections automatically. 7. Regulation on the organization, conduct and realization of tax audits and studies,which, in addition to a number of procedural regulations was reaffirmed by the Order 80-A of the head of tax authority, dated January 30, 2020 which has been adapted to the new structure of the tax authority. 8. The cooperation of the units carrying out tax administration and units carrying out legal, investigative proceedings of the tax body has been regulated by the SRC Chairman Order 419-A, dated May 20, 2020. | 1. By the Order №1151-Ա of the RA SRC Chairman dated 08.12.2020 on making changes to Order №300-Ա, dated 06.04.2020 the risk criteria existing in the monitoring center, were supplemented and brought to 66. In May-June, 2021, a tender was announced for the acquisition of consulting services for the development and introduction of new risk assessment criteria in the above-mentioned automatic notification system. The procurement procedure is at the stage of signing the contract. 2 . By the RA SRC Chairman Order №260-A approved on 23.03.2020, Power BI reporting-analytical system has been launched under the SRC e-government system within which 9 analytical tools were elaborated in 2020, of which 5 have already been launched during 2021. Two new reporting forms have been programmed into the Big Data system. At present, a total of 42 reporting items are included in the analytical system of Big Data, including 6 on foreign economic activity. 3. Based on court practice, the approach to detecting the rules of operation of cash registers has been changed in the tax body since December, 2021, in particular, control purchase studies are already being carried out instead of cash register inspections. At the same time, due to the above, changes were made in the electronic system of organizing inspections of the tax body, as a result of which it is possible to publish instructions for control purchase studies based on a specific purpose. Corresponding changes were also made in the internal procedures defined by the RA SRC orders (80-A and 195-A). | • Introduction andoperation of Big Data Analytics (Power BI) Analytical System (Power BI) • Introduction and testing of an automated cameral studies system • Review of tax risk assessment and implementation procedures • Acquisition of consulting services for the Introduction and implementation of new risk assessment criteria in the automatic notification system • Based on the court practice, change of the rules of operation of cash registers in the tax body, introduction of the practice of control purchase studies instead of cash register inspections (orders of the RA Chairman of the State Revenue Committee (8-0A and 195-A)): |  | In progress | The analytical tools will be constantly adapted to the current legal regulations |  |  | IMF
3․ STRATEGIC PLANNING, DRAWING UP MEDIUM-TERM EXPENDITURE FRAMEWORK AND STATE BUDGET
| 16․ Objectives and results of all budget programs included in the 2023 state budget are in line with existing sectoral strategies and cover all existing strategies that have an impact on budget revenues and expenditures | 16․1․ Review / develop budget programs in line with existing strategic policy | MoF | SBs | 2020-2022 |  |  | Availability of conformity assessment | By RA Prime Minister By Recommendation No. 02 / 08.5 / 35060-2020, dated 21.07.2020, all SBs were asked to harmonize the financial assessments of the sector strategies with the MTEF. As of 13.08.2020, the measure is implemented in 18 out of 46 SB having submitted the report on PFMSR progress report and the presented budget programs correspond to the policy directions defined by the main strategies of the PA. Work is underway in 28 bodies to implement the measure: analysis of budget programs from the point of view of compliance with existing strategic documents is carried out. 2 There is a process of reviewing strategies / policy directions in connection with the reorganization and legislative changes in the SB. The responsible unit of the RA Ministry of Finance has developed a measure of self-assessments of the conformity of the sectoral policy of the public authority and the compliance of the budget programs, which has been filled in by the public authorities and submitted to the MoF. | Within the support of the UNDP, an inventory of the RA strategic documents is carried out, the policy frameworks defined by them (goals, results, targets, etc.) are mapped, and the compliance of the budget programs related to them is assessed. The work also includes assessments of compliance with strategic planning frameworks and related budget programs. |  |  | In Progress | Following the completion of the inventory of strategic documents in the relevant areas and the mapping of the policy frameworks defined by them (goals, results, targets, etc.), public authorities will be required to review the content and structure of budget programs depending on the existing strategic documents in the field. |  |  | IMF(UNDP/RF MOF)
All the programs included in the 2023 state budget are in line with the existing strategies
The 2023 budget programs fully cover all existing strategies that have an impact on budget revenues and expenditures.
All programs included in the 2023 state budget (except for administrative programs) have program passports, which are submitted to the RA NA together with the 2023 ․ draft state budget
|  | 16․2 Identification and regulation of practical problems related to the current PB methodology and its application | MoF | - | 2020-2022 |  |  | Existence of a report on the study of the PB methodology, the existing gaps related to its application | The measure is implemented with the technical support of the IMF, within the framework of which IMF experts conducted a study of the gaps and problems of the PB methodology and its application. The preliminary results of the study, including the recommendations on measures to improve the application of the "B methodology" were submitted to the MoF: The MoF is currently studying the assessments presented by the experts, the approaches and the issues of their practical application. At the same time, it is envisaged that in parallel with this work, self-assessments will be carried out on the gaps and problems of the introduction of the PB methodology in the state bodies, and its application. Based on the results of the above-mentioned external assessments and self-assessments, a schedule of measures to improve the application of the PB methodology will be developed as necessary. | With the technical support of the IMF, a study of the gaps and problems of the PB methodology and its application were conducted and suggestions were made to improve the PB methodology . At the same time, self-assessments were carried out in state bodies , which are now being discussed. |  |  | In Progress | Based on the results of self-assessments, as well as after the discussions on the proposals provided by the IMF, a list of measures to improve the application of the PB methodology will be developed, as neccessary with an appropriate schedule. |  |  | GIZ(IMF/RF MOF)
Existence of list of measure and schedule of PB methodology and its application improvement
The measures to improve the PB methodology are implemented in accordance with the schedule of measures
|  | 16․3․ Measures aimed at developing human resources | MoF | - | 2020-2023 |  |  | Institutional Capacity Assessment Report on Existing Human Resources (s) in line with the PB embedded system requirements | The possibility of being provided with external technical assistance for the implementation of the institutional capacity assessment of the existing human resources and for the implementation of the elaboration of capacity building program in accordance with the requirements of the embedded PB, is currently being discussed with partner international organizations. It is envisaged that in parallel, internal assessments of the relevant capacities in the state bodies will be carried out. Based on the results of the above-mentioned external-internal evaluations, an appropriate capacity building program will be developed. | In the framework of the measure, self-assessments were carried out in the state bodies on the basis of the self-assessment format of deficiencies and gaps provided to the state bodies, including in terms of human resource capacity, which are being discussed. In the scope of the IMF technical assistance recommendations on specific capacity development issues were also made. At the same time, within the framework of the "Program of measures aimed at capacity building of human resources in the RA state bodies from the point of view of full implementation of program budgeting" defined by the RA Government Decision No. 1223-L dated 12.09.2019, continuous professional trainings in the field of CB are regularly carried out. |  |  | In Progress | Based on the results of the self-assessments carried out in the state bodies, as well as the results of the discussions of the submitted proposals, taking into account the list of measures to improve its application of the PB methodology, the Elaboration activities of a modern capacity development program will launch | The current capacity assessments do not provide a complete picture, so there is a need for technical assistance in implemeting a full / comprehensive capacity building assessment and elaboprating capacity building action plan in state bodies. | negotiate with donor internation organizations experenced in the field to get appropriate technical assistance | GIZ(IMF/RF MOF)
Availability of an up-to-date capacity building program
Capacity building activities are implemented in accordance with the approved program
| 17․ As of the end of the 2023 budget year, there is a regular budget program evaluation process in all state bodies responsible for budget programs. | 17․1․ Development of budget program evaluation guidelines | MoF | - | December, 2022 |  |  | The concept of evaluating budget programs is available | Within the measure the activities for elaboration of the budget program monitoring and evaluation concept, methodology, as well as the system introduction measure schedule are being implemented with the technical assistance of GIZ. In the scope of the technical assistance, the draft budget program monitoring, evaluation concept has been elaborated and submitted to MoF which is currently being studied and discussed by the MoF. After clarifying the approaches to the concept, the relevant methodology and action plan will be developed by the experts. | In the scope of the technical assistance of GIZ, the draft budget program evaluation concept has been elaborated and submitted to the RA Prime Minister office for approval on December 27, 2021 by the letter 01/8-5/21538-2021 in th form of the RA Prime Minister draft Decree. With the support of the GIZ, a draft budget program evaluation guide has been elaborated and is under discussion. | Draft budget program evaluation concept. Draft Budget Program Evaluation Guide. |  | In Progress | Using the developed concept of program evaluation, it is planned to carry out pilot evaluations of 3 budget programs. |  |  | GIZ
Budget program evaluation guidelines have been developed
|  | 17․2․ Introduce a process of regular evaluation of budget programs | MoF | SB | December, 2023 |  |  | Existence of a schedule and measures for the implementation of budget program evaluation functions | The activities to be carried out within the framework of the event are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. | The activities to be carried out within the framework of the measure are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure |  |  | Not started | After the approval of the budget program evaluation concept, the schedule for the implementation of budget program evaluation functions and the list of measures will be clarified. | The developed program evaluation concept envisages the adoption of a centralized program evaluation model, in case of which it will be necessary to edit the evaluation criteria of the results of this measure | After the approval of the Concept with the submitted format review the criteria for evaluating the results of the measure | GIZ
As of the end of the 2023 budget year, each state body responsible for budget programs has a regular program evaluation process.
As of the end of the 2023 budget year, at least 1 budget program implemented by each state body responsible for budget programs has been assessed experimentally in accordance with the approved guidelines.
6. MTEF process, budget disciplinary and transparency | 18․ Programs / measures arising from the manadatoy obligations of the state are identified and registered | 18․1 Identification and registration of programs / measures arising from the mandatory obligations of the state | MoF | SBs | December, 2021 |  |  | Appropriate methodology is available and procedures are elaborated | The methodological instructions for preparing and submitting budget applications in the framework of the 2021 and 2022 budget processes already contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. The programs / measures arising from the mandatory obligations of the state within the 2021 budget process have already been identified in accordance with the current methodology. At present, work is being carried out with the technical assistance of the IMF to improve the above-mentioned methodology and its application, within which a document of studies and recommendations has been submitted to the RA MoF. The document is currently being studied and discussed by the MoF. After clarifying the approaches to the methodological issues presented in the document, if necessary, necessary work will be undertaken to review the methodology for identifying and registering the programs / measures arising from the mandatory obligations of the state, and to localize the new methodology. | The methodological instructions for preparing and submitting budget applications in the framework of the 2022 budget processes contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. The programs / measures arising from the mandatory obligations of the state within the 2022 budget process have already been identified in accordance with the current methodology. To improve the above-mentioned methodology recommendations have been elaborated with the technical assistance of the IMF which were later piloted with the example of the RA MoF. After summarizing the results of the piloting necessary work will be undertaken to review the methodology. | • methodology and procedures for identifying and accounting programs / measures arising from mandatory state obligations have been elaborated (MTEF and state budget formation methodical instructions) • Within the framework of the budget process for 2021 and 2022, the programs / measures arising from the mandatory state obligations were identified in accordance with the current methodology. | December 2021 | Completed | Summary of test results of methodology review proposals and review of existing methodology as needed. |  |  | IMF
In the framework of the 2022 budget process, the mandatory obligations of the state are identified and registered
| 19. Introduction of a single process of drafting the MTEF and annual budget | 19.1․ Creating a legal basis and elaborating methodology for ensuring a single process of drafting the MTEF and annual budget | MoF | - | 2021 |  |  | The single process of drafting the MTEF and annual budget is carried out | Since 2020 the MTEF and annual budget drafting is being carried out in a single process for which the schedules established by the RA Prime Minister's decisions on starting the budget processes of 2021 and 2022 serve as a legal basis. After summarizing the results of the 2021 budget process, the expediency of making relevant amendments to the Law "on the Budgetary System of the Republic of Armenia" will be considered. Accordingly, if necessary, a package of relevant changes will be developed and submitted for approval. |  | • Since 2020 the MTEF and state budget formation activites are being carried out in single procedure | August 2020 | Completed |  |  |  | IMF
| 20․ Simplified budget and simplified budget execution reports are available to public | 20․1 Elaborating and publicizing the simplified version of the state budget and the budget execution report | MoF | - | Within one month after the adoption of the 2021 RA state budget (Publication of the Simplified Budget) 2021 (Publication of simplified budget report ) |  |  | Simplified Budget for 2021 and Budget Execution Reports are published on the official website of the MoF Discussions have been held with CSOs on simplified budget and budget execution reports (at least twice a year) | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021: For this purpose, with the support of the GIZ the methodological instructions for the preparation of sectoral budget projects by the state bodies within the framework of the drafting of the RA 2021 draft state budget and MTEF 2021-2023 were elaborated posted on the official website of the MoF link: http://www.minfin.am/website/images/website/documents/Metodakan2021%20(2).docx), as well as it was officially provided to the public authorities. Based on the information provided to the Ministry of Finance by state bodies in accordance with the methodological guidelines for the preparation of sectoral draft budgets "Citizen Budget 2021" was elaborated and published on the official website of the Ministry of Finance. (available at the following link: https://minfin.am/website/images/website/byuje%20ev%20krknaki%20harkum/Citizen_budget_Final_V%20_01.02.2021_compressed.pdf ): | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021. Based on the information provided to the Ministry of Finance by state bodies in accordance with the methodological guidelines for the preparation of sectoral draft budgets "Citizen Budget 2021" was elaborated and published on the official website of the Ministry of Finance (available at the following link: https://minfin.am/website/images/website/Citizen%20Budget%202022_V1.pdf ) At the same time, after the approval of the report on the exection of the state budget for 2020, a simplified version of that report was developed and posted on the official website of the Ministry of Finance (available at the following link: https://minfin.am/hy/page/2020_tvakani_petakan_byujei_parzecvats_hashvetvutyun )։ | • Elaboration of methodological instructions for the preparation of sectoral drafts of the citizen's budget •Elaboration and publication of citizen's budget 2021 and 2022 at the RA MoF official website. • The simplified version of the report on the execution of the state budget for 2020 has been developed and published on the website of the Ministry of Finance | Activities for 2020 and 2021 are carried out. | It is a periodic process | The development of the simplified version of the state budget execution report is planned to start in 2021 after the adoption of the report on the execution of the RA state budget. Development and publication of the Citizen's budget for 2023 within one month after the adoption of the law on the state budget of the Republic of Armenia for 2023.
| 21. Civil society organizations are more actively involved in the budget process | 21.1.Disclosure of information on budget proposals | SBs | - | 2020-2023 |  |  | RA state bodies have platforms to discuss budget proposals with CSOs. | The measure on the 2021 budget process has been implemented. According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2021 and 2022 budget process, clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. In order to ensure the public discussions on budget applications of state bodies, with the support of the GIZ, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting state budgets (link: http://www.minfin.am/ website / images / website / byuje_amsakan / PB% 20instructions% 20for% 202021% 20budget% 20process-1% 20 (1) .docx): The latter were posted on the MoF official website and provided to all state bodies. At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. | The measure on the 2021 budget process has been implemented. According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2021 and 2022 budget process, clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. In order to ensure the public discussions on budget applications of state bodies, with the support of the GIZ, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting state budgets (link: http://www.minfin.am/ website / images / website / byuje_amsakan / PB% 20instructions% 20for% 202021% 20budget% 20process-1% 20 (1) .docx): The latter were posted on the MoF official website and provided to all state bodies. At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. | • Development of methodological guidelines for ensuring public participation in the development of budget programs of state agencies | Activities for 2020 and 2021 are carried out. | It is a periodic process |  |  |  | (RF MOF)
|  | 21.2. Establishment of a platform (s) for discussing budget proposals with CSOs | SBs | - | 2020-2023 |  |  | The budget proposals of the RA state bodies include the results of the discussions on the applications with the CSOs. | According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9 "On starting the budget process of the Republic of Armenia for 2021", a requirement was set by state bodies to place their budget applications on their official websites. In order to ensure the process of public discussions on budget proposals of state bodies, with the support of GIZ the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF 2021-2023 and 2021 state budgets (link http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA MoF and provided to all state bodies. At the same time, according to the preliminary agreement, within the framework of the GIZ support, it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the state budgeting process. According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. Nevertheless, conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process. Conditioned by that, according to the methodological instructions of MTEF 2022-2024 (including the state budget of the Republic of Armenia for 2022), it is envisaged that state bodies will organize discussions with CSOs. | According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2022 and 2023 budget process, requirements are set for posting the budget proposals of the RA state bodies on their websites. By the same schedule it has been defined that within the elaboration of draft MTEF (including the state budget) the state bodies should hold discussions with the stakeholder CSO under their competences on budget proposals and submit to the RA MoF Information on the results of those discussions. In order to ensure the public discussions on budget applications of state bodies, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF and state budgets (link: http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx ): At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. However, in Within the framework of the 2022 budget process, discussions on their budget applications haven’t been held with CSOs, mainly due to the lack of proposals on CSO participation in the applications. | • Establishing requirements for the publication of budget applications of state bodies, discussions on applications with CSOs, presentation of their results for the budget processes of 2021 and 2022. |  | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | Ensuring the continuity of publicity of budget applications of state bodies. In particular, ensuring the publicity of budget applications of state bodies within the timeframe set by the RA Prime Minister's decision on starting the 2023 budget process. | Since In the framework of the 2022 budget process, they did not mainly discuss their budget applications with CSOs, so there is a risk in terms of conducting application discussions with CSOs in 2023 .Ք | In order to avoid risks, the RA state bodies were instructed to ensure the organization of discussions with CSOs on their budget applications and the submission of information on it to the RA Ministry of Finance | GIZ (RF MOF)
7․ Automate the process of calculating the cost of budget programs | 22. Within the framework of the 2023 budget process, the processes of calculation (expenditure) of budget programs / measures are carried out through a unified automated system. | 22.1 Step by stem introduction of Automated system of calculating the cost of budget programs | MoF | - | Within one month after the adoption of the 2021 report on the execution of the RA state budget July |  |  | The automated budgeting system has been tested and is ready for implementation. Within the framework of the 2023 budget process, expenditure budgeting were implemented through an automated expnditure budgeting system. | The elaboration and testing of the automated budget expenditure planning system by the RA Ministry of Finance (Authorized Body) has already been completed in December 2019. The system allows applicant bodies to submit online cost-benefit calculations online as part of budget funding applications using pre-designed batch and quota agreed with the Authorized Body in formats preliminary elaborated by applicant bodies and agreed with authorized body , as well as enables the respective competent users of the applicant body and the authorized body approve / reject, as well as summarize the data of the received proposals according to the program, operational-economic classifiers, allowing to receive the necessary details of the openings of the numbers of programs / measures. In 2020 professional meetings were held with the representatives of the applicant bodies on the elaboration of templates for the calculation and substantiation of expenditures on the programs and measures included in the budget proposals. During the training after it, the RA MoF together with the applicant bodies, started the work of elaborating and submitting the templates to the RA Ministry of Finance. All samples agreed and approved by the RA MoF have already been imported into the System. At the same time, based on the data provided by theapplicant bodies, users were created in the system, defining the relevant authorities. | In 2021, the training courses on the development of cost calculation-justification samples for the programs and measures included in the budget applications continued with the representatives of the applicant bodies. The Samples provided by the applicant bodies were agreed upon and approved by the RA Ministry of Finance and entered into the System. | • Elaboration and testing of automated budget planning system |  | In Progress | According to the methodological instructions for the preparation of the 2022-2024 MTEF and state budget for 2022, In order to implement budget program expenditures for 2022, all state bodies should pilot the new software developed for budget program expenditures. | Given that by the end of 2021 not all state bodies have been included in the system and the system has not been fully tested in terms of application in the budget process, there is a risk that budget expenditures under the 2023 budget process will not be fully implemented through automated spending systems. | To give additional instructions to the state bodies to ensure the above-mentioned point as a reminder or to take measures to the structures and responsible persons for the given works shortcomings to hold them accountable for it
4․ BUDGET EXECUTION PROCESS CONTROL, TREASURY SYSTEM
8. Budget Execution Reports | 23. Preparation of reports on the execution of the RA state budget by program classification | 23․1 Adaptation of the electronic budget reporting system to the requirements of program budgeting | MoF | - | December, 2019 |  |  | Existence of reports on the RA state budget execution by program classification | The measure is completed, and the reports on the execution of the first quarter of the RA 2019 state budget in program format on the execution of both financial and performance indicators have been submitted by the bodies responsible for the execution of the programs through the electronic budget reporting system. Before that, the system was tested, on April 1-3, 2019 trainings were organized for 64 specialists responsible for preparing report, the system was introduced in all state bodies, and the latter were assisted in the introduction and operation of the system. As a result, the quarterly (incremental) reports on the execution of the RA 2019 state budget were submitted to the RA Prime Minister's Office in program format. During the year, activities have been carried out to solve the problems identified during the operation of the system. |  | • The electronic system of budget reports has been updated and can ensure the submission of state budget execution reports in software format. | 2019 | Completed
9. Arrears monitoring and management | 24. Arrears monitoring and management | 24.1 Registration of expenditure arrears | MoF | SB | 2020-2023 |  |  | The RA public authorities and territorial administration bodies carry out the registration of arrears on expenses | The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses. Each year the chief budget executive body submits to the Budget Execution Department information on the absence of arrears on state budget expenditures | The measure is regular. Within the framework of the latter, the RA public authorities and territorial administration bodies carry out arrears of expenses. Information on arrears on state budget expenditures is submitted to the RA Ministry of Finance every month. Information on arrears is included in the relevant reports on the execution of the RA state budget. | • State bodies carry out the accounting of arrears on expenses and submit reports on arrears the RA Ministry of Finance every month. | Activities for 2020 and 2021 are carried out | It is a periodic process | Identifying and neutralizing the risks of incurring arrears
Information on arrears is included in the reports on RA State Budget execution
10. Payroll controls | 25. Personnel records and payroll data coordination and implementation of changes in the accounting information system | 25․1 Elaboration of a system for integration of the human resources database into accounting software / AS modules | SB | CSO | 2020-2023 |  |  | Terms of reference for human resource database / accounting information program module integration system is elaborated and approved | As of 2020 In 5 SBs the system is embedded, all the processes related to the personnel registration and salary fund data are carried out through the system, activities are being carried out for system introduction in 5 SBS, in 2 SBs there is an issue of software, terms of reference is being elaborated. The other SBs did not provide information on the measure implementation. According to the information provided by the CSOs, terms of reference of integration system of human resources database with accounting Information System Module was developed for the implementation of the event. The latter stipulates that the relevant employee of the accounting unit will receive an automatic notification about the necessary function performed by the personnel management units in order to make the required changes in the electronic accounting program. | In order to develop the best mechanism for data transfer between the Civil Service Information Platform (hereinafter the Platform) and the accounting information systems used in state bodies, and to ensure its further implementation, discussions were held during 2021. Taking into account that Armenian programs are mainly used for the implementation of accounting functions in state bodies discussion was initiated and organized with the participation of companies engaged in the development of software securities used for accounting purposes in state bodies who expressed their willingness to assist in the implementation of the software solutions described above within the framework of the system functionality. The works are being discussed. |  |  | In Progress | 1. Presentation of the work already done by the platform maintenance technician to solve the problems, organization of discussions. 2. Meetings aimed at the willingness and opportunities to make changes in the 1C programs used in state bodies, 3. Meetings with AS representatives to discuss data, their characteristics, as well as the agreement needed to start specific work:
|  | 25․2 Introduction and maintenance of the system | [5 empty] | The system is embedded and all processes related to personnel records and payroll data are carried out through the system | The system was launched in the fourth quarter of 2020, and data entry by government agencies on the information platform is currently underway. At the same time, the system is in re-testing process in order to identify problemns and give them relevant solutions.
| 26. Payroll audit | 26․1 implementation of payroll audit by the Internal Audit | MoF | SB, CSO | 2021-2023 |  |  | Data transfer and comparison deficiencies are identified | Payroll audit was not carried out in most of SBs having provided information, due to liquidation of the internal audit unit and following the long-term process of organizing procurement procedures and concluding contracts as a result of oursourcing the function. At the same time, payroll audit is envisaged in the annual Internal Audit Plan for 2021 in 11 PMs that provided information. | A corresponding working group has been set up jointly with the Civil Service Office of the Office of the RA Prime Minister to identify shortcomings in the transfer and comparison of salary data. Based on the results of the working discussions, the following vision was adopted that before the full implementation of the measures provided for in Clause 25, the Ministry of Finance will collect the the results of the salary audit carried out within the framework of internal audit in the manner prescribed by law in accordance with the legislation to identify shortcomings in the transfer of data and comparison between staff management and accounting units. In the framework of the measure, the RA state bodies were offered to envisage the implementation of salary audits in the annual internal audit work programs. In 36 of 48 state bodies it is already planned to perform salary audit by the 2021-2022 annual program. |  |  | In Progress | Carrying out salary audit by state bodies and submission of results to the RA Ministry of Finance
The reports provide recommendations on payroll control
| 27. Ensuring the accountability of the calculation of salaries and equivalent payments | 27.1 Notification of data on calculation of salaries equivalent payments and received income received to employees, | MoF | SB | 2021-2023 |  |  | Employees receive monthly information on the calculation and payment of income received during the previous month | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries during 2020. | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries . |  |  | In Progress | Introduction of mechanisms for providing information on the income received by employees in state bodies and provision of information.
5. PUBLIC DEBT
11. Public debt management | 28. Improving the RA Law "on Public Debt" | 28․1 Conformity of the RA Law "on Public Debt" to the standards applied by international financial institutions | MoF | - | December, 2022 |  | Decembet 2023 | Improving debt statistics by clarifying the definitions used in the RA Law on Public Debt ("Public Debt" and "Government Debt") | The preliminary version of the RA draft Law "On Public Debt" has been elaborated. Discussions are underway with international financial institutions to obtain technical assistance for the implementation of the measure | The preliminary version of the RA draft law "On Public Debt" has been elaborated | Elaboration of the RA draft law "On Public Debt" |  | In progress | During the first half of the year, as a result of discussions, the RA draft law "On Public Debt" will be submitted for approval |  |  | (ADB/WB/EU)
| 29. RA Government debt portfolio exchange rate risk mitigation | 29․1 Increasing the share of deficit financing in the state budget each year at the expense of net domestic borrowing | MoF | - | December, 2023 |  |  | The share of deficit financing in the state budget at the expense of net domestic borrowed funds is at least 50.0% | The share of deficit financing in the state budget at the expense of net domestic borrowing was 84.7% in 2020 | The share of deficit financing in the state budget for 2021 at the expense of net domestic borrowed funds is 40.6% | • The share of deficit financing in the state budget at the expense of net domestic borrowed funds is 84.7% in 2020 and 40.6% in 2021 | The Minimum targets are ensured for 2020 The minimum targets for 2021 are not ensured | It is a periodic process | The share of deficit financing program in the state budget for 2022 at the expense of net domestic borrowed funds is 70.2% | The work envisaged for the year 2021 is underperformed as the share of deficit financing in the state budget at the expense of net domestic borrowed funds for 2021 has significantly decreased from 84.7% to 40.6% compared to the previous year. | Take measures to ensure the target indicators for 2022.
6. PUBLIC SECTOR ACCOUNTING
12. Public Sector Accounting | 30. Monitoring the annual financial statements of public sector organizations | 30․1 Monitoring the financial statements of public sector organizations by the MoF | MoF | - | 2019-2023 |  |  | · Financial statements in accordance with the RA Public Sector Accounting Standard (IAS) | In April 2020, a letter was sent to public sector organizations to submit their 2019 transaction log and financial statements for monitoring purposes. The already submitted financial statements are monitored, and after summarizing the results, they are submitted in writing to the relevant public sector organizations. At the same time, based on the monitoring results the 9th և 10th issues of the Professional Directory were prepared in 2020 and sent to the public sector organizations. |  | • Starting from 2020 The financial statements of public sector organizations are being monitored. | Activities for 2020 and 2022 are carried out. | It is a periodic process | At the end of each year, public sector organizations submit the package of their operations log and financial statements which are monitored by the staff of the department. Errors and inaccuracies in the above information are identified and reported to the appropriate organizations to avoid similar errors in the future. "Professional Directory" periodicals are prepared on the basis of common errors.
|  | 30․2 Methodology review (as needed) | MoF | - |  |  |  | Improved regulatory framework | The draft law "On Making Amendments to the Law on Accounting of Public Sector Organizations" has been developed by the Ministry of Finance which has been approved by the RA NA bu first reading on September 18, 2020. | The RA law ՀՕ-84-N "On Making Amendments to the Law on Accounting of Public Sector Organizations" elaborated by the RA MoF was adopted by the RA National Assembly on March 4, as well as a number of by-laws have been elaborated and approved on the basis of these changes. | • The draft law "On Making Amendments and supplements to the Law on Accounting of Public Sector Organizations" adopted by the RA NA by first reading on September 18, 2020. |  | In progress | The measure is regular. The review of the public sector accounting methodology will be carried out if necessary.
|  | 30.3 Implementation of the qualification process for chief accountants of public sector organizations | MoF | - | 2020-2023 |  |  | Qualified Chief Accountants of Public Sector Organizations | During 2020, 10 qualification exams for public sector accountants were held, as a result of which 54 people were qualified. | During 2021, 34 qualification exams for public sector accountants were held, as a result of which 143 people were qualified. As of December, 2021, 197 people are qualified as public sector accountants in Armenia. | Qualifications of Chief Accountants of Public Sector Organizations՝ • 10 exams in , 54 qualified persons, • 34 exams in 2021, 143 qualified persons. | Activities for 2020 and 2022 are carried out. | It is a periodic process
| 31. Preparation of interim consolidated financial statementss at the ministries level | 31․1 Development of a methodology for consolidating financial statements | MoF | - | 2022-2023 |  |  | Consolidation methodology is available | The draft consolidation methodology has been developed and will be reviewed by international experts within the activity for the introduction of the GFMIS. | The draft consolidation methodology has been developed and will be reviewed by international experts within the activity for the introduction of the GFMIS. | • Elaboration of a draft methodology for consolidating financial statements. |  | In progress | Revision of the draft consolidation methodology within the framework of the GFMIS |  |  | (GIZ/WB)
|  | 31․2 Development or acquisition of a joint computer program for the purpose of consolidation | MoF | - |  |  |  | Computer program necessary for consolidation | this measure is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. | This measure is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. |  |  | In progress | The elaboration of the technical requirements of the financial statements consolidation module will be carried out within the framework of the GFMIS
|  | 31․3 Preparation of interim consolidated financial statements at the ministries level | MoF | - | December, 2023 |  |  | Interim consolidated financial statements at the ministries level are submitted | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. |  |  | Not started
7. CORPORATE ACCOUNTING AND AUDIT
13. Regulation of corporate accounting and audit activity | 32. Introduction of public control system over accounting and auditing activities | 32․1 Completion of the necessary sub-legislative framework | MoF | - | 2020-2021 |  |  | New specialized structures for sector regulation and control - Public oversight board model | The RA Government decision 1336-N, dated August 13, 2020 "On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Computer Software Enabling Accounting" was elaborated and approved. 4 sessions of public oversight board were held as a result of which Decision 1-Լ "On defining the Procedure for Maintaining the Register of Auditors, Expert Accountants, Audit Organizations, and Minimum List of Data Included in It" was adopted on August 31, 2020 and Decision 2-Լ "On approving the decision N 6-L of October 26, 2020 of the Board of the Chamber of Auditors and Expert Accountants of Armenia" was adopted on November 11. Legal acts related to the extension of qualification certificates of accountants and auditors have been developed and approved. The draft decision of the AOB "On approval of the procedure for conducting mandatory inventory of assets and liabilities" has been developed, which is currently under discussion. | In order to regulate the areas, the RA Audit Chamber, expert accountants, have developed a number of legal acts, which have been submitted to the Public Oversight Board of Accounting and Auditing activity for approval. During 2021, 7 sessions of the Oversight Board took place, as a result of which 15 decisions of the Oversight Board were adopted. At the same time, the legal acts related to the extension of the qualification certificates of accountants and auditors were elaborated and approved. During 2021, seminars-discussions were organized for the employees of the Ministry of Finance of the Republic of Armenia on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing.: | • The RA Government decision 1336-N, dated August 13, 2020 "On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Computer Software Enabling Accounting" • Public Oversight Board Decision 1-Լ, dated August 31, 2020"On defining the Procedure for Maintaining the Register of Auditors, Expert Accountants, Audit Organizations, and Minimum List of Data Included in It" • Legal acts related to the extension of qualification certificates of accountants and auditors have been developed and approved • The draft decision of the POB "On approval of the procedure for conducting mandatory inventory of assets and liabilities" has been developed | 2021 | Completed |  |  |  | (WB/RD MOF)
Effective audit quality control system
adjusted scope of organizations subject to mandatory audit
|  | 32․2 Staff training | [5 empty] | Appropriate level of capacity | During 2020, remote seminars were organized for the employees of the RA Ministry of Finance on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing. | During 2021, seminars-discussions were organized for the employees of the RA Ministry of Finance on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing. | Capacity building of the RA MoF staff during 2020 and 2021 | 2021 | Completed
8. FINANCIAL MANAGEMENT AND CONTROL OF STATE ORGANIZATIONS: STATE NON-Commercial ORGANIZATIONS (SNCO)
14. Financial Management and Control of state organizations accountability of state non-commercial organizations | 33. Improving the system of accountability and monitoring of the financial and economic activities of SNCOs | 33․1 Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | MoF | - | 2020-2023 |  |  | Availability of an up-to-date system for monitoring the financial and economic activities of SNCOs | In order to implement reforms in the system of public financial management, a system of fiduciary control of state non-commercial organizations has been developed since 2010 in the field of financial management and control of state organizations. In view of testing the elaborated system in practice and elaborating fiduciary control effective system, In 2010, the RA Government, with the support of the World Bank, initiated the "Piloting of Fiduciary Control Systems of SNCOs" project. At this stage, the elaborated system is being studied, work is being done to modernize it and bring it in line with the current system of SNCO activities. Studies have been conducted in the field of activity of state non-commercial organizations in order to elaborate a system of non-financial (productive) indicators. | Studies have been conducted in the field of activity of state non-commercial organizations in order to elaborate a system of non-financial (outcome) indicators. |  |  | In progress | It is planned to hold discussions with a number of authorised bodies. |  |  | ADB
9. PUBLIC PROCCUREMENT
15. Upgrading the e-procurement system | 34. New e-procurement system software | 34․1 Development and introduction of new e-procurement system software | MoF | - | December, 2020 | December, 2021 | 3rd decade of December 2023 | New existing e-procurement software | Activities have been carried out with donor organizations to develop a business model and terms of reference for the introduction of a new e-procurement system. In particular, an agreement was reached with the European Bank for Reconstruction and Development to elaborate a new e-procurement software system with the latter's technical and financial assistance, according to which it is expected to obtain from EBRD business model rationale for the introduction of the new e-procurement system. Given that there is no response from the Bank yet, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model and terms of reference for the implementation of the e-procurement system, provided that it will not be implemented by the consultant if implemented by the EBRD. The issue related to the substantiation of the business model proposed by the Bank is currently being discussed, after the clarification of which the relevant decision will be made. | The measure was included in the action plan of the RA Government for 2021-2026. The development of the terms of reference of the new e-procurement system is planned to be carried out within the framework of the contract for the provision of consulting services for the implementation of the GFMIS |  |  | Not started. | Preparation of terms of reference, organization of competitive procurement procedure for software development, system design and operation
16. Procuurement planning | 35. Improving the procurement planning system | 35․1 Develop RA Government draft decision on the introduction of a unified planning system for determining the cost estimates of items with similar characteristics automatically | MoF | - | December, 2020 | December, 2021 | 3rd decade of December 2023 | The same needs of customers are met with items with the same characteristics and cost estimates | The relevant proposals for the implementation of the mentioned measure were received and summarized from the RA public administration bodies based on the letter 01/26-1/3308-2020 of the RA Minister of Finance, dated 21.03.2020. | The implementation of the measure is interconnected with the development of new software for the e-procurement system |  |  | In progress. | The implementation of the measure is interconnected with the development of new software for the e-procurement system
17. Procurement Appeal System | 36. Improving the procurement appeal system | 36.1 Making changes in the RA Law "On Procurement" | MoF | - | December, 2021 |  |  | Functional and independent appeal system | The RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Amendments to the RA Law on State Duty", "On Making Amendments and supplements to the RA Civil Procedure Code" have been elaborated and submitted to public government bodies, international donor organizations and civil society for consideration. Discussions with the EU SIGMA Program Expert Group are ongoing. | The package of draft laws was adopted by the National Assembly on 17.11.2021 in the first reading. | The package of RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Supplements to the RA Law on State Duty", "On Making Amendments and supplements to the RA Civil Procedure Code", adopted by the RA National Assembly on 17.11.2021 in the first reading |  | In Progress | Adoption of the package of draft laws by the National Assembly in the second reading
10. PUBLIC INTERNAL FINANCIAL CONTROL AND FINANCIAL-BUDGETARY OVERSIGHT
18. Financial management and control | 37. Ensuring the introduction of financial management and control system | 37․1 Testing of FMS system methodology | MoF | - | December, 2020 | December, 2021 | Decembet 2022 | Piloted methodology of FMS | As of 2019, there are still draft legal acts for the introduction of the FMS, which need to be reviewed once again, considering them from the point of view of the implementation of the PB system, discussing them with the Civil Service Office. In order to test the FMS system, an agreement was reached in 2019 with the RA Ministry of Education and Science (there is an official letter from the Ministry of Finance and an agreement with the pilot ministry) to pilot the above methodology. The second state body that was selected and an agreement reached with the latter's representatives is the RA Ministry of Labor and Social Affairs. | As a result of the work with the development partner organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical support. In order to support the RA Ministry of Finance in the introduction of the financial management system, drafts of relevant technical specifications have been developed. |  |  | In progress | Finalize the pilot work, and as a result, complete the methodology approval work. | The deadlines required for the measure are short and there is a risk in securing the measure within the set timeframe. | Accelerate the work related to the testing of the FMS methodology as much as possible, assess the realism of the implementation of the measure and, if necessary, make a proposal for extension of the term. | GIZ
|  | 37․2 Adoption of FMS Concept and FMS Legislative Acts |  |  | 2021-2022 |  | 2022-2023 | · FMS adopted concept and legislation | During 2018-2019 the FMC draft concept has been elaborated with the support of GIZ. | It is related to the results of the measure 37.1 |  |  | Not started. |  | The implementation of the measure is related to the results of event 37.1, the implementation of which is assessed as risky. | Take measures to implement the 37․1 measure on time.
|  | 37․3 Introduction of FMS system in public sector organizations | MoF | SB | Since 2022 |  |  | · The process of introducing the FMS system is carried out according to the set schedule | As the measure is related to event 37.1, the work related to this event will start after the testing of the FMS system methodology and adoption of FMS concept and relevant legislation | It is related to the results of the measure 37.1 and 37.2 |  |  | Not started. |  | The implementation of the measure is related to the results of event 37.1 and 37.2 , the implementation of which is assessed as risky. | Accelerate 37.1 and 37․2 measures activities
19. Public sector internal audit | 38․ Carrying out external evaluation of the quality of internal audit | 38․1 Approval of the external audit quality assessment methodology | MoF | - | December, 2019 | December, 2021 | December, 2022 | Order approved by the RA Minister of Finance "On approving the procedure for conducting external evaluation of the internal audit quality | In the context of this measure, with the support of the World Bank, an external quality assessment manual was developed, which was piloted in 2 organizations of the RA public sector. RA Minister of Finance draft order has been elaborated. The draft order was discussed with the representatives of state bodies, was finalized and is ready for approval. | The measure is planned to be implemented with the support of development partner organizations. As a result of discussions with development partner organizations, a proposal was received from the World Bank to support the implementation of the measure, the scope of which is being adjusted. |  |  | Not started. |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the deadlines for the implementation of the measure are short, it is necessary to take steps to implement the measuree in due time. | Clarify the issue of those responsible for the implementation of the measure, organize the activities envisaged by the strategy of the measure as soon as possible. | WB
|  | 38․2 Carrying out external evaluation of the quality of internal audit in public sector organizations |  |  | 2020-2022 | 2021-2023 | 2022-2023 | All public sector organizations where an internal audit system is in place will be subject to external evaluation by the MoF. |  | Is related to the results of measure 38.1 |  |  | Not started. |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the implementation of the measure is related to the results of measure 38.1 which is considered risky | Clarify the issue of those responsible for the implementation of the measure, and take steps to organize the measure 38.1 in the set timeframe
Report on the quality of internal audit of the RA public sector
| 39․ Ensuring Internal Audit and External Audit Cooperation | 39․1 Define internal audit and external audit cooperation procedures | MoF | AC (by agreement) | December, 2023 |  |  | Joint order of the RA Minister of Finance and the Chairman of the RA Audit Chamber "On approving the order of internal-external audit cooperation" | The procedure for internal-external audit cooperation has been under development since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version and after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. | The procedure for internal-external audit cooperation has been under elaboration since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version and after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. |  |  | In progress | Make the document complete, submit to the RA Audit Chamber and Sbs for consideration and submit the revised document for approval as a result of discussions | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure
| 40. Emphasis on Performance Audit Capability and Provide practical application of 30% of the annual plan | 40․1 Approval of performance audit methodology | MoF | - | 2019-2020 | 2021-2022 | 2022-2023 | Approved order of the RA Minister of Finance "On approving the performance audit manual" | RA Minister of Finance draft order "On approving the performance audit manual" has been developed, which is in the process of revision, within the framework of which it is necessary to ensure the connection of the performance audit with the embedded PB system, which which will provide an opportunity to comprehensively assess the results of the programs of the PBs implementing budget programs considering it not only in the context of financial but also in the context of non-financial performance indicators. |  |  |  | Not represented |  | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure
|  | 40․2 Increasing the role of performance auditing in internal audit legislation |  |  | December, 2020 | December, 2022 |  | Requirement stipulated in the internal audit legislation, according to which the performance audit will make up 30% of the annual internal audit plan |  | It is related to the results of the measure 40.1 |  |  | Not represented |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the implementation of the measure is related to the results of measure 40.1 which is considered risky. | Clarify the issue of those responsible for the implementation of the measure, and take steps to organize the measure 40.1 in the set timeframe
|  | 40.3 Development of performance auditing skills of internal auditors operating in RA public sector organizations |  |  | 2020-2023 | 2022-2023 |  | Internal auditors in RA public sector organizations trained in performance auditing |  | It is related to the results of the measures 40.1 and 40.2 |  |  | Not represented |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the implementation of the measure is related to the results of measure 40.1 and 40.2 which is considered risky. | Clarify the issue of those responsible for the implementation of the measure, and take steps to organize the measure 40.1 ևand 40.2 in the set timeframe | (GIZ)
| 41. Development of professional knowledge and skills of internal auditors | 41․1 Elaborating a program for developing the professional knowledge and skills of internal auditors | MoF | - | December, 2020 | December, 2021 | December, 2022 | Internal auditors' professional knowledge and capacity are assessed, needs identified, development plan approved |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. |  |  | Not represented | Modernization of the internal audit qualification system will be carried out and modernization of the internal audit capacity building program. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
|  | 41․2 Optimization of continuous professional training courses for internal auditors |  |  | 2020-2022 | 2021-2023 | 2022-2023 | The internal auditors have the requirements of the RA legislation on internal audit, international advanced experience, theoretical knowledge of internal audit and practical skills. |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. |  |  | Not represented | Modernization of the internal audit qualification system will be carried out and modernization of the internal audit capacity building program. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
|  | 41․3. Elaboration of an online information system for the continuous professional training of internal auditors |  |  | 2020-2021 | 2021-2022 | 2022-2023 | Internal auditors undergo an annual continuous professional training program through an online information system |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. |  |  | Not represented |  | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
|  | 41․4 Review of the Public Sector Internal Auditor Qualification Procedure |  |  | December, 2021 | December, 2022 |  | Internal auditor qualification system based on relevant international approaches |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. |  |  | Not represented | Modernization of the internal audit qualification system will be carried out and modernization of the internal audit capacity building program. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
20. Central harmonization unit (CHU) | 42. CHU personnel recruitment and capacity building | 42․1 CHU personnel recruitment and capacity building | MoF | - | 2019-2021 |  | 2022-2023 | Necessary capacities are available in CHU | The relevant unit which was carrying out the functions of the CHU, was dissolved on February 24 of this year and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CHU. | The relevant unit which was carrying out the functions of the CHU, was dissolved on February 24 2022 and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CHU. |  |  | In progress | Recruitment of CHU staff and organizing training courses for staff capacity building | The relevant unit which will deal with the CHU functions, has not yet been specified and is staffed with specialists with relevant capabilities. | Clarify as soon as possible the issue of the unit dealing with the functions of the CHU and staff with specialists with relevant capabilities.
21. Financial and budgetary control | 43․ Ensuring effective financial and budgetary control activities | 43․1․ Review of financial-budgetary control legislation, update, development of new methodology for implementation of financial-budgetary control | MoF | - | 2020-2021 |  | 2022-2023 | By-laws defining the modern methodology of financial and budgetary control | In the context of this group of measures, the main problems in the system of financial-budgetary control were formulated in 2018-2019. The RA Government decision "On defining the procedure of financial and budgetary control of the Republic of Armenia" and declaring null and void the RA Government decisions dated July 11, 2002 N 1112 N and February 23, 2012 N 207 " has been elaborated which is under discussion | An expert mission was developed with the European Commission's TAIEX expert group to elaborate a new methodology document on the analysis of the status quo of the existing financial control system in Armenia and capacity-building program. However, it was not enough to achieve the strategy. |  |  | In progress | It is planned to continue the work within the framework of the EU SIGMA program.
|  | 43.2 Capacity building of specialists in the field of financial-budgetary control |  |  | 2022-2023 |  |  | Specialists in the field of financial-budgetary control have professional skills and have relevant knowledge |  |  |  |  | Not started.
|  | 43․3 Availability of necessary databases for risk assessment |  |  | 2020-2023 |  | 2022-2023 | Introduction of a new risk system based on complete, substantiated and justified information analysis | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. |  |  | In progress | Work is currently underway with donor organizations, in particular through the EU SIGMA program.
11. PUBLIC ASSETS AND PUBLIC INVESTMENT MANAGEMENT
22. Public assets management | 44. Ensure monitoring of government financial and non-financial assets | 44.1․Elaboration and approval of the methodology of public asset management and legal acts necessary for its introduction | MoF | - | 2020-2022 |  |  | Existing methodology on management of financial and non-financial assets of the Government, and legal acts approved in accordance with the RA legislation | An agreement was reached on the provision of IMF technical assistance for the implementation of the measure, within the framework of which the report "Program Budgeting and Management of Public Assets" was submitted to RA the Ministry of Finance for consideration. | In the framework of IMF technical assistance, the conceptual and methodological approaches to the public asset management were elaborated and submitted to the position of the RA Ministry of Finance. The remarks and suggestions of the RA Ministry of Finance were presented on the latter, on the basis of which the experts were offered to review the report. |  |  | In progress | Clarify further steps to be taken in this area based on the results of the study of proposals on conceptual and methodological approaches to public asset management. | The timing of the measure is short, and at present the conceptual-methodological approaches to public asset management are not specified. At the same time, the role of the RA Ministry of Finance in terms of developing and monitoring the methodology of public asset management needs to be clarified. | To formulate the position of the RA Ministry of Finance on the presented approaches as soon as possible. Based on the results, if necessary, initiate the design of relevant conceptual and legal documents. | (GIZ/IMF/RF MOF)
|  | 44.2 Implementation of trainings on asset management techniques in accordance with the approved legislation | MoF | SB |  |  |  | Specialists trained in accordance with the law on public assets | .The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  |  | Not started. |  | The implementation of the measure depends on the results of the measure mentioned in pointz 44.1. the implementation of which is assessed as risky | Take measures to implement the measures mentioned in point 44.1 in due time. | GIZ
|  | 44.3 Preparation and monitoring of financial and non-financial asset registers | SB | - |  |  |  | Asset Monitoring Report | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  |  | Not started. |  | The implementation of the measure depends on the results of the measure mentioned in pointz 44.1. the implementation of which is assessed as risky | Take measures to implement the measures mentioned in point 44.1 in due time.
| 45. Ensuring transparency of the sale, transfer, alienation process and the right to use non-financial assets | 45.1 definition of procedures for the sale, transfer, alienation process and the right to use non-financial assets will be reviewed. | MoF | MoTAI | 2022-2023 |  |  | Procedures for the sale, transfer, alienation process and the right to use non-financial assets are approved. | The activities to be carried out within this measure are the introduction of a public asset management methodology to be developed under measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  |  | Not started. |  | The implementation of the measure depends on the results of the measure mentioned in pointz 44.1. the implementation of which is assessed as risky | Take measures to implement the measures mentioned in point 44.1 in due time. | IMF
23. Public Investment Management | 46․ Creating a Legislative Basis: Public Investment Management Methodology | 46.1․ Elaboration of a public investment management manual | MoF | - | December, 2019 |  |  | Public Investment Management Manual has been developed and is ready for testing | 1. Within the framework of the works aimed at the introduction of the public investment program management system, in particular, the elaboration of a methodology for identifying, elaborating, evaluating and setting priorities of public investment programs the draft Public Investment Management Manual (hereinafter the Manual) was developed jointly with the experts of the World Bank (hereinafter the WB). According to the appendix approved by the RA Prime Minister's decision N 5-A of January 9, 2020 "On starting the budget process of 2021" of the RA Prime Minister, for the latter’s testing the RA Ministry of Economy has provided to the RA Ministry of Healthcare, Ministry of Education, Science, Culture, Sports, Ministry of territorial administration and infrastructure, in the defined timeframe "The form for the investment project concept and quality assessment" (the standard form) to present the new projects in excess of 70 million drams in the standard form. The pilot stages of the manual have passed 8 investment projects provided by the mentioned agencies. 2. The testing of the manual with the agencies was carried out in stages, by sectors. In this regard, in the first phase, from January 29 to February 14, 2020, 6 meetings and discussions were held, during which the information on the Manual was provided to the representatives of the relevant agencies, as well as consultancy on the completion of the Form per the Manual. 3. In the second stage, on February 24-28, 2020, a seminar-discussion was held with the participation of WB experts, experimentally selected ministries, representatives of the RA Ministries of Finance, Economy and the Office of the RA Deputy Prime Minister Tigran Avinyan, during which the WB experts gave a detailed reference to the principles of identifying problems within the framework of investment projects, setting goals, and action-intermediate result-end-impact-benefit "logical chain formation. Based on the relevant examples, the mechanisms for calculating the demand-risk analysis, as well as the financial-economic analysis of investment projects were presented. 8 new investment projects submitted by the RA Ministry of Health, the RA Ministry of Education and Science and the RA Ministry of TAI were studied. During the discussions, observations and proposals were submitted for all the projects, as a result of which the representatives of the ministries were offered to amend the provided investment project applications based on the submitted considerations and submit the revised version to the RA Ministry of Economy. 3․ In the 3rd stage, on March 12, 2020, and March 13, a video conference was held at the RA Ministry of Economy with the participation of the staff of the RA Ministry of Health, the RA Ministry of Education and Science and the WB experts. During the video conference, the considerations on the investment projects submitted in accordance with the Standard Form, provided by the agencies, were further discussed, on the basis of which it is planned to finalize the revision of the projects. As a result of the implemented works, the strengths and weaknesses of the Manual were identified, as well as the shortcomings were registered, localizing the Manual as much as possible, taking into account the situation in the Republic of Armenia. The above-mentioned works were summarized in April 2020. |  | • Elaboration of a draft Public Investment Management Manual | 2020 | Completed |  |  |  | WB
|  | 46.2․ Testing the Public Investment Management Manual and identifying deficiencies. |  |  | december, 2020 |  |  | Report on testing results and existing deficiencies. | The manual was tested in the following phases Phase 1 1. From January 28 to February 14, 2020 , meetings and discussions were held with the representatives of the RA Ministry of Health, the RA Ministry of Education, Science, Culture and Sport the RA TAI within the introduction of the Public Investment Management System on completing investment projects according to the Model in the framework of the manual test. 2. On February 24-28, 2020, with the participation of representatives of interested state agencies, in particular the RA Ministry of Territorial Administration, the Ministry of Health, the Ministry of ESCS, the Ministry of Finance, the Ministry of Economy, and the Office of the Deputy Prime Minister Tigran Avinyan, 5 seminars-discussions on the new initiatives completed by the relevant agencies in accordance with the form within the framework of the public investment management system implementation. 3. Given the coronavirus situation, further manual testing was performed online. Preliminary evaluation of investment projects has been carried out. 4. Taking into account that as a result of the study of investment projects the indicators of investment projects were not provided with sufficient accuracy, on the initiative of the RA Ministry of Economy organized on June 23, 2020 a remote workshop was organized and held the WB experts, within which the necessary indicators were discussed for each investment project, as a result of which it was decided that the "Human Life Value" indicator is missing in Armenia, while it is necessary for evaluating public investment, in particular, social programs. In this context, a working group has been set up to recruit relevant specialists to calculate this indicator. 5. As a result of the discussions with the selected pilot agencies, the investment project provided by the RA Ministry of Health was selected, additional work was done to include new indicators for the evaluation of the project. ։ The indicators of the considered project of a similar program provided by the WB experts were studied, within the framework of which the indicators became almost 75% comparable. In terms of 25% incomparable indicators ․ Preliminary feasibility study is planned to be carried out on August 3, 2020 with WB expertsto identify the missing indicators, but due to martial law, this process has been postponed to early 2021. In case of absence of "Human Life Value" index for Armenia in the mentioned period, the index calculated by the WB for Armenia will be taken into account ։ 6. As a result of the preliminary feasibility study carried out jointly with the WB experts, the practical testing phase of the Manual will be summarized, the results of which will be included in the Manual (as mentioned in point 46.1). ։ In the context of the above, it will be possible to fully assess the Manual, as a result of which it is planned to carry out the work of circulating the Manual among the relevant departments, summarizing and approving the considerations on the latter. Phase 2 On September 25, 2020, the RA Prime Minister held a consultation, during which the draft concept of public investment management was presented, and as a result the Prime Minister proposed to take note of the draft and instructed to continue the work on strategy revision and finalize the document. In continuation of the work on the introduction of the public investment management system launched in the first half of 2020, the scope of the agencies previously involved in the work on the introduction of the public investment management system has been expanded. In this context, an online discussion was held on November 4, 2020, chaired by the RA Deputy Minister of Economy Avag Avanesyan with the participation of the representatives of the relevant agencies and the second phase of the manual testing works has started During the discussion, the Deputy Minister provided details, in particular, on the purpose of the introduction of the public investment management system, features, provisions of the draft, as well as programs financed from the consolidated budget, the economic profitability of the latter. During the online discussion, clarifications were provided on the methodology of evaluation criteria for public investment programs stipulated by the Project, as well as the scope of competence of each department within the Project, project identification, project evaluation, prioritization and evaluation procedures. The role of the RA Ministry of Finance in the framework of the introduction and operation of the public investment management system was especially emphasized. In this regard, the representative of the RA Ministry of Finance was offered to present the problems and risks that are visible in the Sample and may hinder the budget process. The representative of the RA Ministry of Finance emphasized the process of public investment management, but the latter registered the issue of implementing the budget process on the basis of the Manual as a methodological guide. In this regard, the RA Deputy Minister of Economy pointed out that it can be stated that the process of public investment management is an adjunct to the budget process, does not imply a change in the budget process and the only change is the International Monetary Fund requirement that the list of planned programs be included in the 2022 budget documents. The process of public investment management is regular throughout the year and the identified projects can be included in the list of projects at any time, after passing the relevant procedures. During the online meeting, they also touched upon the issues to be further discussed by the RA Ministry of Finance, in particular, the issue of codes given to the programs at the planning stage (the application submitted to the RA Ministry of Finance and the program that went through the process of public investment management should have the same code, so that in the future they can be easily identified. As a result of the discussion, an agreement was reached between the participants to identify at least three project ideas for each agency on which joint work on the development of exemplary model forms will be carried out. In connection with the above, the RA Ministry of Economy has initiated separate meetings in each agency with the participation of the Deputy Ministers and employees of the relevant units during which the RA Ministry of Economy has presented and continues a detailed information on the introduction of public investment management system. In this regard, a schedule of preliminary meetings has been set for each agency. As of December 2020, separate meetings-discussions were organized with the representatives of the RA Ministry of Education, Science, Culture and Sport, the RA TAI, the RA TAI Water Committee, the RA Ministry of Justice, the RA Ministry of Emergency Situations As a result of these discussions, the mentioned ministries have already provided drafts of public investment programs, relevant lists, around which online substantive discussions have taken place, and provided consulting proposals. It should be noted that the work on the introduction of a public investment management system is ongoing; in 2021, separate meetings with other agencies are also planned. | The process of testing and correcting the shortcomings of the draft Public Investment Management Manual has already been completed. The draft manual is currently being finalized. | • The draft Public Investment Management Manual has been tested and shortcomings have been identified | 2021 | Completed |  |  |  | WB
|  | 46.3․ Review and approval of the Public Investment Management Manual |  |  | December, 2020 | December, 2021 | December, 2022 | The Public Investment Management Manual is approved by the RA Government | 1․ As a result of the discussions on the project, as well as the experimental work, it was necessary to amend the Manual. Relevant work is currently underway in the direction of the latter, with the aim of creating an effective system for multifactorial evaluation of public investment programs, based on which the cross-sectoral priorities of those programs are determined. 2. Work has been underway for about 6 months to review the manual, taking into account the sequential implementation of all stages and components of the test, summarizing the results, and making appropriate amendments. The final summarization of the manual is planned to be held by 2nd ten days of Decemeber, 2021 During the testing of the manual, shortcomings were identified, which are being addressed, in particular:  During the testing of the public investment management manual, there was a need to create a legal basis for the introduction of a public investment management system. As a result the RA Prime Minister draft decision "On approving the Procedure for Identifying, elaborating and Evaluating and Determining Priorities of Public Investment Programs in the Republic of Armenia, Methodology for Evaluating Public Investment Programs, and Model form for Elaboration and Evaluation of Public Investment Program" has been elaborated. (hereinafter the Draft).  It is necessary to carry out harmonization and compliance of legislation and legal acts related to the introduction of public investment management system.  In addition to the single Public Investment Management Manual, it is necessary to develop brief methodological manuals / guides for each stage of the Public Investment management process, which will be useful to both public and private sector representatives.  Ensuring the involvement of relevant units of ministries, including financial departments, in training / retraining processes and the continuity of these courses  Establishment of relevant professional sectoral target groups to promote the effective implementation of public investment and to ensure the public investment management process.  In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the performance of statistical work aimed at increasing the accountability of public investments within the framework of the manual. | Within the framework of the introduction of a public investment management system the RA Prime Minister Decree N 472-L, dated May 4, 2021 "On Approving Procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project" (PIM decision) was elaborated and adopted. Based on the considerations presented as a result of the manual testing, the PIM manual was also amended in parallel Work is currently underway to finalize the revision of the Public Investment Management Manual the manual was reviewed once again together with the World Bank experts and finalized, appropriate adjustments have been made, taking into account the results of the sequential implementation of all stages and components of the practical piloting of the manual as well as the provisions and procedure provided by the PIM decision | •Approval of Procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project" (RA Prime Minister Decree N 472-L, dated May 4, 2021)։ |  | In progress. | Completion of the review of the Public Investment Management Manual in cooperation with the RA Ministry of Finance |  |  | WB
| 47. Capacity building of public investment specialists | 47․1․ Elaboration of a capacity building program for public investment specialists for the training on public investment management manual | MoE | - | December, 2020 | December, 2022 |  | The Public Investment Management Manual is approved by the RA Government | 1․In the framework of the introduction of the Public Investment Management System, during the first half of 2020 seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy After the seminars / trainings aimed at capacity building, the needs of public investment specialists were assessed in the framework of which the needs of specialists have been identified, particularly in the component of financial calculations. In this regard, the RA Ministry of Finance is expected to be more actively involved in the implementation of the mentioned event. 2.In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the accountability and statistics of the public investments carried out within the framework of the manual, without which it is possible to record a 70% assessment. 3․in the framework of the introduction of the Public Investment Management System, seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy | 1․ 1․ Within the introduction of the PIM system, as well as in terms of the procedure defined by the PIM decision and completing the Model Form defined by the Decision N 472-Լ, dated May 4, 2021, d 2021, the Public Investment Policy Department of the RA Ministry of Economy conducted workshops and work discussions on capacity building with the participation of representatives of all interested bodies, including local self government bodies according to the agreed program and agenda. In particular, online trainings on public-private partnership with the initiative of the Commercial Law Development Program under the United States Department of Commerce with the participation of relevant bodies (RA Ministry of TAI, RA Ministry of High-Tech Industry, RA Ministry of Education, Science, Culture and Sport, RA MoF, Road Department SNCO, City of Yerevan) Within the framework of the working visit of the World Bank experts to Armenia, a training-workshop was organized on the indicators necessary for the construction of the financial and economic model of public investment programs, calculation mechanisms, in particular, the calculation of the internal rate of economic profitability. |  |  | In progress. | 1․Elaboration of a methodology and training program jointly by the RA Ministry of Economy and the RA Ministry of Finance for capacity building of public investment specialists as needed within the framework of the Model Form approved by the PIM decision to conduct additional trainings for the representatives of the concerned departments 2․Completion of the elaboration of a program for capacity building of public sector specialists as a result of seminars-discussions, trainings and workshops 3․Elaboration of PIM videos and guides ։ |  |  | WB
|  | 47.2 Capacity building |  |  | 2020-2021 |  | 2022-2023 | The capacity of public investment specialists is sufficient | Within the framework of the introduction of the Public Investment Management System, the testing of the Public Investment Management Manual, activities aimed at developing the capacity and training of public sector specialists are carried out, which are of a continuous nature and are envisaged during 2021. Taking into account the working meetings held in the agencies, as well as the subsequent discussions, responsible representatives from each agency are invited to participate in the professional training courses. Phase 1․ 1 A total of 40 public sector specialists (RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office) were trained and capacity building workshops were held with them within the framework of introduction of public investment management system. 2․ During the first half of 2020, 16 seminars-discussions / workshops were organized jointly with the RA Ministry of Economy and WB  This year from January 28 to February 14, 6 working discussions were held in the RA Ministry of Economy with the representatives of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI on the completion of a common model form (hereinafter referred to as the Model Form) quality assessment concept of the investment project in the framework of the introduction of the Public Investment Management System From February 24 to 28, this year 5 seminars-discussions on new initiatives completed by the relevant agencies related to the Model form within the framework introduction of the Public Investment Management System were organized and held in the WB Armenia Office with the participation of the representatives of the interested state agencies, in particular, RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office  On March 12 and 13, 2020, 2 video conferences were held at the RA Ministry of Economy with the participation of the WB experts, with the participation of the employees of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, with the WB experts.  On June 23, 2020 organizing 1 online workshop on economic and financial evaluation of investment projects for the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA MTAI with the initiative of the RA MoE and by the WB experts  Conducting a separate remote discussion with the representative of the RA Ministry of Health, during which the indicators of the investment project provided by the RA Ministry of Health were observed, as well as they were compared with the indicators of a similar program.  An online discussion was held with the relevant representatives of the Ministry of Education and Science of the Republic of Armenia, within the framework of which the investment projects with a large social component were considered in detail, peculiarities of applying the standards applicable to them and elaboration/drafting of these projects. In this context, within the framework of the already established experience, work is being done on the evaluation criteria of large social components - programs that do not have primary economic benefits, but provide secondary benefits. Phase 2  During the second phase of the manual testing, 18 discussions were held with the involvement of representatives of about 100 public investment sectors, in particular, representatives of the RA TAI the RA TAI Water Committee, the RA MOESCS, the RA Ministry of Emergency Situations and the Ministry of Justice. | 1. In the first half of 2021, a total of 9 meetings, including online, about 120 public sector specialists (representatives of the public administration system, local self-government bodies) were trained, capacity building workshops were held with the latter in the framework of meetings-discussions on the introduction of the PIM system, as well as the awareness of the procedure stipulated by the PIM decision completion of model form. The mentioned meetings-discussions were conducted both online and in the format of local meetings in the sectorial ministries during which detailed presentation on the information related to procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project was presented. 2. In the second half of 2021 around 9 capacity building courses were organized about 120 public sector specialists with the participation of representatives of the public administration system ։ 3. Working discussions are regularly held in the RA Ministry of Economy with the participation of the representatives of the sectoral ministries in order to improve the legislative framework of the PIM system. | • Seminar-discussions and workshops aimed at capacity building of PI 120 specialists. |  | In progress | Regular implementation of capacity building meetings and ensuring continuity. |  |  | WB
| 48. The public investment projects included in the 2023 annual budget are prepared in accordance with the requirements of the defined PIM manual | 48.1. Practical application PIM manual in the budget process | MoF | MoE | December, 2021 | December, 2022 |  | The public investment projects included in the 2023 approved budget have been developed in accordance with the requirements of the PIM manual | An agreement has been reached with the IMF for assistance, under which work has begun since October, in 2020. and are under discussion. The measure was included in the draft decision of the RA Government on making changes in the decision 1716-L of the RA Government, within which the term was extended for 1 year and corresponding changes have been made in the titles of the target name and result evaluation indicators. The extension of the term of the measure is conditioned by the one-year extension of the implementation period of the measure "46.3 ․ Review and approval of the Public Investment Management Manual, as well as with the deadlines for organizing the budget process. | The report "Public Investment Management an Budget Process" was developed within the framework of IMF support. The observations of the Ministry of Finance on the latter were presented, which are still under discussion. |  |  | In progress | After the approval of the Public Investment Management Manual, in the framework of the budget process, the requirements for planning capital expenditures in accordance with the requirements of the manual will be defined within the framework of the methodological instructions for the preparation of the state budget. |  |  | (GIZ/IMF/ADB/WB/AFD)
| 49.Monitoring of public investment projects | 49.1 Monitoring of public investment projects | MoF | MoE | 2022-2023 |  |  | Published report on the results of the monitoring of public investment projects | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines. | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines. |  |  | Not started | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and may require external technical assistance, of which no clarity is currently available. | Depending on the course of the event referred to in point 48.1, submit a proposal to revise the timing of the event as needed. | (GIZ/IMF/ADB/WB)
12․FINANCIAL MANAGEMENT IN SELF LOCAL GOVERNMENT BODIES
24. Efficiency of financial management in local self-government bodies | 50. Development of capacities and professional skills of the administrative staff of local self-government bodies | 50.1․ Implementation of public finance management reform program in local self-government bodies | MoF | MoTAI | 2020-2023 |  |  | Study reports | Within the framework of this measure, the work on PFM reforms in local self-government bodies is currently carried out directly by the RA Ministry of Territorial Administration, which is the coordinator of the measure. Harmonization of program budgeting methodologies of community and national level. 2017 Elaboration of a program budgeting training program . Availability of the 2015 PB curriculum. Organizing and holding training on program budgeting methodology, its application and PB awareness for the administrative staff of the local self-government bodies of the enlarged communities in 2014-2020. 2014-2020 Development of competencies and professional skills of the administrative staff of local self-government bodies. Providing technical assistance, advice to financial managers of municipalities, staff members involved in the process of preparing the annual program budget for 2015 to 2020. 2015-2020 Availability of annual program budgets for large communities Providing technical assistance and consulting on community annual program budget development and holding public hearings in 52 enlarged communities for 2016 to 2020. 2016-2020 Existence of brief program budgets for the mentioned years for all the communities enlarged during those years. Providing technical assistance and consulting on quarterly and annual monitoring and evaluation of community annual program budget plans in enlarged communities for 2016 to 2020 . 2016-2020 Availability of program budget monitoring quarterly and annual plans for all communities enlarged during those years. Implementation of the "Citizen Participation in Community Budgeting" program in 10 pilot communities within the framework of the regional program funded by the Eastern Partnership Regional Public Administration Reform Fund. 2018-2020 May Development of competencies and professional skills of the administrative staff of local self-government bodies with knowledge and experience necessary for the further application of active methods of civic participation in budgeting processes. -Elaboration and publication of a "Participation of Residents in the Local Budgeting Process" participatory budgeting manual. June, 2019-2020 the manual is available Elaboration of "Gender-sensitive budgeting at the community level", GIZ, UNDP 2019-2020 the draft manual is available | 1. Summary of the results of the "baseline study of the current system of internal financial control in local self-government bodies" conducted in September-December, 2020 and discussion of further steps 2. PB budget approval in 52 unified communities in 2022, budget drafting in PB format, public discussions on them 3. Integration of gender sensitive budgeting approaches in 20 community budgets 4. Study on the application of APSAS in 52 merged communities, as well as the applicability of the APSAS developed handbook for communities 5. Summary of the results of the "baseline study of the current status of public investment management in local self-government bodies" conducted in September-December, 2020 and discussion of further steps | • Summary of the results of the baseline study of the existing system of internal financial controland outline of further steps • budget approval in 52 enlarged communities in 2021 and 2022 in PB format, brief budget drafting in PB format, public discussions on them • Development of participatory gender budgeting manuals at the local level • Integration of gender sensitive budgeting approaches in 20 community budgets • Study on the application of APSAS in 52 merged communities, as well as the applicability of the APSAS developed handbook for communities • Summary of the results of the baseline study of the current status of public investment management in local self-government bodies and outline of further steps |  | In progress | 1․Increasing the effectiveness and independence of internal audit in communities, as well as elaborating standardization templates for internal audit 2․Ensuring the introduction of mandatory budgeting of Program Budgeting as a community budget in the communities by law 3․Introduction of Gender budgeting in 10 enlarged communities 4․Elaboration of the PIM concept and manual in the communities, piloting and final introduction 5․Revision of the relevant legal framework for the introduction of the PIM system in the communities |  |  | GIZ
Transparent and participatory budget process plans at the local self government bodies
|  | 50.2․ Monitoring of the public financial management reform program in local self-government bodies and full implementation | [5 empty] | Employees of local self government bodies capable of implementing public finance management reforms | Elaboration of an IPSAS-based accounting manual based on International Public Sector Accounting Standards. Providing the manual to all enlarged communities and interested structures. Preliminary study of the use of IPSAS-based accounting manual and standards in enlarged communities, identification of gaps and submission of recommendations for improving the system operation. Study of the preliminary situation of the property management process of enlarged communities, identification of gaps and submission of proposals for the improvement of the system. Preliminary study of the functions, rights and scope of responsibilities of the administrative heads of the settlements of the enlarged communities and submission of proposals for the improvement of the activities. | 1․ Implementation of capacity building activities for the preparation of community budgets, public discussion, approval, implementation and approval of reports in 52 enlarged communities in the PB format including through online training modules (placed in community management information system) have continued. 2․Elaboration of a database of emergency interventions developed for the administrative leaders of 52 unified communities, based on real experience and cases have continued. 3․Implementation of capacity building activities for the implementation of APSAS in the communities, including through online training modules (placed in community management information system) have continued 4․Elaboration and piloting of consolidated financial reporting methodologies continued in 2 advanced enlarged communities have continued | • Implementation of capacity building activities for the preparation of community budgets, public discussion, approval, implementation and approval of reports in 52 enlarged communities in the PB format including through online training modules (placed in community management information system) • Elaboration of a database of emergency interventions developed for the administrative leaders of 52 unified communities, based on real experience and cases • Implementation of capacity building activities for the implementation of APSAS in the communities, including through online training modules (placed in community management information system) • Elaboration and piloting of consolidated financial reporting methodologies continued in 2 advanced enlarged communities • Study of the process of managing the property of enlarged communities • Study of the functions, rights and responsibilities of the administrative leaders of the settlements of the enlarged communities |  | In progress | 1․Support for next year's program budgets anf their summary budgets in 52 enlarged communities through intensive implementation of capacity building measures 2․Improving the APSAS system in 10 enlarged communities 3․Development of a public service cost formula 4․Elaboration and implementation of capacity building measures necessary for the introduction of the PIM |  |  | GIZ
13. EXTERNAL CONTROL AND LEGISLATIVE CONTROL
25. Control of the financial-budgetary sphere by the National Assembly | 51. Provide external control (Reports of annual budget and AC ) | 51.1 Review of annual draft budgets | NA (with agreement) | AC (with agreement) | 2019-2023 |  |  | · More effective study of the draft annual budget | In the RA NA Standing Committees and their joint sittings, the preliminary version of the RA 2021 state budget and later on the Draft was discussed | The RA NA Standing Committee on Financial-Credit and Budgetary Affairs in the joint sittings with the sectoral committees of the National Assembly, later also in the sittings of the National Assembly, discussed the RA 2022 the draft state budget. |  | Activities for 2020 and 2021 are carried out | It is a periodic process | During 2022 discussions of the preliminary version of the RA 2023 state budget, and later the Draft, are envisaged in the standing committees of the RA NA and their joint sessions.
|  | 51.2 Study of the annual report on the execution of the state budget and AC conclusion on the latter and organizing hearings with audited state bodies | [5 empty] | · More Effective Study of AC reports on annual financial statements | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2020 state budget execution process. The monitoring was carried out on the basis of inquiries from the Budget Office commission, each month, through the study and analysis of references with comparative analysis. • The annual report on the execution of the RA 2019 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly. • studied the references provided by the Government on the execution of the quarterly, semi-annual and nine months of the state budget of the Republic of Armenia for 2020 (also discussed at the sitting of the commission), as well as 28 current conclusions of the Audit Chamber on the execution of the first quarter semi-annual of the state budget of the Republic of Armenia 2020, • cooperates with non-governmental organizations ։ | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2021 state budget execution process. The monitoring was carried out on the basis of the study և analysis of the references with the comparative analysis obtained from the Budget Office, each month, The budget office has prepared and provided to the Commission references with comparative analysis on the collection of state budget revenues of 2021, according to the process of expenditure execution, the RA state debt of 2021 and the main socio-economic indicators • the annual report on the execution of the RA 2020 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly, • studied the references on the execution of the first quarter and nine months of the state budget of the Republic of Armenia for 2020, as well as first quarter, semi-annual and nine months of the state budget of the Republic of Armenia 2021, • cooperates with non-governmental organizations ։ | • Establishment of a Subcommittee on Audit Issues in the Composition of the NA Standing Committee on Financial-Credit and Budgetary Affairs • Study of Annual report on the execution of the state budget for 2020 and the AC opinion on the latter. | Activities for 2021 are carried out | It is a periodic process | During 2022 RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • will monitor the 2022 state budget execution process • the annual report on the execution of the RA 2021 state budget will be discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, • will study the references on the execution of the first quarter, semi annual and nine months of the state budget of the Republic of Armenia for 2022, as well as the current opinions of the Audit Chamber which relate to the execution of nine months of the RA state budget for 2021, first quarter and first semi-annual semi-annual of the state budget of the Republic of Armenia 2022
|  | 51.3 Exercising post-audit control by the Committee | [5 empty] | Exercising post-audit control by the Committee | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, which convened 2 sittings during 2020 and studied 36 current conclusions of the Audit Chamber. of which 28 on the execution of the first quarter and semi-annual of the RA 2020 state budget | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, convened 3 sittings during the seventh convocation of the National Assembly, studied 46 current conclusions of the Audit Chamber. During the eighth convocation of Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly convened 2 sittings, studied 32 current conclusions of the Audit Chamber. |  | Activities for 2021 are carried out | It is a periodic process | During 2022 the Standing Committee on Financial-Credit and Budgetary Affairs of the AR National Assembly will study and discuss the current conclusions of the Audit Chamber.
| 52. Capacity building of the Budget Office, NA deputies and experts of committees | 52.1 Institutional-internal capacity building of the budget office | NA (with agreement) | - | 2019-2023 |  |  | The budget office has the necessary tools to carry out its functions | On September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, the 2020-2023 development strategy of the Budget Office of the RA National was approved, according to which in the context of institutional capacity building of the Budget Office it is planned to expand the functions. In particular, 1. Providing information on the observance of fiscal rules defined by the Government in accordance with parts 8.2 and 8.4 of Article 21 of the Law on the Budget System of the Republic of Armenia and Part 7 of Article 5 of the Law of the Republic of Armenia "on Public Debt" 2. Providing information on the inconsistencies, elimination of distortions, implementation of recommendations in the current conclusions submitted by the Audit Chamber to the National Assembly, 3. Providing opinions to the deputies and factions of the National Assembly - the authors of the draft laws on the significant reduction of the state budget revenues or the increase of expenditures 4. Preparation of references on gender sensitivity of state budget expenditures In order to implement the changes defined by the strategy, a legal package of changes has been developed, according to which corresponding changes and additions are envisaged in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly. It was discussed by the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs, the staff of the National Assembly and other specialists. | On September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, the 2020-2023 development strategy of the Budget Office of the RA National was approved. In order to implement the changes defined by the strategy, a legal package of changes has been developed, according to which corresponding changes and additions are envisaged in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly. The package was submitted to the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs for consideration. For capacity building of the budget office staff, the experts participated in professional capacity building courses. | • Approval of the 2020-2023 development strategy of the Budget Office of the RA National Assembly |  | In progress | The legal package of changes and supplements in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly will be studied by the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs, will be discussed and a decision will be made to put it into circulation with the expectation of approval by the National Assembly
|  | 52.2 Capacity building of NA deputies and experts of committees |  |  | 2020-2023 |  |  | The NA deputies and the experts of the committees effectively carry out the study of the draft annual budget, as well as the control over the execution of the state budget |  | The Budget Office, within the framework of its continuous capacity building function of the National Assembly, organized 2 workshops on budget process of the Republic of Armenia, program and gender-sensitive budgeting for NA deputies, their assistants, factions’ experts, and experts of financial and budgetary supervision standing committee. | • Organization of 2 workshops on budget process of the Republic of Armenia, program and gender-sensitive budgeting for NA deputies, their assistants, factions’ experts, and experts of financial and budgetary supervision standing committee. |  | In progress | The Budget Office of the RA National Assembly, within the framework of its continuous capacity building function of the National Assembly, envisages seminars, workshops on public finance management, including program budgeting, gender-sensitive budgeting, SDG and gender budgeting for NA deputies, their assistants, NA staff, standing committees and factions. Within the framework of the UN Development Program "New Armenia - Modern Parliament", trainings are planned for the NA deputies and experts of the committees.
26. Independence of the Audit Chamber and external audit of the government's annual financial statements | 53. Defining and implementing 2020-2023 strategic goals of Audit Chamber ․ | 53.1 Strategy of the RA Audit Chamber and elaboration and approval of action plan for its implementation | AC (by agreement) | - | 2019-2020 |  |  | Audit Chamber 2020-2023 ․ Strategy and Action Plan Approved in accordance with ISSAI | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop and approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation. The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed (basis RA Audit Chamber Decision 150-Լ, dated August 7, 2020). | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop and approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation. The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed (basis RA Audit Chamber Decision 150-Լ, dated August 7, 2020). | • Approval of the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation (RA Audit Chamber Decision 150-Լ, dated August 7, 2020) | 2020 | Completed
|  | 53.2 implementation of measures approved by the Audit Chamber strategy for 2020-2023 |  |  | 2020-2023 |  |  | The objectives set by the strategy are implemented in accordance with the defined schedule | The Strategic Development Plan of the Audit Chamber of the Republic of Armenia for 2020-2023, the action plan for its implementation approved by the RA Audit Chamber Decision 150-Լ , dated August 7, 2020 includes all the defined indicators. The Audit Chamber for the implementation of indicators, held an online presentation on the strategy for the external and internal stakeholders of the Audit Chamber (including the Ministry of Finance, the National Assembly, donor organizations, partner accounting bodies) on December 20, 2020. | The Strategic Development Plan of the Audit Chamber of the Republic of Armenia for 2020-2023, the action plan for its implementation approved by the RA Audit Chamber Decision 150-Լ , dated August 7, 2020 includes all the defined indicators. The Audit Chamber for the implementation of indicators, held an online presentation on the strategy for the external and internal stakeholders of the Audit Chamber (including the Ministry of Finance, the National Assembly, donor organizations and partner accounting bodies) on December 20, 2020. Within the framework of the implementation of the Strategic Development Plan, the following activities were carried out during the reporting period with the support of the SIGMA Program: 1) The package of amendments to the articles related to the RA Audit Chamber in the RA Constitution and the RA Law “On Audit Chamber” has been developed, which was officially sent to the RA National Assembly by the RA Audit Chamber On October 7, 2021 and the RA Government, 2) discussions on the structure of the communication strategy of AC and preparations for elaboration were carried out: with the support of the Swedish National Audit Office - 1) 25 employees were trained on "Performance Accounting", 2) Elaboration of the manual for the performance audit of the AC has started. With the support of the United Nations Development Program (UNDP), three experts (qualified auditors) and one IT specialist were involved in the audits of the Audit Chamber. With the joint support of the US Government Accountability Office (GAO) and USAID: 1) Design works of the quality management system of the AC were carried out, 2) Arrangements have been made to modernize the auditing planning process. In order to monitor the implementation of the above measures, the Audit Chamber conducts semi-annual online meetings on the implementation of the strategy with external stakeholders assisting the Audit Chamber (including donor organizations, partner audit bodies). |  |  | In progress | Process for the discussion of the legal reform package developed with the support of SIGMA program and creation of an agenda based on it by the RA NA. Elaboration and approval of communication strategy - With the joint support of GAO and USAID, the system for quality management and planning process of the AC activities will be elaborated. With the support of the Swedish National Audit Office, the manual for performance audit of the AC will be elaborated, professional trainings will be held. UNDP will continue to support in the involvement of experts /qualified auditors/ specialists in the 2022 audits of the Audit Chamber |  |  | (GIZ)
| 54. Capacity building of AC staff and Improving professional skills | 54.1 Development and approval of the capacity building program of the AC staff |  |  | 2022-2023 |  |  | AC auditors perform audits in accordance with ISSAI standards | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFC strategy. | The measure is included in the Strategic Development Plan of the RA Audit Chamber for 2020-2023, and the plan of measures for the implementation of the Strategic Development Plan defines the implementation dates envisaged by the PFMS strategy. | Inclusion of the staff capacity building program in the 2020-2023 strategic development plan of the RA Audit Chamber. |  | In progress | Preparations are being made to ensure these indicators within the set timeframe in the scope of the implementation of the Strategy |  |  | (GIZ)
|  | 54.2 Capacity building of AC staff and improvement of professional skills | [5 empty] | Qualified External Auditors | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFC strategy. There are preliminary agreements for providing external support to this measure | The measure is included in the Strategic Development Plan of the RA Audit Chamber for 2020-2023, and the plan of measures for the implementation of the Strategic Development Plan defines the implementation dates envisaged by the PFMS strategy. In the reporting year, with the support of GIZ, 55 employees participated in the auditor qualification course "Fundamentals of Financial Accounting" . | 55 employees of AC participated in the auditor qualification course "Fundamentals of Financial Accounting" . |  | In progress | Preparations are being made to ensure these indicators within the set timeframe in the scope of the implementation of the Strategy |  |  | (GIZ)
14. GOVERNMENT FINANCIAL MANAGEMENT INFORMATION SYSTEM (GFMIS)
27. Government Financial Management Information System (GFMIS) | 55. Introduction of the main components of the GFMIS - Phase 1 | 55.1 Acquirement of consulting services for the revision of GFMIS tender documents | MoF | MoHTI | December, 2020 |  |  | The tender processes were organized and carried out for purchasing consulting support services for GFMIS introduction. | On May 7, 2020 the first stage of the two-stage procurement process for the selection of a consultant assisting the Ministry of Finance in the process of introduction of the GFMIS was organized. 7 organizations applied for pre-qualification, of which 5 became pre-qualified participants, "Harmony" Foundation, Ernst & Young CJSC, AAM Management Information Consulting Ltd., Deloitte Armenia CSJC, Moore Management Consulting Ltd. Further on, the negotiation phase has started. From now on, the stage of negotiations has begun. On 5․11․2020, the pre-qualified participants were provided the invitation of second phase tender. Deadline for submitting bids is set 25.01.2021 by invitation. and as of that day, one of the 5 pre-qualified organizations, the "Harmony" Foundation, has submitted a bid. The latter's bid is under evaluation. | In January-April, 2021 the results of the two-stage procurement process for the selection of a consultant assisting the MoF in the GFMIS introduction process have been summarized. On 20.04.2021 a contract was signed with the winning company for the provision of consulting services in the framework of the GFMIS introduction program. Within the contract, the elaboration of the report of the first stage of the project introduction defined by the contract terms of reference schedule has started in the framework of which the consultant presented the management manual of the GFMIS introduction program. | • A tender was held to select a consultant to assist the MoF in the GFMIS introduction. • As a result of the tender a consultant was selected, with whom a contract was signed. | 2021 | Completed |  |  |  | RF/Mof
|  | 55.2 Organization of GFMIS acquistion |  |  | 2020-2021 |  | 2022-2023 | The complete package of documents for the implementation of the GFMIS tender has been drawn up, the tender has been held | Will be implemented 55.1. after the selection of the Consultant presented by the measure within the established timeframe. | The activities of the second stage of the GFMIS introduction, envisaged by the contract signed with the expert, have started per the business process analysis of all modules/subsystems of the GFMIS, diagnosis, identification/formulation of final business processes, definition of alternatives and elaboration of a terms of reference of the version selected by the MoF. | The GFMIS introduction envisaged by the contract concluded with the expert has started. |  | In progress | As a result of summarizing the works of the 2nd stage envisaged by the contract signed with the consultant, the terms of reference necessary for the acquisition of the software of the modules included in the GFMIS program will be developed, on the basis of which the procurement process will start. |  |  | RF/Mof
| 56. Introduction of the main components of the GFMIS - Phase 2 | 56.1 Start of GFMIS implementation program elaboration |  |  | December, 2022 |  | December 2023 | GFMIS implementation program developed by the company recognized as the winner of the tender within the timeframe set in the ToR. |  |  |  |  | Not started |  |  |  | WRF/Mof
|  | 56.2 Training of GFMIS users |  |  | December, 2022 |  | December 2023 | GFMIS users are trained | [8 empty] | RF/Mof

## Used terms
Terms used in the column "Status" of the Report
Completed | The measure is completely done.
In Progress | The works on the implementation of the measure have started,considered to be in progress. The works envisaged within the framework of the measure have not been completed yet.
Not started | The works on the implementation of the measure have not started yet, mainly due to depending on the results of other measures.
It is a periodic process | The actions defined by the measure are periodic processes, which are an integral part of the ongoing functions of the state body. The results of these measures do not have a clear beginning or end.
Not started | No information was provided on the progress of the measure.
Risky | There are risks associated with the on time implemention of the mesaure.