## PFM
ANNUAL REPORT FOR 2022 On the implementation of the action plan measures to be implemented in PFMSR 2019-2023
Sector/component | Target | Measures | Performer | Co-performer | Deadline | Deadlines revised by the RA Government Decision N 283 -Լ, dated 04․03․2021 | Deadlines revised by the RA Government Decision N 2189 -Լ, dated 30․03․2021 | Outcome evaluation indicators | Progress of measures and done activities/achievements (30.12.2020) | Progress of measures and done activities/achievements (30.12.2021) | Progress of measures and done activities/achievements (30.12.2022) | Outcome | Actual execution date | Status (see used terms) | Next steps (activities) | Issues and risks related to measure implementation | Risk management measures | Development partner organization supporting the implementation of the measure present (suggested)
1 | 2 | 3 | 4 | 5 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15
1․ FORECAST of MACROECONOMIC AND BUDGET INDICATORS, FINANCIAL RISK ACCOUNTABILITY
1. Forecast of macroeconomic and budget indicators | 1. Elaboration of final versions of the model (s), introduction in the Ministry of Finance and full operation | 1.1 relaboration of final versions of DSGE models | MoF | - | December, 2019 |  |  | Availability of up-to-date tools for fiscal policy analysis and medium-term macroeconomic forecasts | DSGE model is elaborated | DSGE model is elaborated |  | Availability of DSGE model for macroeconomic forecasting | December 2019 | Completed
|  | 1.2 Introduction and full operation of DSGE models |  |  | 2020-2023 |  |  | Introduction of new tools and use in the budget process, more comprehensive and accurate estimates and analysis on impact of fiscal policy on the economy | DSGE model was tested and finalized during 2020 (as a result of joint working discussions with IMF experts) . Preliminary versions of relevant documents have been developed. Discussions on the elaboration of a working document and elaboration of separate sections were carried out jointly with IMF experts. With the help of the model, the effects of the coronavirus multifaceted fiscal measures on the Armenian economy were assessed. Based on the results, the 2021-2023 MTEF macro-fiscal framework was created (including the preliminary version of the draft law on the state budget for 2021). Later, in the conditions of new information available and current developments, re-evaluations were carried out through the model, on the basis of which the macro-fiscal framework underlying the 2021 State Budget was formed. An accompanying analytical and evaluation document and model manual has been developed. Discussions on the development of a working document and elaboration of separate sections were carried out jointly with IMF experts. The model assesses the social, economic and financial impacts of the implemented and to be implemented fiscal measures. Based on the results, the 2021-2023 MTEF macro-fiscal framework was created (including the preliminary version of the draft law on the state budget for 2021). Later, in the conditions of new information available and current developments, re-evaluations were carried out through the model, on the basis of which the macro-fiscal framework underlying the 2021 State Budget was formed | During 2021, the model was used in the process of building the MTEF 2022-2024 and 2022 state budget macro-fiscal framework, a quantitative assessment of the impact of the forecast fiscal measures was carried out, and a forecasting policy scenario was developed. The final documentation of the related analytical-evaluation activities performed during the elaboration of the model, in particular, the article "Estimates of Fiscal Multipliers for Armenia" (Estimates of Fiscal Multipliers for Armenia), as well as elaboration of a manual for using the model was carried out (The article was presented at the 11th annual conference of the Armenian Economic Association). The final editing of the joint working document of the RA Ministry of Finance and the IMF was carried out together with the IMF experts taking into account the comments and suggestions of the reviewers. | During 2022, it was applied in the process of building the macro-fiscal framework of the MTEF 2023-2025 and the 2023 State Budget: a quantitative assessment of the effects of the planned fiscal measures and building a policy scenario of forecasts were carried out. The working document on “Ararat Fiscal Strategy Model/AFSM DSGE model” was jointly published by the RA Ministry of Finance and the IMF. | Application of the DSGE model in the 2021 and 2022 budget process | Activities envisaged for 2020 and 2021 are completed | It is a periodic process | It is planned to use the model in the elaboration of the state budget, as well as for assessing the effects in various policies/events/shocks arising from the imperative of the time. |  |  | IMF(RF MOF)
| 2. Assessing the effects of deviations between fiscal policies planned and actually implemented on the basis of macro-founders and fiscal rules | 2.1 . Detection of deviations between planned and actually implemented fiscal policy and impact assessment | MoF | - | 2020-2023 |  |  | Improved estimates of fiscal risks at the macroeconomic level. | It is envisaged to implement starting from 2021, within 10 days after the publication of the annual state budget indicators, within 15 days after the publication of the annual GDP. | On the basis of actual data of 2020, the deviations of the planned and actual fiscal policies were assessed, and their macroeconomic impacts were given. The assessment results were presented in the form of a presentation, and were included in the annual report of 2020 state budget. | Deviations of planned and actual fiscal policies and their macroeconomic effects were evaluated based on 2021 actual data. The results of the evaluation were presented in the form of a presentation, as well as were included in the 2021 annual state budget report. | Evaluation and reflection of deviations of planned and actual fiscal policies and their macroeconomic effects in the 2021 annual state budget report. | The actions planned for 2021 are carried out | It is a periodic process | In the future, it is planned to carry out the works periodically, every year after the publication of the official indicators of the previous year, during the 1st half of the year. |  |  | IMF
Assessments of the effects of fiscal policy, deviations from the planned ones on the economy
| 3. Ensuring staff with relevant qualifications and skills | 3.1. Implementation of measures aimed at raising the qualification of the staff | MoF | - | 2019-2023 |  |  | Availability of staff with relevant qualification and skills | During 2020, no business trips were carried out due to the limitations caused by the limitations caused by the coronavirus. In January, only one employee of the Macroeconomic Policy Department was trained within the framework of the trainings organized by IMF in Vienna (JVI). However, employees participated in other available online courses, including regular webinars initiated by JVI. Employees were encouraged through the remuneration fund provided to the department, as well as other promotional methods were applied. | Conditioned by the cancellation of the IMF training due to the epidemic and the changes in the training format, six employees of the Macroeconomic Policy Department (Department) was trained in the JVI organized online courses during 2021. Employees also participated in other available online courses, as well as regular webinars initiated by JVI. in the framework of bilateral cooperation between the Financial Research Institute of the Ministry of Finance of the Russian Federation 6 employees of the Department participated in the regular weekly trainings and discussions. 11 employees of the Department took part in the trainings organized by the OGResearch Research Center on the initiative of the Financial Research Institute of the RF Ministry of Finance | During 2022, 3 employees of the Macroeconomic Policy Department participated in the courses organized by the Joint Vienna Institute (JVI) and the International Monetary Fund in Vienna, and 2 employees were trained remotely (online). Employees also participated in other available online courses as well as regular webinars initiated by JVI. During 2022, in the framework of bilateral cooperation between the Financial Research Institute of the Ministry of Finance of the Russian Federation and the RA Ministry of Finance trainings and discussions were held regularly, including 3 employees of the department were sent to Moscow to participate in discussions on tax revenue and macroeconomic forecasting system. An exchange of experience was held at the Ministry of Finance of the Czech Republic, in which 1 employee of the Department of Macroeconomic Policy participated. | Trainings aimed at developing the professional capabilities of the personnel dealing with macroeconomic forecasts | Activities envisaged for 2020 and 2021 are carried out | It is a periodic process | In case of the resumption of courses by international organizations, the employees of the department will also be trained in the business trips format. In the future, it is regularly planned to carry out activities aimed at increasing the professional abilities and qualifications of personnel. During the first half of 2022, in the framework of bilateral cooperation between the Financial Research Institute of the Ministry of Finance of the Russian Federation and the RA Ministry of Finance regular courses and discussions are planned to be held in the second semester of 2022 as well. |  |  | IMF/RF MOF
| 4. Improving the function of fiscal risk assessment | 4․1 Expanding the coverage of fiscal risk assessment, improving the methodology | MoF | - | 2020-2023 |  |  | Fiscal risk assessments include an expanded range of fiscal risk sources | Fiscal risk assessments related to the activities of 20 organizations operating in the infrastructure (energy, transport, water economy) sectors were carried out, which also included the analysis of contingent liabilities arising from the contracts of public-private partnership companies. The latter were reflected in the document RA 2021-2023 MTEF (link: http://www.minfin.am/en/page/petakan_mijnazhamket_tsakhseri_tsragre/). At the same time, the work on expanding the scope of assessment of fiscal risk sources continues. | Fiscal risk assessment activities related to the activities of organizations operating in infrastructure (energy, transport, water economy) and other sectors, including the analysis of contingent liabilities arising from public-private partnership format, as well as contracts with the right to purchase electricity; which were reflected in the document of RA MTEF 2022-2024. and the state budget for 2022. | Fiscal risk assessment works related to the activities of organizations operating in infrastructure (energy, transport and water management) and other sectors, where the analysis of the contingent liabilities arising from the contracts of the organizations operating in the format of public-private partnership, as well as the right to purchase electricity, the study of budget lending, the distribution of loans by sectors, the fiscal risks arising from natural and man-made disasters were also included which were reflected in the RA MTEF 2023-2025 and 2023 State Budget. | Inclusion in the 2022 and 2023 budget documents of the assessment of the fiscal risk of infrastructure sector organizations and the analysis of contingent liabilities arising from the contracts of organizations operating in the PPP format. It is envisaged to adopt also a government decision that will set requirements for companies with strategic state participation, such as “Armenian National Interests Fund” CJSC. Based on the recommendations submitted, it is planned to prepare a concept for the monitoring, approval and control framework concept related to local self-government bodies and local self-government bodies’ debt. |  | In Progress | In the framework of the theme "Improving the accountability of state joint-stock companies", the International Monetary Fund plans to provide technical assistance for the purpose of issuing debt instruments by the local government. |  |  | ADB/IMF
[8 empty] | Improved fiscal risk methodology | The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in terms of public-private partnership projects was approved by RA Government decision N1785-Լ , dated 06․11․2020. With the support of ADB consultants the RA Minister of Finance draft Order "On Approving Methodological Guide for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" | The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in terms of public-private partnership projects was approved by RA Government decision N1785-Լ , dated 06․11․2020 for the implementation of the functions assigned to the RA Ministry of Finance per the RA Law "On Public-Private Partnership". At the same time Decision on setting the maximum permissible limit of public-private partnership obligations of the Republic of Armenia (in terms of contingent liabilities) was approved by the RA Governmnet Decision N955-Լ, dated 10․06․2021. With the support of ADB consultants the RA Minister of Finance draft Order "On Approving Methodological Guideline for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" A brief overview of the assessment of the relevant range of specific fiscal risks was provided. The draft decision of the RA Government defining the maximum limit of direct liabilities of PPPs is being developed. | The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in relation to the Public-Private Partnership projects was approved by the RA Government Decision N1785-Լ, dated 06․11․2020 for the implementation of the functions assigned to the RA Ministry of Finance by the RA Law "On Public-Private Partnership". At the same time, by the RA Government Decision N955-Լ, dated 10․06․2021 the Decision “On setting the maximum permissible limit of the liabilities of the public-private partnership of the Republic of Armenia (in terms of contingent liabilities) was approved. With the support of ADB consultants, the RA Minister of Finance Order N 388-Լ "On Approving Methodological Guideline for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects". On April 28, 2022, the RA Government Decision N 585-Ն defining the permissible limit of contingent and direct liabilities of PPPs was adopted. The draft of the RA government's decision defining the maximum limit of direct liabilities of PPPs is in the elaboration phase. | • Approval of the methodology for calculating and evaluating the RA contingent liabilities in terms of PPP projects (RA Government Decision N1785-Լ, dated 06․11․2020) • Setting the maximum permissible limit of PPP liabilities (RA Governmnet Decision N955-Լ, dated 10․06․2021). • RA Minister of Finance draft Order "On Approving Methodological Guideline for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects". |  | In Progress
| 5. Development of analytical skills of fiscal risk assessment specialists | 5․1 Capacity building | MoF | - |  |  |  | Specialists with improved analytical skills in assessing fiscal risks | During the second half of the year, 2020, one employee of the department was trained within the framework of the trainings organized in Vienna (JVI). In addition, the relevant specialists of the department (3 specialists) participated in the PFRAM2.0 training course on fiscal risk assessment of PPPs organized by the IMF (developed by the WB և IMF) ։ The employees also took part in the trainings organized by the World Bank in Yerevan. In addition, training is provided as part of ADB's consulting work. | During 2021 in the scope of online JVI organized courses 2 employees of the Department were traimed, Besides employees of the Deparment participated in "Financial Analysis" and "Financial Modeling" courses organized by the International Academy of Business, as well as in the course on public-private partnership in the scope of the Commercial Law Development Program under the US Department of Commerce. | Five employees of the department were trained within the online courses organized in Vienna (JVI) in 2022-2023. In addition, department employees participated in the "Building Sustainable Generational Economies": 14th Global Conference of the NTA Network" organized by the National Transfer Accounts (NTA), the study visit "Expanding Green Finance Practices in the Republic of Armenia" by the KfW and the Netherlands Enterprise Development Bank (FMO), as well as the "Climate Responsive Fiscal Planning" course by the Asian Development Bank. The "Financial Analysis" and "Financial Modeling" courses organized by the International Academy of Business, as well as the course dedicated to the public-private partnership planned in the framework of the "Commercial Law Development Program" under the US Department of Commerce | Trainings aimed at professional capacity building of the staff dealing with fiscal risk forecasting |  | In Progress | In order to improve the professional abilities and qualifications of personnel, the trainings are continuous. |  |  | ADB/IMF
2․ STATE REVENUE POLICY, TAX ADMINISTRATION
| 6. Assessing the needs of the tax environment based on the economic development priorities and opportunities | 6․1 Outline directions for further tax system reforms based on economic development priorities and opportunities | MoE | MoHTI, MoE, MoTAI | May, 2020 |  |  | The directions of further reforms of the tax system are outlined | At present, clarifications are being carried out on the Armenian economic policy, based on which the proposals on further directions of tax reforms will be derived. | As a result of the measure, the RA Ministry of Economy studied the directions of further reforms of the tax system based on the priorities and opportunities of economic development and the directions of the tax system reforms were reflected in the concept of the RA economic policy elaborated by the RA Ministry of Economy, which currently has the status of the RA Government draft decision. |  | Outlining the directions of further reforms of the tax system in the concept of RA economic policy | First half of 2021 | Completed |  |  |  | RF MOF
| 7. Reducing the scope of application of tax benefits | 7.1 Elaboration of the RA draft law "On Making Amendments to the RA Tax Code" | MoF | - | 2020-2023 |  |  | Low-efficiency, non-targeted tax benefits are eliminated |  | ADB has submitted the final Report on the reduction of the scope of tax benefits, which presents recommendations, analysis, studies and relevant calculations aimed at reducing low-efficiency, non-targeted tax benefits ADB has introduced a tool for analyzing the impact of tax expenditures, which is under study է: The reference on "Structure of tax expenditures - sectoral value added" has been elaborated, international experience has been studied. | Work in this direction is ongoing. In particular, for ensuring the implementation of the measure, the tax revenue management program for the years 2022-2025 was elaborated by the RA Ministry of Finance and approved by the Clause 1 of the RA Prime Minister's Decree N 919-Լ, dated August 12, 2022, and the revisions of the tax policy for the coming years will be carried out in accordance with the directions of the mentioned program. In this regard, please be informed that the main provisions of the tax policy to be implemented in the direction of the reduction of tax privileges were presented by the mentioned decision. At the same time, an agreement was reached with the International Monetary Fund to provide technical assistance during 2023 in order to implement the measure to reduce low-efficiency and non-targeted tax privileges based on the recommendations presented by the results the possibilities and expediency of making relevant revisions in the tax legislation will be discussed. In addition, we inform you that in order to explore the possibilities of reducing the existing scope of tax expenditure and increasing the tax potential at its expense, the measure "On elaboration of a program aimed at increasing the efficiency of tax expenditures" has been defined by the RA Government Decision N2117-Լ, dated December 22, 2022 (for the RA Ministry of Finance). In the framework of the mentioned measure, until the 3rd ten days of June 2023, it is planned to carry out studies aimed at increasing the efficiency of tax expenditures, submit a report on the results of the studies, then discuss the report at the Prime Minister's office and, if necessary, elaborate and submit a draft of the relevant legal act for consideration by the RA government. | • Elaboration of a package of recommendations aimed at reducing low-efficiency and non-targeted tax priviliges. • Designing a toolkit for the analysis of the impact of tax expenditures. |  | In progress | 1. Provision of technical assistance by the International Monetary Fund, as well as elaboration of a program aimed at increasing the efficiency of tax expenditures. 2. Ցածր արդյունավետություն ունեցող և (կամ) հասցեականություն չունեցող ոլորտային հարկային արտոնությունների վերացման ուղղությամբ, ըստ անհրաժեշտության, հարկային օրենսդրության մեջ կատարվելիք փոփոխությունների վերաբերյալ առաջարկությունների մշակում: 3. Ներկայացված առաջարկությունների քննարկում շահագրգիռ պետական կառավարման մարմինների և մասնագիտական հասարակական կազմակերպությունների հետ: 4. Քննարկումների արդյունքների հիման վրա ՀՀ հարկային օրենսգրքում համապատասխան փոփոխություններ և լրացումներ նախատեսող օրենքի նախագծի մշակում և ՀՀ կառավարության քննարկմանը ներկայացում: |  |  | ADB
| 8․ Review of turnover tax burden | 8․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | 2020-2023 |  |  | As a result of the conducted studies, the turnover tax burden has been revised | The measure is implemented with the technical assistance of ADB, for which relevant international experts were involved, with whom a number of working meetings were held. At the same time, the measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. According to the measures 2 and 3 of the appendix approved by point 1 of that decision, by the third ten days of May 2021, the RA Ministry of Finance must develop draft laws envisaging increase of the turnover tax rates, decrease of the turnover tax threshold. | The first stage of receiving technical assistance for the implementation of the activiteis on the review of the turnover tax burden with ADB is completed Within the framework of ADB technical assistance, a preliminary and final report was submitted, which presented recommendations, analysis, studies and relevant calculations on turnover tax burden References on "Information on the number of economic entities operating in different taxation systems" and "Comparison of the tax burden on the general taxation system and turnover tax system" have been elaborated | Work in this direction is ongoing. In particular, for ensuring the implementation of the measure, the tax revenue management program for the years 2022-2025 was elaborated by the RA Ministry of Finance and approved by the Clause 1 of the RA Prime Minister's Decree N 919-Լ, dated August 12, 2022, and the revisions of the tax policy for the coming years will be carried out in accordance with the directions of the mentioned program. In this regard, please be informed that the main directions of the tax policy to be implemented in the direction of the transformation of different taxation systems were presented by the mentioned decision. | Approval of measures aimed at reducing the tax policy gap Decision N 1455-L, dated December 30, 2020). |  | In progress | 1. Elaboration of recommendations on the changes to be made in the tax legislation in the direction of revising the tax burden on turnover tax. 2. Discussion of the presented recommendations with the interested state government bodies and professional-social organizations. 3. Based on the results of discussions, elaboration of a draft law providing for relevant amendments and supplements to the RA Tax Code and submission to the RA Government for consideration. |  |  | ADB
| 9․ Settlement of issues related to the documentation of transactions for the sale of agricultural products | 9․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2021 |  |  | Issues related to documenting transactions are settled | Measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to the 6th measure of the appendix approved by point 1 of the same decision, by 3rd ten days of May, 2021 the RA Ministry of Finance should develop a draft law on the regulation of issues related to the documentation of transactions for the sale of agricultural products and submit to the RA Government for consideration. | Activities are underway to resolve issues related to the documentation of transactions for the sale of agricultural products. Analytical work and study of international experience were carried out in the direction of the measure implementation. In the framework of the mentioned measure, 3 working discussions were held with the RA Ministry of Economy, during which the possibilities of documenting different types of both crop and animal products were discussed.: Representatives of the RA State Revenue Committee were also involved in the mentioned discussions. | Work in this direction is ongoing. For agricultural sector development, in the framework of tax regulations review, a draft law providing for additions to the RA Tax Code was elaborated by the RA Ministry of Economy. The RA Ministry of Finance considered the adoption of the project inappropriate, including taking into account the results of discussions with IMF specialists. On the other hand, please also be informed that during the discussions with IMF experts, the latter also agree that as a result of the current rules of taxation with VAT, non-competitive taxation arrangements may arise for various chains of sale of agricultural products. However, IMF specialists consider it appropriate to implement the settlement of the mentioned problems through targeted budget support programs, which the RA Ministry of Finance agrees with, and in this regard, we have suggested that the RA Ministry of Economy jointly discuss with the RA Ministry of Finance the options for solving the existing problems through budget support programs. The above mentioned draft was discussed on November 29, 2022 at the sitting of the financial and economic ministerial standing committee. As a result, the project was withdrawn from the agenda. Taking into account the referred, please be informed that the directions for revising the tax regulations for the development of the agricultural sector are still being discussed and at the moment a decision has been made to solve the problems within the framework of the non-tax budget support toolkit. |  |  | In progress | 1. Conducting further discussions. 2. Elaboration of proposals for revising tax regulations that hinder the development of the agricultural sector. 3. Discussion of the presented recommendations with the interested state government bodies and professional-social organizations. 4. Based on the results of discussions, elaboration of a draft law providing for relevant amendments and supplements to the RA Tax Code and submission to the RA Government for consideration.
| 10. Equivalent tax on visible wealth or property | 10․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2020 |  |  | Visible wealth or property is taxed adequately | On June 25, 2020, the RA National Assembly adopted the RA Law "On Making Amendments to the Tax Code of the Republic of Armenia" aimed at reviewing the real estate tax system. |  |  | • Revision of the real estate tax system - Adoption of the RA Law "On Amendments and Additions to the RA Tax Code" (June 25, 2020) | 2020 | Completed
| 11․ Providing legal bases for the introduction of the income declaration system based on the current economic motives | 11․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2021 |  | 3rd decade of June 2022 | Legal bases for the introduction of the income declaration system based on the current economic motives is ensured | The action plan necessary for the introduction of the individual income declaration system was approved by the order No. 104-L of the RA Minister of Finance, dated April 6, 2020. b. Studies of the international experience of the system of income declaration of individuals were carried out and the results were submitted for discussion, c. The RA draft law “On Making Amendments and Addenda to the RA Tax Code” aimed at the introduction of the system of income declaration of individuals has been elaborated. At the same time, please be informed that measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to the 5th measure of the appendix approved by point 1 of the decision, by the 3rd ten days of September, 2021, the draft law envisaging introduction of the income declaration system based on the current economic motives shoud be elaborated and submitted to the RA Governemnt for consideration. | The study of international analytical experience was carried out in the direction of the implementation of the measure. The work done was discussed with the RA Prime Minister on January 11, 2022. | The mentioned event has already been implemented. In particular, on December 23, 2022, the RA National Assembly adopted the RA Law "On Making Amendments and Supplements to the Tax Code of the Republic of Armenia" aimed at introducing the system of income declaration, operating on the basis of economic motives. | • Approval of the action plan for the introduction of the income declaration system for natural persons (of the RA MoF Order N 104-L, dated 06.04.2020). • RA law on amendments and additions to the RA Tax Code aimed at introducing the income declaration system for natural persons. |  | Completed
4. Revenue Transparency and Compliance | 12. Tax potential and gap assessment | 12.1. Assessment of tax potential and gap for the three major types of taxes (VAT, profit tax, income tax) | MoF | - | 2019-2023 |  |  | Existence of tax potential and gap assessment methodology for three major types of taxes (VAT, profit tax, income tax); Tax potential and gap estimates for the three major types of taxes (VAT, profit tax, income tax) | In the framework of tax potential gap assessment, the RA Ministry of Finance, in cooperation with the RA State Revenue Committee and the RA Central Bank, assessed the tax potential of the Republic of Armenia, the results of which were discussed with the RA Deputy Prime Minister in December 2019. Based on this, agreements were reached and the RA State Revenue Committee was instructed to conduct a study and present its assessments on the tax potential. In this regard, the RA State Revenue Committee in 2020 carried out works on assessing the tax potential on VAT and tax gap, and submitted the results to the Office of the RA Deputy Prime Minister. In order to prove the implementation of the structural benchmark approved in the framework of the program with the IMF, a brief reference on the tax gap assessments and completed activities package of the RA Ministry of Finance and SRC was submitted to the IMF. which were the basis for considering the status of structural benchmarking to be "pending" in the IMF's third review report under the program signed with the IMF and published in December, 2020 . A more comprehensive reference is currently being drawn up on the activities done to assess the tax potential and gap which needs to be submitted to the IMF in order to consider the above structural benchmarl "completed" in future IMF reports. | During 2021 for the purpose of updating tax potential and gap assessment the RA SRC was requested information which was received. The received data have been elaborated and finalized, 2019 and 2020 tax potential and gap assessment has been implemented | 12.1. Assessment of tax potential and gap for three major types of taxes (VAT, profit tax, income tax) • Availability of tax potential and gaps assessment methodology for three major types of taxes (VAT, profit tax, income tax). • Assessment of the tax potential and gap in three major types of taxes (VAT, profit tax, income tax) RA MoF Macroeconomic Policy Department 2019-2023. During 2022 for updating the assessment of the tax potential and gap, the necessary information was requested and received from the RA SRC. The data were processed and summarized, an assessment of the tax potential and gap for 2020 and 2021 was carried out, the results of which were discussed in interagency meetings (with the participation of representatives of the Central Bank, the State Revenue Committee, the Ministry of Economy). During 2023, it is planned to develop a unified methodology for assessing the tax potential and gap for major types of taxes (VAT, income tax, profit tax), which will be acceptable to all interested agencies, and based on this methodology, assess the tax potential and gap. End of June, 2023 | Tax potential and gap assessment in 2019, 2020and 2021 | Activities for 2020 and 2021 are carried out | It is a periodic process | During 2023, it is planned to develop a unified methodology for assessing the tax potential and gap for major types of taxes (VAT, income tax, profit tax), which will be acceptable to all interested agencies, and based on this methodology, assess the tax potential and gap |  |  | IMF
| 13․ Publication of information on tax refunds from the budget to ensure transparency of public finances | 13․1 Publication of data on tax refunds from the state budget on a quarterly basis | SRC | - | 2019-2023 |  |  | Relevant information published | In accordance with the RA SRC Chairman order N 267-A, dated 17.04.2019, the relevant information is published on a monthly basis in the RA SRC official website (http://www.petekamutner.am) in the section "Tax Information", sub-section "Tax Statistics" , part "Tax Statistics data" | Pursuant to the RA SRC Chairman Order №267-A, dated 17.04.2019, the relevant information is published monthly in the part “Tax Statistical Data”, sub-section “Tax Statistics”, section “Tax Information” of the RA SRC official website (http://www.petekamutner.am). | Pursuant to the RA SRC Chairman Order №267-A, dated 17.04.2019, the relevant information is published monthly in the part “Tax Statistical Data”, sub-section “Tax Statistics”, section “Tax Information” of the RA SRC official website (http://www.petekamutner.am). | The relevant information was published on the official website of the RA SRC | Activities for 2020 and 2021 are carried out | It is a periodic process | Publication of relevant information on a monthly basis.
| 14․ Continuous reduction of the shadow economy, exclusion of privileged taxpayers | 14․1 Expand opportunities for access to third party information and for effective use | SRC | - | 2019-2023 |  |  | Reducing the tax shadow Exclusion of taxpayers with privileged status and creating an equal tax environment for all taxpayers | 1. In order to ensure access to information to the tax authority from third parties on real estate, their owners, property rights, restrictions, limitations and their changes the RA Government draft decision "On making changes and additions to the RA Government decision N 388-N, dated April 6, 2017 " has been elaborated and sirculated since December, 2019. Taking into account the RA MoF standpoint on the draft that these changes should be initiated by drafting the decision of the RA Government Decision "On Making Amendments to the Decision No. 1337-N, dated October 5, 2017", the elaboration of which was initiated in January 2020, however, given that the RA Cadastre Committee developed the draft decision of the RA Government “On making changes in the RA Government Decision No. 388-N, dated April 6, 2017” and put into circulation in February 2020, thus 1337-N draft will be put into circulation once the draft 388-N regulations come into force 2 Within the framework of the draft joint decision of the RA Central Bank and the MoF On approving "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. 3. During the electronic opening of transit declarations for import transactions within the EEU, mistakes are made by the customs authorities of other EEU member states when filling in the transit declarations and in the future, during the closing of declarations in the Republic of Armenia, the information is entered into the "Taxpayer 3" electronic management system with corresponding shortcomings which creates significant inconveniences in the process of comparing and analyzing the information available in the e-management system Given the importance of the issues raised, it was proposed to enable the electronic tax authority to enter accurate data on the import of goods from the EEU countries, in particular, by manually verifying the data in the "Taxpayer 3" e-government system. | 1. The Ra Government draft Decision "On Making Amendments and Supplements to the RA Governmnet Decision N1337-N, dated October 5, 2017" was elaborated by the RA SRC and adopted by the RA Government Decision 159-N, dated 11.02.2021, as a result of which the tax authority will be provided with access to information on real estate owners, cadastral assessment. 2. In the framework of the draft joint decision of the RA Central Bank and the MoF "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. The order was established by the joint decision of the RA Minister of Finance No. 2-N, dated June 16, 2021 and No. 39-N, dated March 30, 2021 according to paragraph 58 of which, financial institutions shall submit information on assets transferred during the year of a legal entity or sole proprietor to the tax authority by February 20 of the following year. 3. In accordance with the Clause 122, Annex 1 of the RA Government Decision 596-Ն, dated 19.03.2015, copies of issued construction or demolition permits shall be submitted to the tax authority by the competent bodies issuing construction permits in the Republic of Armenia (including the Municipality of Yerevan). There are problems with the format and content of the information presented in this process. In order to regulate the receipt of information, the draft decision on making changes to RA Government Decision No. 596-N, dated 19.03.2015 was elaborated ent to the relevant interested bodies of the RA state administration for an opinion by the letter No. 01 / 3-4 / 80262-2021 dated 14.12.2021 . 4․A request was sent to 32 government agencies to assess the scope for expanding information received from third parties and to identify opportunities for further cooperation. Based on the responses received from the authorized bodies, the following directions were outlined for the expansion of the information received from third parties and relevant letters were sent to develop the legal basis for the exchange. a) Information on the owners of vehicles (including legal entities) reflected in the electronic information database of the "Traffic Police" service of the RA Police, as well as the persons operating them (including the addressees of the administrative act) b) Information available in the unified e-government system of civil acts registration in the RA Ministry of Justice c) Fees, dividends and other similar information of citizens submitting declarations in the register of the RA Commission for the Prevention of Corruption d) Information on final acts of public objects approved within the sphere of urban development existing in the RA Urban Development, Technical and Fire Safety Inspection Body, in the field of transport control for taxis of 5-7-seater vehicles, as well as the number of design documents of the objects submitted to the inspection body for the purpose of disclosure. e) RA State Cadastre Committee to get the complete history of real estate transactions: 5. By the letter N01//188-2021, dated 13.04.2021 the Commission for Prevention of Corruption informed on that they can not provide complete data yet, as the database does not provide such an opportunity yet. Work is underway to create a new system. 6․In June, 2021 the tax authority prepared an application for basic interconnection of data belonging to state or local self-government bodies and transfer of personal data for the purpose of using the web services of the Civil Status Acts Registration Agency of the RA Ministry of Justice, the RA Cadastre Committee, and the RA Police. On 25.06.2021, the application was sent to "EKENG" CJSC to ensure the further process. Database interconnection and personal data transfer integration technical manuals of Police, Civil Status Acts Registration Agency and Cadastre were sent to RA SRC by "EKENG" CJSC by email on July 2, 2021. After receiving the answers to the inquiry mentioned in the 5th column of this appendix, measures will be taken to obtain the existing information useful for the tax control process in the databases of the mentioned bodies. 2024 | 14.1 14.1 Expanding opportunities for receiving and effective use of information from third parties • Reducing the tax shadow • Exclusion of taxpayers with privileged status and creation of an equal tax environment for all taxpayers. 1. By the RA SRC Chairman letter N01/3-4/76184-2020, dated 04.12.2020, the Ra Government draft Decision "On Making Amendments and Supplements to the RA Government Decision N1337-Ն, dated October 5, 2017" was drawn up and adopted by the RA Government Decision 159-Ն, dated 11.02.2021, as a result of which the tax authority will be provided with access to information on real estate owners, cadastral assessment. 2. In the framework of the joint draft decision of the RA Central Bank and the MoF "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as on the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month including, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. The order was established by the joint decision of the RA Minister of Finance N 2-Ն, dated June 16, 2021 and of the Board of the RA Central Bank N 39-Ն, dated March 30, 2021 according to paragraph 58 of which, financial institutions shall submit information on assets pardoned during the year of a legal entity or sole proprietor to the tax authority by February 20 of the following year. 3. In accordance with the Clause 122, Annex 1 of the RA Government Decision 596-Ն, dated 19.03.2015, copies of issued construction or demolition permits shall be submitted to the tax authority by the competent bodies issuing construction permits in the Republic of Armenia (including the Municipality of Yerevan). There are problems with the format and content of the information presented in this process. In order to regulate the receipt of information, the draft decision on making changes to RA Government Decision N 596-Ն, dated 19.03.2015 was elaborated and submitted to the relevant interested bodies of the RA state administration for an opinion by the letter N 01/3-4/80262-2021, dated 14.12.2021 . The opinions received from the relevant interested bodies of the RA state administration were summarized and sent to the RA Ministry of Justice for state-legal examination on 24.05.2022 by the letter N 01/3-4/36029-2022, which will be submitted to the RA Government for consideration after receiving it. 4. In order to assess the scope of expansion of information received from third parties and to identify opportunities for further cooperation, a survey was prepared for 32 state administration bodies by the RA SRC letter N 01/4-3/69065-2020, dated 29.10.2020. Based on the responses received from the authorized bodies, the following directions were outlined for the expansion of the information received from third parties and relevant letters were sent to develop the legal basis for the exchange. a) Information on the owners of vehicles (including legal entities) reflected in the electronic information database of the "Traffic Police" service of the RA Police, as well as the persons operating them (including the addressees of the administrative act) b) Information available in the unified e-government system of civil acts registration in the RA Ministry of Justice c) Fees, dividends and other similar information of citizens submitting declarations in the register of the RA Commission for the Prevention of Corruption d) Information on final acts of public objects approved within the sphere of urban development existing in the RA Urban Development, Technical and Fire Safety Inspection Body, in the field of transport control for taxis of 5-7-seater vehicles, as well as the number of design documents and other similar information of the objects submitted to the inspection body for the purpose of disclosure. e) RA State Cadastre Committee to get the complete history of real estate transactions. 5. By the letter N01//188-2021, dated 13.04.2021 the Commission for Prevention of Corruption informed that they couldn’t provide complete data yet, as the database does not provide such an opportunity yet. Work is underway to create a new system. 6. In June, 2021 the tax authority prepared an application for basic interconnection of data belonging to state or local self-government bodies and transfer of personal data for the purpose of using the web services of the Civil Status Acts Registration Agency of the RA Ministry of Justice, the RA Cadastre Committee, and the RA Police. On 25.06.2021, by the letter N /6-1/39031-2021 the application was sent to "EKENG" CJSC to ensure the further process. Database interconnection and personal data transfer integration technical manuals of Police, Civil Status Acts Registration Agency and Cadastre were sent to RA SRC by "EKENG" CJSC by email on July 2, 2021.: 7. Work is being carried out on the integration of relevant information from state databases, as well as further introduction of the system in the POWER BI reporting-analytical system or within the additional services (10% of the value of the services under the contract) of the contract already concluded for the services of the "Taxpayer 3" electronic management system, in particular a) traffic police web service data acquisition is in the programming phase, b) The receiving of data from the web service of the RA Cadastre Committee is also in the planning phase, the work of which will be completed in at least 6 months., c) Integration of the relevant information (10% of the value of the services stipulated in the contract) from the Civil Status Acts Registration Agency register of the RA Ministry of Justice is in progress. As a result of the working discussion, it was decided that the general analysis of these data in the Power BI system will be possible after the completion of the programming work. 8. On 04.08.2022 a working discussion was held between the employees of the RA SRC, the RA Police, "EKENG" CJSC, the organization servicing the Civil Status Acts Registration Agency system and the representative of the organization servicing the road policy system. Taking into account the large amount of data needed for analysis, in order to avoid overloading the systems, several options for data transfer were discussed and it was decided to transfer the databases to the SRC once through hard drive, and then to provide the changes in the databases at certain intervals through the Government Interoperability Platform using the web service. It has been agreed that. 1) The RA SRC will provide the "EKENG" CJSC with the necessary data structure, composition and desired methods of inquiry for each database to be inquiried, 2) On the basis of the provided information, a web service for providing changes registered in the Civil Status Acts Registration Agency database will be elaborated, and if necessary, a new web service for the Road Police will be developed, 3) databases with the required structures will be provided to RA SRC through hard drive by the Road Police and the Civil Status Acts Registration Agency, 4) "EKENG" CJSC will ensure the transfer of information on changes in databases through the Government's interoperability platform: The 4 processes listed above are currently underway. Along with completing the process of obtaining information in the directions indicated in point 4 of the 5th column of this appendix, work will be done to obtain the information available in the database of other state bodies and to be used in the tax control process. 2024 | During 2022 measures were taken in the direction of obtaining the information to be used in the tax control process from the state administration bodies, as well as their automation. 2 Work is being carried out on the integration of relevant information from state databases, as well as further introduction of the system in the POWER BI reporting-analytical system or within the additional services (10% of the value of the services under the contract) of the contract already concluded for the services of the "Taxpayer 3" electronic management system, in particular a) traffic police web service data acquisition is in the programming phase, b) The receiving of data from the web service of the RA Cadastre Committee is also in the planning phase, the work of which will be completed in at least 6 months., c) Integration of the relevant information (10% of the value of the services stipulated in the contract) from the Civil Status Acts Registration Agency register of the RA Ministry of Justice is in progress. As a result of the working discussion, it was decided that the general analysis of these data in the Power BI system will be possible after the completion of the programming work. 4. On 04.08.2022 a working discussion was held between the employees of the RA SRC, the RA Police, "EKENG" CJSC, the organization servicing the Civil Status Acts Registration Agency system and the representative of the organization servicing the road policy system. Taking into account the large amount of data needed for analysis, in order to avoid overloading the systems, several options for data transfer were discussed and it was decided to transfer the databases to the SRC once through hard drive, and then to provide the changes in the databases at certain intervals through the Government Interoperability Platform using the web service. It has been agreed that. 1) The RA SRC will provide the "EKENG" CJSC with the necessary data structure, composition and desired methods of inquiry for each database to be inquiried, 2) On the basis of the provided information, a web service for providing changes registered in the Civil Status Acts Registration Agency database will be elaborated, and if necessary, a new web service for the Road Police will be developed, 3) databases with the required structures will be provided to RA SRC through hard drive by the Road Police and the Civil Status Acts Registration Agency, 4) "EKENG" CJSC will ensure the transfer of information on changes in databases through the Government's interoperability platform: The 4 processes listed above are currently underway. |  | In progress | Along with completing the process of obtaining information in the directions indicated in point 4 of the 5th column of this appendix, work will be done to obtain the information available in the database of other state bodies and to be used in the tax control process.
| 15․ Ensuring timely declaration and fulfillment of tax liabilities by taxpayers in full | 15․1 Modernization and capacity building of tax authority analytical and control tools | SRC | - | 2019-2023 |  |  | The staff of the tax authority has the necessary capacity to enforce tax legislation There is a revised and constantly improving tax control toolkit | 1.The Order 260-A was approved by the RA SRC Chairman on 23.03.2020 , which provides for the development and automation of risk-taking analytical tools. Built-in "Big Data" analytical processing system (Big Data Analytics - Power BI)is installed, which allows analytical work, creating reports with different criteria. At present, a total of 24 reporting items are included in the analytical system of large databases, including 4 on foreign economic activity. New approaches have been used in the risk management system based on large-scale data analysis to more effectively target risks. 2. The automated system for conducting cameralistic studies has been introduced and tested in the e-government system of the tax authority. During the testing, the problems that hindered the operation of the system were identified, and work is underway to solve them. 3. The current procedure of tax risk assessment carried out during tax administration has been studied in detail and the risk assessment and realization procedure, including the toolkit has been completely revised by the Order No. 195-A, dated February 28, 2020. 4. The current procedure of the automatic monitoring system used during the tax administration has been studied in detail in 2020. The procedure for implementing and monitoring risk assessment was completely revised by the Order No. 300-A, dated April 6, 2020, while partially changing the risk assessment toolkit. At the same time, the criteria for assessing risk based on monitoring results, supplementing the system with new criteria characterizing the real risk of taxpayers was revised by the decision No. 1151-A of the RA SRC Chairman dated 08.12.2020 5.The description of the planning process of complex tax inspections based on risk criteria was studied in 2020 and the new procedure was approved by the order No. 460-A of the head of tax authority, dated May 25, 2020, according to which the priority of inclusion in the annual program of inspections was given to the taxpayers who declared the highest sales turnover, as well as to the taxpayers in the high risk zone. 6. A new automated system of inspections has been launched in the information system of the tax authority since March, 2020 as a result of which it has been possible to selectively include inspectors in complex tax inspections automatically. 7. Regulation on the organization, conduct and realization of tax audits and studies,which, in addition to a number of procedural regulations was reaffirmed by the Order 80-A of the head of tax authority, dated January 30, 2020 which has been adapted to the new structure of the tax authority. 8. The cooperation of the units carrying out tax administration and units carrying out legal, investigative proceedings of the tax body has been regulated by the SRC Chairman Order 419-A, dated May 20, 2020. | 1. By the Order №1151-Ա of the RA SRC Chairman dated 08.12.2020 on making changes to Order №300-Ա, dated 06.04.2020 the risk criteria existing in the monitoring center, were supplemented and brought to 66. In May-June, 2021, a tender was announced for the acquisition of consulting services for the development and introduction of new risk assessment criteria in the above-mentioned automatic notification system. The procurement procedure is at the stage of signing the contract. 2 . By the RA SRC Chairman Order №260-A approved on 23.03.2020, Power BI reporting-analytical system has been launched under the SRC e-government system within which 9 analytical tools were elaborated in 2020, of which 5 have already been launched during 2021. Two new reporting forms have been programmed into the Big Data system. At present, a total of 42 reporting items are included in the analytical system of Big Data, including 6 on foreign economic activity. 3. Based on court practice, the approach to detecting the rules of operation of cash registers has been changed in the tax body since December, 2021, in particular, control purchase studies are already being carried out instead of cash register inspections. At the same time, due to the above, changes were made in the electronic system of organizing inspections of the tax body, as a result of which it is possible to publish instructions for control purchase studies based on a specific purpose. Corresponding changes were also made in the internal procedures defined by the RA SRC orders (80-A and 195-A). | 1. Over 2019 December - 2020 January, the current procedure of tax risk assessment during the tax administration was subjected to a detailed study and by the head of the tax authority Order N 195-Ա, dated February 28, 2020, the risk assessment and realization procedure was completely revised, including the toolkit. 2. In February-March 2020, the current procedure of automated (monitoring system) used during tax administration was studied in detail and the procedure of risk assessment and implementation in a monitoring manner was completely revised, by the decision of the head of the tax authority order N 300-Ա, dated April 6, 2020 at the same time, the risk assessment toolkit was partially changed. By the RA SRC Chairman Order N 1151-Ա, dated 08.12.2020, with the additions made to the order N 300-Ա, dated 06.04.2020, the risk criteria operating in the monitoring center were increased and brought to at least the threshold set by the measurable indicator of the strategy (66 criteria). In May-June 2021, a tender was announced for the acquisition of consulting services for the programming and introduction of new risk assessment criteria in the above automated notification system. The procurement procedure is at the stage of concluding the contract. During the 1st quarter of 2022, active work was carried out with the IT department and the contractor in order to introduce new software standards and fully startup of the existing standards in the monitoring system. As of 31.03.2022, 48 risk assessment criteria are fully implemented in the automated monitoring notification system, of which 8 are newly programmed. During the 2nd quarter of 2022, active work has been going on with the IT department and the contractor in order to introduce new software standards and fully startup of the existing standards in the monitoring system. As a result, as of 01.07.2022, 61 risk assessment criteria are fully implemented in the automatic monitoring notification system, of which 13 are newly programmed. As of December, 2022, 63 risk assessment criteria have been implemented in the automatic monitoring notification system 3. In April, 2020, a description of the planning process for complex tax audits based on risk criteria was studied and by the Order N 460-Ա, dated May 25, 2020 of the head of the tax authority, a new procedure was approved, according to which the priority for inclusion in the annual inspection program was given to taxpayers who declared the highest sales turnover, as well as high-risk taxpayers. 4. Since March, 2020, a new automated inspection system has been launched in the information system of the tax authority, as a result of which it has become possible to automatically implement the selectivity of the inclusion of inspectors in complex tax inspections. 5. By the order N 80-Ա, dated January, 2020 of the head of the tax authority, the regulations on the organization, conduct and implementation of tax inspections and studies were re-confirmed, by which, among a number of procedural regulations, they were adapted to the new structure of the tax authority. 6. By the order 419-Ա, dated May 20, 2020 of the head of the tax authority the cooperation between tax administration departments and tax authority legal, investigation departments was regulated and unified. 7. By the head of the tax authority Order 260-Ա, dated March 23, 2020, the Power BI reporting-analytical system was launched under the SRC electronic management system, within the framework of which 9 analytical tools were developed in 2020, of which 5 have already been launched during 2021. 8. Based on judicial practice, starting from December 2021, the tax authority has changed the approach to discovering the rules for the operation of control cash registers, in particular, instead of cash register inspections, control purchase studies are already being carried out. At the same time, conditioned by the aforementioned, changes were made in the electronic system for organizing inspections of the tax authority, as a result of which it was possible to publish instructions for control purchase studies based on a specific goal. Corresponding changes were also made in the internal procedures defined by the orders of the RA SRC Chairman (80-Ա and 195-Ա) 9. RA Laws N HO-55-N, No. HO-42-N, dated 04.03.2022 and HO-86-N, dated 23.03.2022 (hereinafter referred the Laws ) on making amendments and additions to the RA Tax Code (hereinafter the Code) expanded the range of control tools of the tax authority, in particular: - The Code was supplemented by Article 349.1, which defined the type of thematic study: - Clause 2, Part 3 of Article 335 of the Code reads with the new edition, which defines the type of verification of the accuracy of the calculation and collection of the state duty. - Part 2 of Article 335 of the Code has been supplemented with new content - point 3, with the type of transfer pricing verification. With the use of the mentioned control tool, the tax authority will more effectively organize the process of collecting additional liabilities arising from the risks that emerged during the analysis. Conditioned by the entry into force of the above Laws, changes and additions were made to the internal procedures, in particular, by the RA SRC Chairman order N568-Ա, changes and additions were made to the RA SRC Chairman order N80-Ա, dated 30.01.2020 Internal procedures for conducting transfer pricing audits are under development. In order to introduce and apply the three-level system of transfer pricing documentation, the RA SRC Chairman Order N 941-Լ, dated September 9, 2022 "On defining the content and submission procedure of the information required by the local document" and Order N 942-Լ "On the content and submission of the information required by the main document" and the Order N 939-Լ "On establishing the form and filling procedure of the report exchanged between countries", dated September 9, 2022 were adopted. 10. Since October 1, 2022 the RA Law ՀՕ-55-Ն, dated 04.03.2022 (hereinafter the Law) entered into force, as a result since October 1, 2022, documents related to inspections and studies, decisions of the tax and customs authorities' appeal commission, as well as cameral study protocols are sent to taxpayers through the personal office of the electronic reporting system of the tax authority, and till October 1, 2022, the above documents were provided to taxpayers and received from them by hand and by postal service At the same time, with the introduction of the electronic system, taxpayers also had the opportunity to submit their objections and the necessary documents during control measures electronically. Since October 1, 2022, as a result of legislative changes, a new type of "Thematic Study" was launched, through which the tax authority got the opportunity to carry out supervisory work and impose an obligation on taxpayers who did not respond to the results of the analysis or gave unsubstantiated reports. In the past, the types of tax audits and studies defined by the legislation did not provide sufficient efficiency for cases when individual transactions of taxpayers were considered risky based on the analyzes performed by the tax authority, but the taxpayers, being notified about it, did not submit reports or did not verify the reports already submitted. The problem became especially obvious when the amount of tax arising as a result of a possible violation did not exceed AMD 10 million, that is, in this case it was not possible to carry out criminal proceedings and provide money within it. | The RA Law ՀՕ-55-Ն, dated 04.03.2022, entered into force from October 1, 2022, and as a result, from October 1, 2022, documents related to inspections and studies, decisions of the appeals committee of tax and customs bodies, as well as cameral study protocols are sent to taxpayers through the electronic reporting system of the tax body - personal office, and before October 1, 2022, the above-mentioned documents were provided to taxpayers and received from them by hand and by postal service. As of December, 2022, 63 risk assessment criteria have been implemented in the automatic monitoring notification system. |  | In progress | Analytical tools constantly |  |  | IMF
3․ STRATEGIC PLANNING, DRAWING UP MEDIUM-TERM EXPENDITURE FRAMEWORK AND STATE BUDGET
| 16․ Objectives and results of all budget programs included in the 2023 state budget are in line with existing sectoral strategies and cover all existing strategies that have an impact on budget revenues and expenditures | 16․1․ Review / develop budget programs in line with existing strategic policy | MoF | SBs | 2020-2022 |  |  | Availability of conformity assessment | By RA Prime Minister By Recommendation No. 02 / 08.5 / 35060-2020, dated 21.07.2020, all SBs were asked to harmonize the financial assessments of the sector strategies with the MTEF. As of 13.08.2020, the measure is implemented in 18 out of 46 SB having submitted the report on PFMSR progress report and the presented budget programs correspond to the policy directions defined by the main strategies of the PA. Work is underway in 28 bodies to implement the measure: analysis of budget programs from the point of view of compliance with existing strategic documents is carried out. 2 There is a process of reviewing strategies / policy directions in connection with the reorganization and legislative changes in the SB. The responsible unit of the RA Ministry of Finance has developed a measure of self-assessments of the conformity of the sectoral policy of the public authority and the compliance of the budget programs, which has been filled in by the public authorities and submitted to the MoF. | Within the support of the UNDP, an inventory of the RA strategic documents is carried out, the policy frameworks defined by them (goals, results, targets, etc.) are mapped, and the compliance of the budget programs related to them is assessed. The work also includes assessments of compliance with strategic planning frameworks and related budget programs. |  | Inventory of strategic documents and mapping of policy frameworks defined by them /goals, results, targets, etc./ and assessment of compliance of budget programs related to them. |  | Completed | Following the completion of the inventory of strategic documents in the relevant areas and the mapping of the policy frameworks defined by them (goals, results, targets, etc.), public authorities will be required to review the content and structure of budget programs depending on the existing strategic documents in the field. |  |  | IMF(UNDP/RF MOF)
All the programs included in the 2023 state budget are in line with the existing strategies
The 2023 budget programs fully cover all existing strategies that have an impact on budget revenues and expenditures.
All programs included in the 2023 state budget (except for administrative programs) have program passports, which are submitted to the RA NA together with the 2023 ․ draft state budget
|  | 16․2 Identification and regulation of practical problems related to the current PB methodology and its application | MoF | - | 2020-2022 |  |  | Existence of a report on the study of the PB methodology, the existing gaps related to its application | The measure is implemented with the technical support of the IMF, within the framework of which IMF experts conducted a study of the gaps and problems of the PB methodology and its application. The preliminary results of the study, including the recommendations on measures to improve the application of the "B methodology" were submitted to the MoF: The MoF is currently studying the assessments presented by the experts, the approaches and the issues of their practical application. At the same time, it is envisaged that in parallel with this work, self-assessments will be carried out on the gaps and problems of the introduction of the PB methodology in the state bodies, and its application. Based on the results of the above-mentioned external assessments and self-assessments, a schedule of measures to improve the application of the PB methodology will be developed as necessary. | With the technical support of the IMF, a study of the gaps and problems of the PB methodology and its application were conducted and suggestions were made to improve the PB methodology . At the same time, self-assessments were carried out in state bodies , which are now being discussed. | Based on the results of self-assessments, as well as after the discussions on the proposals provided by the IMF, the elaboration of a list of measures to improve the application of the PB methodology has started, with an appropriate schedule. | Availability of a list and schedule of measures to improve the PB methodology and its application |  | Completed |  |  |  | GIZ(IMF/RF MOF)
Existence of list of measure and schedule of PB methodology and its application improvement
The measures to improve the PB methodology are implemented in accordance with the schedule of measures
|  | 16․3․ Measures aimed at developing human resources | MoF | - | 2020-2023 |  |  | Institutional Capacity Assessment Report on Existing Human Resources (s) in line with the PB embedded system requirements | The possibility of being provided with external technical assistance for the implementation of the institutional capacity assessment of the existing human resources and for the implementation of the elaboration of capacity building program in accordance with the requirements of the embedded PB, is currently being discussed with partner international organizations. It is envisaged that in parallel, internal assessments of the relevant capacities in the state bodies will be carried out. Based on the results of the above-mentioned external-internal evaluations, an appropriate capacity building program will be developed. | In the framework of the measure, self-assessments were carried out in the state bodies on the basis of the self-assessment format of deficiencies and gaps provided to the state bodies, including in terms of human resource capacity, which are being discussed. In the scope of the IMF technical assistance recommendations on specific capacity development issues were also made. At the same time, within the framework of the "Program of measures aimed at capacity building of human resources in the RA state bodies from the point of view of full implementation of program budgeting" defined by the RA Government Decision No. 1223-L dated 12.09.2019, continuous professional trainings in the field of CB are regularly carried out. | Due to the existence of an up-to-date capacity building program, the amendment, updating and inclusion of new topics was carried out in the "Program of measures aimed at the development of existing human resources capacities in RA state bodies from the point of view of the full introduction of program budgeting" defined by the RA government's decision N 1223-Լ, dated 12.09.2019. | About 350 specialists have undergone professional training In the framework of the "Program of measures aimed at capacity building of human resources in the RA state bodies from the point of view of full introduction of program budgeting" |  | In Progress | During 2023, continuous professional training will be carried out in accordance with the approved modern program. |  |  | GIZ(IMF/RF MOF)
Availability of an up-to-date capacity building program
Capacity building activities are implemented in accordance with the approved program
| 17․ As of the end of the 2023 budget year, there is a regular budget program evaluation process in all state bodies responsible for budget programs. | 17․1․ Development of budget program evaluation guidelines | MoF | - | December, 2022 |  |  | The concept of evaluating budget programs is available | Within the measure the activities for elaboration of the budget program monitoring and evaluation concept, methodology, as well as the system introduction measure schedule are being implemented with the technical assistance of GIZ. In the scope of the technical assistance, the draft budget program monitoring, evaluation concept has been elaborated and submitted to MoF which is currently being studied and discussed by the MoF. After clarifying the approaches to the concept, the relevant methodology and action plan will be developed by the experts. | In the scope of the technical assistance of GIZ, the draft budget program evaluation concept has been elaborated and submitted to the RA Prime Minister office for approval on December 27, 2021 by the letter 01/8-5/21538-2021 in th form of the RA Prime Minister draft Decree. With the support of the GIZ, a draft budget program evaluation guide has been elaborated and is under discussion. | By the RA Prime Minister Decree N 446-Ա, dated April 28, 2023, "Concept of introduction of the evaluation system of state budget programs" was approved. A budget program evaluation guide was also elaborated. 3 budget programs to be piloted were also selected (1183 Safe school program, 32003 Construction of modular buildings for public schools with small numbers of children, 1176 Ensuring control and regulation in the aviation field, 11001 Control and regulation services in the aviation field, and 1187 Agriculture modernization program, 12009 state support measure for the establishment of vineyards, intensive orchards and orchards cultivated with modern technologies in the Republic of Armenia). | • Established concept of budget program evaluation • Budget program evaluation guide |  | In Progress | Using the elaborated project evaluation concept, it is planned to carry out pilot evaluations of 3 budget programs. |  |  | GIZ
Budget program evaluation guidelines have been developed
|  | 17․2․ Introduce a process of regular evaluation of budget programs | MoF | SB | December, 2023 |  |  | Existence of a schedule and measures for the implementation of budget program evaluation functions | The activities to be carried out within the framework of the event are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. | The activities to be carried out within the framework of the measure are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure |  |  |  | Not started | After the approval of the budget program evaluation concept, the schedule for the introduction of budget program evaluation functions and the list of measures will be clarified. |  |  | GIZ
As of the end of the 2023 budget year, each state body responsible for budget programs has a regular program evaluation process.
As of the end of the 2023 budget year, at least 1 budget program implemented by each state body responsible for budget programs has been assessed experimentally in accordance with the approved guidelines.
6. MTEF process, budget disciplinary and transparency | 18․ Programs / measures arising from the manadatoy obligations of the state are identified and registered | 18․1 Identification and registration of programs / measures arising from the mandatory obligations of the state | MoF | SBs | December, 2021 |  |  | Appropriate methodology is available and procedures are elaborated | The methodological instructions for preparing and submitting budget applications in the framework of the 2021 and 2022 budget processes already contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. The programs / measures arising from the mandatory obligations of the state within the 2021 budget process have already been identified in accordance with the current methodology. At present, work is being carried out with the technical assistance of the IMF to improve the above-mentioned methodology and its application, within which a document of studies and recommendations has been submitted to the RA MoF. The document is currently being studied and discussed by the MoF. After clarifying the approaches to the methodological issues presented in the document, if necessary, necessary work will be undertaken to review the methodology for identifying and registering the programs / measures arising from the mandatory obligations of the state, and to localize the new methodology. | The methodological instructions for preparing and submitting budget applications in the framework of the 2022 budget processes contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. The programs / measures arising from the mandatory obligations of the state within the 2022 budget process have already been identified in accordance with the current methodology. To improve the above-mentioned methodology recommendations have been elaborated with the technical assistance of the IMF which were later piloted with the example of the RA MoF. After summarizing the results of the piloting necessary work will be undertaken to review the methodology. |  | • The methodology and procedures for the identification and registration of programs/measures arising from the contingent liabilities of the state have been elaborated (Methodological instructions for the preparation of the MTEF and the annual budget) •In the framework of 2021 and 2022 budget process, the programs/measures arising from the mandatory liabilities of the state have been identified in accordance with the existing methodology. | December 2021 | Completed | Summary of test results of methodology review proposals and review of existing methodology as needed. |  |  | IMF
In the framework of the 2022 budget process, the mandatory obligations of the state are identified and registered
| 19. Introduction of a single process of drafting the MTEF and annual budget | 19.1․ Creating a legal basis and elaborating methodology for ensuring a single process of drafting the MTEF and annual budget | MoF | - | 2021 |  |  | The single process of drafting the MTEF and annual budget is carried out | Since 2020 the MTEF and annual budget drafting is being carried out in a single process for which the schedules established by the RA Prime Minister's decisions on starting the budget processes of 2021 and 2022 serve as a legal basis. After summarizing the results of the 2021 budget process, the expediency of making relevant amendments to the Law "on the Budgetary System of the Republic of Armenia" will be considered. Accordingly, if necessary, a package of relevant changes will be developed and submitted for approval. |  |  | • Since 2020 the MTEF and state budget formation activites are being carried out in single procedure | August 2020 | Completed |  |  |  | IMF
| 20․ Simplified budget and simplified budget execution reports are available to public | 20․1 Elaborating and publicizing the simplified version of the state budget and the budget execution report | MoF | - | Within one month after the adoption of the 2021 RA state budget (Publication of the Simplified Budget) 2021 (Publication of simplified budget report ) |  |  | Simplified Budget for 2021 and Budget Execution Reports are published on the official website of the MoF Discussions have been held with CSOs on simplified budget and budget execution reports (at least twice a year) | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021: For this purpose, with the support of the GIZ the methodological instructions for the preparation of sectoral budget projects by the state bodies within the framework of the drafting of the RA 2021 draft state budget and MTEF 2021-2023 were elaborated posted on the official website of the MoF link: http://www.minfin.am/website/images/website/documents/Metodakan2021%20(2).docx), as well as it was officially provided to the public authorities. Based on the information provided to the Ministry of Finance by state bodies in accordance with the methodological guidelines for the preparation of sectoral draft budgets "Citizen Budget 2021" was elaborated and published on the official website of the Ministry of Finance. (available at the following link: https://minfin.am/website/images/website/byuje%20ev%20krknaki%20harkum/Citizen_budget_Final_V%20_01.02.2021_compressed.pdf ): | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021. Based on the information provided to the Ministry of Finance by state bodies in accordance with the methodological guidelines for the preparation of sectoral draft budgets "Citizen Budget 2021" was elaborated and published on the official website of the Ministry of Finance (available at the following link: https://minfin.am/website/images/website/Citizen%20Budget%202022_V1.pdf ) At the same time, after the approval of the report on the exection of the state budget for 2020, a simplified version of that report was developed and posted on the official website of the Ministry of Finance (available at the following link: https://minfin.am/hy/page/2020_tvakani_petakan_byujei_parzecvats_hashvetvutyun )։ | In the framework of the measure, according to the schedule approved by the RA Prime Minister's Decree N 72-Ա, dated January 20, 2022 "On Implementation of the elaboration process of the 2023 state budget of the Republic of Armenia, the implementation of the 2023-2025 state medium-term expenditure framework of the Republic of Armenia and the elaboration of the drafts of the 2023 state budget of the Republic of Armenia”, it has been defined that after the adoption of the 2022 state budget the RA MoF elaborates and publicizes the citizen's budget for 2022. Based on the information provided to the Ministry of Finance by state bodies in accordance with the methodological guidelines for the preparation of sectoral draft budgets "Citizen Budget 2022" was elaborated and published on the official website of the Ministry of Finance (available at the following link: https://minfin.am/website/images/website/Citizen%20Budget%202022_V1.pdf). At the same time, after the approval of the 2021 state budget execution report, a simplified version of that report was elaborated and posted on the official website of the Ministry of Finance (available at the following link: https://minfin.am/hy/page/2021_tvakani_petakan_byujei_parzecvats_hashvetvutyun) | • Elaboration of methodological instructions for the preparation of sectoral drafts of the citizen's budget •Elaboration and publication of citizen's budget 2021 and 2022 at the RA MoF official website. • The simplified version of the report on the execution of the state budget for 2021 has been elaborated and published on the website of the Ministry of Finance | Activities for 2020 and 2021 are carried out. | It is a periodic process
| 21. Civil society organizations are more actively involved in the budget process | 21.1.Disclosure of information on budget proposals | SBs | - | 2020-2023 |  |  | RA state bodies have platforms to discuss budget proposals with CSOs. | The measure on the 2021 budget process has been implemented. According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2021 and 2022 budget process, clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. In order to ensure the public discussions on budget applications of state bodies, with the support of the GIZ, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting state budgets (link: http://www.minfin.am/ website / images / website / byuje_amsakan / PB% 20instructions% 20for% 202021% 20budget% 20process-1% 20 (1) .docx): The latter were posted on the MoF official website and provided to all state bodies. At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. | The measure on the 2021 budget process has been implemented. According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2021 and 2022 budget process, clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. In order to ensure the public discussions on budget applications of state bodies, with the support of the GIZ, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting state budgets (link: http://www.minfin.am/ website / images / website / byuje_amsakan / PB% 20instructions% 20for% 202021% 20budget% 20process-1% 20 (1) .docx): The latter were posted on the MoF official website and provided to all state bodies. At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. | Measure regarding the 2023 budget process was carried out According to the schedule approved by the RA Prime Minister's Decree on starting the RA 2023 budget process, clear requirements have been set for posting the budget applications of the RA state bodies on their websites, holding discussions with CSOs regarding the budget applications, and submitting the information on the results of these discussions to the RA MoF together with the applications. | • Elaboration of methodological instructions for ensuring public participation in the process of elaborating budget programs of state bodies | Activities for 2020 and 2021 are carried out. | It is a periodic process |  |  |  | (RF MOF)
|  | 21.2. Establishment of a platform (s) for discussing budget proposals with CSOs | SBs | - | 2020-2023 |  |  | The budget proposals of the RA state bodies include the results of the discussions on the applications with the CSOs. | According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9 "On starting the budget process of the Republic of Armenia for 2021", a requirement was set by state bodies to place their budget applications on their official websites. In order to ensure the process of public discussions on budget proposals of state bodies, with the support of GIZ the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF 2021-2023 and 2021 state budgets (link http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA MoF and provided to all state bodies. At the same time, according to the preliminary agreement, within the framework of the GIZ support, it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the state budgeting process. According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. Nevertheless, conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process. Conditioned by that, according to the methodological instructions of MTEF 2022-2024 (including the state budget of the Republic of Armenia for 2022), it is envisaged that state bodies will organize discussions with CSOs. | According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2022 and 2023 budget process, requirements are set for posting the budget proposals of the RA state bodies on their websites. By the same schedule it has been defined that within the elaboration of draft MTEF (including the state budget) the state bodies should hold discussions with the stakeholder CSO under their competences on budget proposals and submit to the RA MoF Information on the results of those discussions. In order to ensure the public discussions on budget applications of state bodies, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF and state budgets (link: http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx ): At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. However, in Within the framework of the 2022 budget process, discussions on their budget applications haven’t been held with CSOs, mainly due to the lack of proposals on CSO participation in the applications. | In the framework of the GIZ support, the description of the electronic platform of participatory budgeting was elaborated, by which it is planned to: to introduce a unified electronic platform that will make it possible to ensure the availability and accessibility of budgetary and other information for the public, creating the necessary conditions for the equal participation of all stakeholders in participatory processes and the consistent dissemination of these processes to the general public and the rooting of a participatory culture Must support and maintain the implementation of the following functions related to participatory processes. • providing public awareness/notices on participatory processes, • publication/disclosure of information on the state budget and budget programs, • presentation of public comments and suggestions, • implementation of public discussions, • presentation of the reaction (feedback) of state bodies regarding the submitted proposals, remarks and discussions, • providing information on the progress of accepted proposals. | Elaboration of a description of the electronic platform of participatory budgeting |  | In Progress | Designing platform(s) for discussion with CSOs on budget applications based on the description of the participatory budgeting electronic platform |  |  | GIZ (RF MOF)
7․ Automate the process of calculating the cost of budget programs | 22. Within the framework of the 2023 budget process, the processes of calculation (expenditure) of budget programs / measures are carried out through a unified automated system. | 22.1 Step by stem introduction of Automated system of calculating the cost of budget programs | MoF | - | Within one month after the adoption of the 2021 report on the execution of the RA state budget July |  |  | The automated budgeting system has been tested and is ready for implementation. Within the framework of the 2023 budget process, expenditure budgeting were implemented through an automated expnditure budgeting system. | The elaboration and testing of the automated budget expenditure planning system by the RA Ministry of Finance (Authorized Body) has already been completed in December 2019. The system allows applicant bodies to submit online cost-benefit calculations online as part of budget funding applications using pre-designed batch and quota agreed with the Authorized Body in formats preliminary elaborated by applicant bodies and agreed with authorized body , as well as enables the respective competent users of the applicant body and the authorized body approve / reject, as well as summarize the data of the received proposals according to the program, operational-economic classifiers, allowing to receive the necessary details of the openings of the numbers of programs / measures. In 2020 professional meetings were held with the representatives of the applicant bodies on the elaboration of templates for the calculation and substantiation of expenditures on the programs and measures included in the budget proposals. During the training after it, the RA MoF together with the applicant bodies, started the work of elaborating and submitting the templates to the RA Ministry of Finance. All samples agreed and approved by the RA MoF have already been imported into the System. At the same time, based on the data provided by theapplicant bodies, users were created in the system, defining the relevant authorities. | In 2021, the training courses on the development of cost calculation-justification samples for the programs and measures included in the budget applications continued with the representatives of the applicant bodies. The Samples provided by the applicant bodies were agreed upon and approved by the RA Ministry of Finance and entered into the System. | The automated system of costing of budget programs has been tested and is ready for introduction. From the point of view of application in the budget process, the issue of the possibility of integrating the budgeting system into the GFMIS program is currently being discussed. | • Elaboration and testing of the automated system for costing of budget programs |  | In Progress | The question of the possibility of integrating the budgeting system into the GFMIS is being discussed
4․ BUDGET EXECUTION PROCESS CONTROL, TREASURY SYSTEM
8. Budget Execution Reports | 23. Preparation of reports on the execution of the RA state budget by program classification | 23․1 Adaptation of the electronic budget reporting system to the requirements of program budgeting | MoF | - | December, 2019 |  |  | Existence of reports on the RA state budget execution by program classification | The measure is completed, and the reports on the execution of the first quarter of the RA 2019 state budget in program format on the execution of both financial and performance indicators have been submitted by the bodies responsible for the execution of the programs through the electronic budget reporting system. Before that, the system was tested, on April 1-3, 2019 trainings were organized for 64 specialists responsible for preparing report, the system was introduced in all state bodies, and the latter were assisted in the introduction and operation of the system. As a result, the quarterly (incremental) reports on the execution of the RA 2019 state budget were submitted to the RA Prime Minister's Office in program format. During the year, activities have been carried out to solve the problems identified during the operation of the system. |  |  |  | 2019 | Completed
9. Arrears monitoring and management | 24. Arrears monitoring and management | 24.1 Registration of expenditure arrears | MoF | SB | 2020-2023 |  |  | The RA public authorities and territorial administration bodies carry out the registration of arrears on expenses | The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses. Each year the chief budget executive body submits to the Budget Execution Department information on the absence of arrears on state budget expenditures | The measure is regular. Within the framework of the latter, the RA public authorities and territorial administration bodies carry out arrears of expenses. Information on arrears on state budget expenditures is submitted to the RA Ministry of Finance every month. Information on arrears is included in the relevant reports on the execution of the RA state budget. | 1. Collection and analysis of performance observations and analyzes of reasons for under-implementation of financial programs provided for by quarterly (incremental) limits of budget allocations, as well as collection and analysis of information on expenditure arrears on obligations undertaken by bodies 2. In the framework of participation in the organization and programming of financial flows service, presentation of operational, daily forecasts on the performance of expenditure program indicators. 3. Timely and full financing of the expenditure part of the state budget | • State bodies carry out the accounting of arrears on expenses and submit reports on arrears the RA Ministry of Finance every month. | Activities for 2020 and 2021 are carried out | It is a periodic process | Identifying and neutralizing the risks of incurring arrears
Information on arrears is included in the reports on RA State Budget execution
10. Payroll controls | 25. Personnel records and payroll data coordination and implementation of changes in the accounting information system | 25․1 Elaboration of a system for integration of the human resources database into accounting software / AS modules | SB | CSO | 2020-2023 |  |  | Terms of reference for human resource database / accounting information program module integration system is elaborated and approved | As of 2020 In 5 SBs the system is embedded, all the processes related to the personnel registration and salary fund data are carried out through the system, activities are being carried out for system introduction in 5 SBS, in 2 SBs there is an issue of software, terms of reference is being elaborated. The other SBs did not provide information on the measure implementation. According to the information provided by the CSOs, terms of reference of integration system of human resources database with accounting Information System Module was developed for the implementation of the event. The latter stipulates that the relevant employee of the accounting unit will receive an automatic notification about the necessary function performed by the personnel management units in order to make the required changes in the electronic accounting program. | In order to develop the best mechanism for data transfer between the Civil Service Information Platform (hereinafter the Platform) and the accounting information systems used in state bodies, and to ensure its further implementation, discussions were held during 2021. Taking into account that Armenian programs are mainly used for the implementation of accounting functions in state bodies discussion was initiated and organized with the participation of companies engaged in the development of software securities used for accounting purposes in state bodies who expressed their willingness to assist in the implementation of the software solutions described above within the framework of the system functionality. The works are being discussed. | 1. On December 21, 2021, a state purchase agreement for the provision of information technology software maintenance services for the needs of the state was signed between the Prime Minister's Office and "ITresources" LLC, which, starting from 2022, Instead of "Harmonia" Foundation will implement the Civil Service Information Platform (hereinafter the Platform) functionality improvement, solving problems during operation and other functions of technical maintenance of the system, including the works to be carried out in the framework of this measure The above format was developed by the office during the reporting period and submitted to the opinion of the partners on August 10, 2022, regarding the salary and other payments paid by the employer within the scope of the employment contract or the employer's individual legal act per conditions. Below is a brief summary of the partners' suggestions for format. The "Link" company, which operates and maintains the 1C systems operated by the Audit Chamber, the State Supervision Service and the State Commission for the Protection of Economic Competition, offered two possible options for exporting the report. 1) automatically by selecting the appropriate domain from which to download the report to the Platform automatically, 2) generate the report from the software and save, after which the report will be uploaded to Platform: Among these options, the choice was made in favor of the 2nd one, taking into account the results of the discussion and the agreements that took place in the Ministry of Finance. The information regarding the discussions held in the Ministry of Finance and the "ArmSoft" company was also transferred to the "Link" company, as the latter was unable to participate due to its workload. The "ArmSoft" company reported that the format can be obtained automatically in the AS-Enterprise system if the data entered in the system meets the conditions of the specified file. In order to carry out the work, it is necessary for the representative of the given body to establish contact with the service provider attached to the AS-Enterprise system. And in the bodies working with the "AS-Accountant 7" system, the filling of the given file will be performed non-automatically. "ITresources" company stated that all bodies should have the opportunity to export a report in the presented format from AS and 1C programs, after which the platform will provide the tools to download that report. At the next stage, in order to carry out software tests at the proposal of "ITresources" company, it was first necessary to download to the Platform test domain the salary paid by the employer to civil servants for a given month (basic and additional salary, bonus, vacation pay) and other payments (temporary disability allowance, financial aid, etc.) data. The Prime Minister's staff was chosen to fulfill that goal. A letter was presented to the Chief of Staff by the Office to provide information on the salaries and other payments paid to about 200 civil servants of the staff. As a result, the mentioned information was exported in an excel file from the AS-Enterprise accounting system operated by the staff by creating a report in the appropriate format, making software updates in the AS system toolkit. |  |  | In Progress | . Creation of a new section in the platform, in which a specialist (user) of the staff management department of each body will have the opportunity, by selecting the accounting period, to download the file received from the accounting systems, in which the data contained in the excel file will be entered into the database of the platform. 2. Preparation of official letters addressed to all state bodies and implementation of consulting work with relevant specialists of staff management and accounting departments 3. Discussion of the issue of reviewing the need to develop Terms of reference due to the appearance of the problems mentioned in points 2 and 3 of the actions described in column 5 of this report and the content of the solutions provided to them. Basically, in the framework of this measure, it is planned not to integrate systems, but to create a toolkit for exchanging information between these systems. 4. From 2023, instead of "ITresources" company, the functions of improving the functionality of the Platform, solving problems during operation, and other functions of technical maintenance of the system will be performed by the e-Governance infrastructure implementation agency.
|  | 25․2 Introduction and maintenance of the system | [5 empty] | The system is embedded and all processes related to personnel records and payroll data are carried out through the system | The system was launched in the fourth quarter of 2020, and data entry by government agencies on the information platform is currently underway. At the same time, the system is in re-testing process in order to identify problemns and give them relevant solutions.
| 26. Payroll audit | 26․1 implementation of payroll audit by the Internal Audit | MoF | SB, CSO | 2021-2023 |  |  | Data transfer and comparison deficiencies are identified | Payroll audit was not carried out in most of SBs having provided information, due to liquidation of the internal audit unit and following the long-term process of organizing procurement procedures and concluding contracts as a result of oursourcing the function. At the same time, payroll audit is envisaged in the annual Internal Audit Plan for 2021 in 11 PMs that provided information. | A corresponding working group has been set up jointly with the Civil Service Office of the Office of the RA Prime Minister to identify shortcomings in the transfer and comparison of salary data. Based on the results of the working discussions, the following vision was adopted that before the full implementation of the measures provided for in Clause 25, the Ministry of Finance will collect the the results of the salary audit carried out within the framework of internal audit in the manner prescribed by law in accordance with the legislation to identify shortcomings in the transfer of data and comparison between staff management and accounting units. In the framework of the measure, the RA state bodies were offered to envisage the implementation of salary audits in the annual internal audit work programs. In 36 of 48 state bodies it is already planned to perform salary audit by the 2021-2022 annual program. | A relevant working group was established together with the Civil Service Office of the Prime Minister's Office, and as a result of a series of discussions, the issues of information exchange in existing accounting programs and human resources management units were raised. | • Deficiencies in data transmission and collation are identified • The reports provide recommendations on the implementation of wage control |  | In Progress
The reports provide recommendations on payroll control
| 27. Ensuring the accountability of the calculation of salaries and equivalent payments | 27.1 Notification of data on calculation of salaries equivalent payments and received income received to employees, | MoF | SB | 2021-2023 |  |  | Employees receive monthly information on the calculation and payment of income received during the previous month | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries during 2020. | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries . | In the majority of reporting PBs, on a monthly basis, employees are informed via e-mail about the calculation and payment of received income. | Every month, employees receive information on the calculation and payment of the income received during the previous month |  | In Progress | Conditioned by the circumstances of the emergence of the problems mentioned in the 2 and 3 points of the actions described in the 5 column of this report and the content of the solutions given to them. Basically, in the framework of this measure, it is planned not to integrate systems, but to create a toolkit for exchanging information between these systems.
5. PUBLIC DEBT
11. Public debt management | 28. Improving the RA Law "on Public Debt" | 28․1 Conformity of the RA Law "on Public Debt" to the standards applied by international financial institutions | MoF | - | December, 2022 |  | Decembet 2023 | Improving debt statistics by clarifying the definitions used in the RA Law on Public Debt ("Public Debt" and "Government Debt") | The preliminary version of the RA draft Law "On Public Debt" has been elaborated. Discussions are underway with international financial institutions to obtain technical assistance for the implementation of the measure | The preliminary version of the RA draft law "On Public Debt" has been elaborated | The preliminary version of the RA draft law "On Public Debt" has been elaborated | • Elaboration of the RA draft law "On Public Debt" |  | In progress | Discussions with the WB continue to finalize the draft RA law "On Public Debt". |  |  | (ADB/WB/EU)
| 29. RA Government debt portfolio exchange rate risk mitigation | 29․1 Increasing the share of deficit financing in the state budget each year at the expense of net domestic borrowing | MoF | - | December, 2023 |  |  | The share of deficit financing in the state budget at the expense of net domestic borrowed funds is at least 50.0% | The share of deficit financing in the state budget at the expense of net domestic borrowing was 84.7% in 2020 | The share of deficit financing in the state budget for 2021 at the expense of net domestic borrowed funds is 40.6% | In 2022, the share of deficit financing in the state budget at the expense of net domestic borrowed funds will be about 79%. | • The share of deficit financing in the state budget at the expense of net domestic borrowed funds is 84.7% in 2020, 40.6% in 2021 and more than 100% in the first half of 2022. | The Minimum targets are ensured for 2020 The minimum targets for 2021 are not ensured | It is a periodic process | The deficit financing program at the expense of net domestic borrowed funds in the state budget for 2023 is 70.5%
6. PUBLIC SECTOR ACCOUNTING
12. Public Sector Accounting | 30. Monitoring the annual financial statements of public sector organizations | 30․1 Monitoring the financial statements of public sector organizations by the MoF | MoF | - | 2019-2023 |  |  | · Financial statements in accordance with the RA Public Sector Accounting Standard (IAS) | In April 2020, a letter was sent to public sector organizations to submit their 2019 transaction log and financial statements for monitoring purposes. The already submitted financial statements are monitored, and after summarizing the results, they are submitted in writing to the relevant public sector organizations. At the same time, based on the monitoring results the 9th և 10th issues of the Professional Directory were prepared in 2020 and sent to the public sector organizations. |  | The measure is regular. Monitoring of the 2021 transaction logs and financial statements of public sector organizations has been carried out. |  | Activities for 2020 and 2022 are carried out. | It is a periodic process | At the end of each year, public sector organizations submit the package of their transaction log and financial statements which are monitored by the staff of the department. Errors and inaccuracies in the above information are identified and reported to the appropriate organizations to avoid similar errors in the future. "Professional Directory" periodicals are prepared on the basis of common errors.
|  | 30․2 Methodology review (as needed) | MoF | - |  |  |  | Improved regulatory framework | The draft law "On Making Amendments to the Law on Accounting of Public Sector Organizations" has been developed by the Ministry of Finance which has been approved by the RA NA bu first reading on September 18, 2020. | The RA law ՀՕ-84-N "On Making Amendments to the Law on Accounting of Public Sector Organizations" elaborated by the RA MoF was adopted by the RA National Assembly on March 4, as well as a number of by-laws have been elaborated and approved on the basis of these changes. | During 2022, there was no need to review the public sector accounting methodology |  |  | It is a periodic process | A review of the public sector accounting methodology will be carried out if necessary.
|  | 30.3 Implementation of the qualification process for chief accountants of public sector organizations | MoF | - | 2020-2023 |  |  | Qualified Chief Accountants of Public Sector Organizations | During 2020, 10 qualification exams for public sector accountants were held, as a result of which 54 people were qualified. | During 2021, 34 qualification exams for public sector accountants were held, as a result of which 143 people were qualified. As of December, 2021, 197 people are qualified as public sector accountants in Armenia. | During 2022, 16 qualification exams for public sector accountants were held, as a result of which 78 people were qualified. Currently275 people are qualified as public sector accountants in Armenia as of December 31, 2022. |  | Activities for 2020 and 2022 are carried out. | It is a periodic process
| 31. Preparation of interim consolidated financial statementss at the ministries level | 31․1 Development of a methodology for consolidating financial statements | MoF | - | 2022-2023 |  |  | Consolidation methodology is available | The draft consolidation methodology has been developed and will be reviewed by international experts within the activity for the introduction of the GFMIS. | The draft consolidation methodology has been developed and will be reviewed by international experts within the activity for the introduction of the GFMIS. | This measure is part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. The draft consolidation methodology is in the process of revision n the framework of the works carried out in the direction of the introduction of GFMIS. | The consolidation methodology is available |  | In progress | The measure can be carried out in the framework of the GFMIS if the appropriate financial and technical means are available. |  |  | (GIZ/WB)
|  | 31․2 Development or acquisition of a joint computer program for the purpose of consolidation | MoF | - |  |  |  | Computer program necessary for consolidation | this measure is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. | This measure is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. | The measure is also a part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS therefore, the implementation depends on the circumstances of the GFMIS introduction | Software program required for consolidation |  | In progress | The software program necessary for consolidation can be purchased if there are adequate financial resources.
|  | 31․3 Preparation of interim consolidated financial statements at the ministries level | MoF | - | December, 2023 |  |  | Interim consolidated financial statements at the ministries level are submitted | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. | Interim consolidated financial statements are presented at the level of ministries |  | Not started | In the case of the availability of a software program, it is planned to prepare consolidated financial reports at the level of at least one ministry, including the ministry and its subordinate SNCOs.
7. CORPORATE ACCOUNTING AND AUDIT
13. Regulation of corporate accounting and audit activity | 32. Introduction of public control system over accounting and auditing activities | 32․1 Completion of the necessary sub-legislative framework | MoF | - | 2020-2021 |  |  | New specialized structures for sector regulation and control - Public oversight board model | The RA Government decision 1336-N, dated August 13, 2020 "On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Computer Software Enabling Accounting" was elaborated and approved. 4 sessions of public oversight board were held as a result of which Decision 1-Լ "On defining the Procedure for Maintaining the Register of Auditors, Expert Accountants, Audit Organizations, and Minimum List of Data Included in It" was adopted on August 31, 2020 and Decision 2-Լ "On approving the decision N 6-L of October 26, 2020 of the Board of the Chamber of Auditors and Expert Accountants of Armenia" was adopted on November 11. Legal acts related to the extension of qualification certificates of accountants and auditors have been developed and approved. The draft decision of the AOB "On approval of the procedure for conducting mandatory inventory of assets and liabilities" has been developed, which is currently under discussion. | In order to regulate the areas, the RA Audit Chamber, expert accountants, have developed a number of legal acts, which have been submitted to the Public Oversight Board of Accounting and Auditing activity for approval. During 2021, 7 sessions of the Oversight Board took place, as a result of which 15 decisions of the Oversight Board were adopted. At the same time, the legal acts related to the extension of the qualification certificates of accountants and auditors were elaborated and approved. During 2021, seminars-discussions were organized for the employees of the Ministry of Finance of the Republic of Armenia on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing.: |  | • The RA Government Decision N 1336- Ն, dated August 13, 2020 “On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Software Enabling Accounting" • Public Oversight Board Decision 1-Լ, dated August 31, 2020 "On defining the Procedure for Maintaining the Register of Auditors, Expert Accountants, Audit Organizations, and Minimum List of Data Included in It" • Legal acts related to the extension of qualification certificates of accountants and auditors have been elaborated and approved • The draft decision of the POB "On approval of the procedure for conducting mandatory inventory of assets and liabilities" has been developed | 2021 | Completed |  |  |  | (WB/RD MOF)
Effective audit quality control system
adjusted scope of organizations subject to mandatory audit
|  | 32․2 Staff training | [5 empty] | Appropriate level of capacity | During 2020, remote seminars were organized for the employees of the RA Ministry of Finance on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing. | During 2021, seminars-discussions were organized for the employees of the RA Ministry of Finance on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing. |  | Capacity building of the RA MoF staff during 2020 and 2021 | 2021 | Completed
8. FINANCIAL MANAGEMENT AND CONTROL OF STATE ORGANIZATIONS: STATE NON-Commercial ORGANIZATIONS (SNCO)
14. Financial Management and Control of state organizations accountability of state non-commercial organizations | 33. Improving the system of accountability and monitoring of the financial and economic activities of SNCOs | 33․1 Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | MoF | - | 2020-2023 |  |  | Availability of an up-to-date system for monitoring the financial and economic activities of SNCOs | In order to implement reforms in the system of public financial management, a system of fiduciary control of state non-commercial organizations has been developed since 2010 in the field of financial management and control of state organizations. In view of testing the elaborated system in practice and elaborating fiduciary control effective system, In 2010, the RA Government, with the support of the World Bank, initiated the "Piloting of Fiduciary Control Systems of SNCOs" project. At this stage, the elaborated system is being studied, work is being done to modernize it and bring it in line with the current system of SNCO activities. Studies have been conducted in the field of activity of state non-commercial organizations in order to elaborate a system of non-financial (productive) indicators. | Studies have been conducted in the field of activity of state non-commercial organizations in order to elaborate a system of non-financial (outcome) indicators. | Studies were conducted in the sphere of activity of state non-commercial organizations in order to develop a system of non-financial (outcome) indicators. | Existence of an up-to-date monitoring system of financial and economic activity |  | In progress | The measure can be carried out with technical support. |  |  | ADB
9. PUBLIC PROCCUREMENT
15. Upgrading the e-procurement system | 34. New e-procurement system software | 34․1 Development and introduction of new e-procurement system software | MoF | - | December, 2020 | December, 2021 | 3rd decade of December 2023 | New existing e-procurement software | Activities have been carried out with donor organizations to develop a business model and terms of reference for the introduction of a new e-procurement system. In particular, an agreement was reached with the European Bank for Reconstruction and Development to elaborate a new e-procurement software system with the latter's technical and financial assistance, according to which it is expected to obtain from EBRD business model rationale for the introduction of the new e-procurement system. Given that there is no response from the Bank yet, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model and terms of reference for the implementation of the e-procurement system, provided that it will not be implemented by the consultant if implemented by the EBRD. The issue related to the substantiation of the business model proposed by the Bank is currently being discussed, after the clarification of which the relevant decision will be made. | The measure was included in the action plan of the RA Government for 2021-2026. The development of the terms of reference of the new e-procurement system is planned to be carried out within the framework of the contract for the provision of consulting services for the implementation of the GFMIS | The measure was included in the 2021-2026 action plan of the RA Government. The elaboration of the terms of refernce of the new electronic procurement system is planned to be carried out in the framework of the contract for the provision of consulting services for the purpose of the introduction of the GFMIS. | New e-procurement software in place |  | In progress | Preparation of terms of reference, organization of competitive procurement procedure for software development, system design and operation
16. Procuurement planning | 35. Improving the procurement planning system | 35․1 Develop RA Government draft decision on the introduction of a unified planning system for determining the cost estimates of items with similar characteristics automatically | MoF | - | December, 2020 | December, 2021 | 3rd decade of December 2023 | The same needs of customers are met with items with the same characteristics and cost estimates | The relevant proposals for the implementation of the mentioned measure were received and summarized from the RA public administration bodies based on the letter 01/26-1/3308-2020 of the RA Minister of Finance, dated 21.03.2020. | The implementation of the measure is interconnected with the development of new software for the e-procurement system | The implementation of the measure is related to the development of new software for the e-procurement system | Similar customer needs are met by items with similar specifications and estimated prices |  | In progress | The implementation of the measure is related to the development of new software for the e-procurement system
17. Procurement Appeal System | 36. Improving the procurement appeal system | 36.1 Making changes in the RA Law "On Procurement" | MoF | - | December, 2021 |  |  | Functional and independent appeal system | The RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Amendments to the RA Law on State Duty", "On Making Amendments and supplements to the RA Civil Procedure Code" have been elaborated and submitted to public government bodies, international donor organizations and civil society for consideration. Discussions with the EU SIGMA Program Expert Group are ongoing. | The package of draft laws was adopted by the National Assembly on 17.11.2021 in the first reading. |  | The package of RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Supplements to the RA Law on State Duty", "On Making Amendments and supplements to the RA Civil Procedure Code" was adopted by the RA National Assembly on 17.11.2021 in the first reading. |  | Completed
10. PUBLIC INTERNAL FINANCIAL CONTROL AND FINANCIAL-BUDGETARY OVERSIGHT
18. Financial management and control | 37. Ensuring the introduction of financial management and control system | 37․1 Testing of FMS system methodology | MoF | - | December, 2020 | December, 2021 | Decembet 2022 | Piloted methodology of FMS | As of 2019, there are still draft legal acts for the introduction of the FMS, which need to be reviewed once again, considering them from the point of view of the implementation of the PB system, discussing them with the Civil Service Office. In order to test the FMS system, an agreement was reached in 2019 with the RA Ministry of Education and Science (there is an official letter from the Ministry of Finance and an agreement with the pilot ministry) to pilot the above methodology. The second state body that was selected and an agreement reached with the latter's representatives is the RA Ministry of Labor and Social Affairs. | As a result of the work with the development partner organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical support. In order to support the RA Ministry of Finance in the introduction of the financial management system, drafts of relevant technical specifications have been developed. | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. | A proven methodology of the FMC system FMC adopted concept and legislation |  | In progress |  | The deadlines required for the measure are short and there is a risk in securing the measure within the set timeframe. | Accelerate the work related to the testing of the FMS methodology as much as possible, assess the realism of the implementation of the measure and, if necessary, make a proposal for extension of the term. | GIZ
|  | 37․2 Adoption of FMS Concept and FMS Legislative Acts |  |  | 2021-2022 |  | 2022-2023 | · FMS adopted concept and legislation | During 2018-2019 the FMC draft concept has been elaborated with the support of GIZ. | It is related to the results of the measure 37.1 | It is related to the results of the measure 37.1 |  |  | Not started |  | The implementation of the measure is related to the results of event 37.1, the implementation of which is assessed as risky. | Take measures to implement the 37․1 measure on time.
|  | 37․3 Introduction of FMS system in public sector organizations | MoF | SB | Since 2022 |  |  | · The process of introducing the FMS system is carried out according to the set schedule | As the measure is related to event 37.1, the work related to this event will start after the testing of the FMS system methodology and adoption of FMS concept and relevant legislation | It is related to the results of the measure 37.1 and 37.2 | It is related to the results of the measure 37.1 and 37.2 |  |  | Not started |  | The implementation of the measure is related to the results of event 37.1 and 37.2 , the implementation of which is assessed as risky. | Accelerate 37.1 and 37․2 measures activities
19. Public sector internal audit | 38․ Carrying out external evaluation of the quality of internal audit | 38․1 Approval of the external audit quality assessment methodology | MoF | - | December, 2019 | December, 2021 | December, 2022 | Order approved by the RA Minister of Finance "On approving the procedure for conducting external evaluation of the internal audit quality | In the context of this measure, with the support of the World Bank, an external quality assessment manual was developed, which was piloted in 2 organizations of the RA public sector. RA Minister of Finance draft order has been elaborated. The draft order was discussed with the representatives of state bodies, was finalized and is ready for approval. | The measure is planned to be implemented with the support of development partner organizations. As a result of discussions with development partner organizations, a proposal was received from the World Bank to support the implementation of the measure, the scope of which is being adjusted. | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. |  |  | Not started |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the deadlines for the implementation of the measure are short, it is necessary to take steps to implement the measuree in due time. | Clarify the issue of those responsible for the implementation of the measure, organize the activities envisaged by the strategy of the measure as soon as possible. | WB
|  | 38․2 Carrying out external evaluation of the quality of internal audit in public sector organizations |  |  | 2020-2022 | 2021-2023 | 2022-2023 | All public sector organizations where an internal audit system is in place will be subject to external evaluation by the MoF. |  | Is related to the results of measure 38.1 |  |  |  | Not started |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the implementation of the measure is related to the results of measure 38.1 which is considered risky | Clarify the issue of those responsible for the implementation of the measure, and take steps to organize the measure 38.1 in the set timeframe
Report on the quality of internal audit of the RA public sector
| 39․ Ensuring Internal Audit and External Audit Cooperation | 39․1 Define internal audit and external audit cooperation procedures | MoF | AC (by agreement) | December, 2023 |  |  | Joint order of the RA Minister of Finance and the Chairman of the RA Audit Chamber "On approving the order of internal-external audit cooperation" | The procedure for internal-external audit cooperation has been under development since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version and after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. | The procedure for internal-external audit cooperation has been under elaboration since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version and after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. |  |  | In progress | Finalize the documents, submit them for discussion with the RA Audit Chamber and PMs, and submit the revised document for approval as a result of the discussions. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure
| 40. Emphasis on Performance Audit Capability and Provide practical application of 30% of the annual plan | 40․1 Approval of performance audit methodology | MoF | - | 2019-2020 | 2021-2022 | 2022-2023 | Approved order of the RA Minister of Finance "On approving the performance audit manual" | RA Minister of Finance draft order "On approving the performance audit manual" has been developed, which is in the process of revision, within the framework of which it is necessary to ensure the connection of the performance audit with the embedded PB system, which which will provide an opportunity to comprehensively assess the results of the programs of the PBs implementing budget programs considering it not only in the context of financial but also in the context of non-financial performance indicators. |  | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. |  |  | Not started |  | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure
|  | 40․2 Increasing the role of performance auditing in internal audit legislation |  |  | December, 2020 | December, 2022 |  | Requirement stipulated in the internal audit legislation, according to which the performance audit will make up 30% of the annual internal audit plan |  | It is related to the results of the measure 40.1 | [5 empty] | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the implementation of the measure is related to the results of measure 40.1 which is considered risky. | Clarify the issue of those responsible for the implementation of the measure, and take steps to organize the measure 40.1 in the set timeframe
|  | 40.3 Development of performance auditing skills of internal auditors operating in RA public sector organizations |  |  | 2020-2023 | 2022-2023 |  | Internal auditors in RA public sector organizations trained in performance auditing |  | It is related to the results of the measures 40.1 and 40.2 |  |  |  | Not started |  | At present, the unit responsible for the implementation of the measure in the RA MoF has not been specified. At the same time, the implementation of the measure is related to the results of measure 40.1 and 40.2 which is considered risky. | Clarify the issue of those responsible for the implementation of the measure, and take steps to organize the measure 40.1 ևand 40.2 in the set timeframe | (GIZ)
| 41. Development of professional knowledge and skills of internal auditors | 41․1 Elaborating a program for developing the professional knowledge and skills of internal auditors | MoF | - | December, 2020 | December, 2021 | December, 2022 | Internal auditors' professional knowledge and capacity are assessed, needs identified, development plan approved |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. |  |  | Not started | Modernization of internal audit qualification system and modernization of internal audit capacity building program will be implemented. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
|  | 41․2 Optimization of continuous professional training courses for internal auditors |  |  | 2020-2022 | 2021-2023 | 2022-2023 | The internal auditors have the requirements of the RA legislation on internal audit, international advanced experience, theoretical knowledge of internal audit and practical skills. |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. |  |  | Not started | Modernization of internal audit qualification system and modernization of internal audit capacity building program will be implemented. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
|  | 41․3. Elaboration of an online information system for the continuous professional training of internal auditors |  |  | 2020-2021 | 2021-2022 | 2022-2023 | Internal auditors undergo an annual continuous professional training program through an online information system |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. |  |  |  | Not started |  | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
|  | 41․4 Review of the Public Sector Internal Auditor Qualification Procedure |  |  | December, 2021 | December, 2022 |  | Internal auditor qualification system based on relevant international approaches |  | As a result of the activities with donor organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical assistance. For this purpose, drafts of relevant technical specofocations have been elaborated to further assist the RA Ministry of Finance in improving the internal audit system. |  |  |  | In progress | Modernization of internal audit qualification system and modernization of internal audit capacity building program will be implemented. | At present, the unit responsible for the implementation of the measure in the RA Ministry of Finance has not been specified. | Clarify the issue of those responsible for the implementation of the measure | (GIZ)
20. Central harmonization unit (CHU) | 42. CHU personnel recruitment and capacity building | 42․1 CHU personnel recruitment and capacity building | MoF | - | 2019-2021 |  | 2022-2023 | Necessary capacities are available in CHU | The relevant unit which was carrying out the functions of the CHU, was dissolved on February 24 of this year and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CHU. | The relevant unit which was carrying out the functions of the CHU, was dissolved on February 24 2022 and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CHU. | The implementation of the measure is related to the implementation of the measure "Defining the vision and road map of the institutional transformation of the internal audit system" provided for in the 6th point of the action plan of the RA Government for 2021-2026 approved by the RA Government Decision N 1902-L, dated 18.11.2021. |  |  | In progress | Recruitment of CHU staff and organizing training courses for staff capacity building | The relevant unit which will deal with the CHU functions, has not yet been specified and is staffed with specialists with relevant capabilities. | Clarify as soon as possible the issue of the unit dealing with the functions of the CHU and staff with specialists with relevant capabilities.
21. Financial and budgetary control | 43․ Ensuring effective financial and budgetary control activities | 43․1․ Review of financial-budgetary control legislation, update, development of new methodology for implementation of financial-budgetary control | MoF | - | 2020-2021 |  | 2022-2023 | By-laws defining the modern methodology of financial and budgetary control | In the context of this group of measures, the main problems in the system of financial-budgetary control were formulated in 2018-2019. The RA Government decision "On defining the procedure of financial and budgetary control of the Republic of Armenia" and declaring null and void the RA Government decisions dated July 11, 2002 N 1112 N and February 23, 2012 N 207 " has been elaborated which is under discussion | An expert mission was developed with the European Commission's TAIEX expert group to elaborate a new methodology document on the analysis of the status quo of the existing financial control system in Armenia and capacity-building program. However, it was not enough to achieve the strategy. | With the expert group of the European Commission's TAIEX tool, the expert mission aimed at elaborating a new methodology document and capacity building program for the analysis of the status quo of the existing financial control system in Armenia and risk-based controls was carried out. However, it was not enough to ensure the result defined by the strategy. As a result of the discussions held in the framework of the EU SIGMA program, "SIGMA work program for Armenia in December 2022- March 2024" draft program provides advice and support for the development of financial control and internal audit, as a result of which the legislative and operational framework for the development and strengthening of financial control and internal audit will be formed. At the same time, the draft decision of the Government of the Republic of Armenia "On making changes to the Decision of the Government of the Republic of Armenia N 1902-L, dated November 18, 2021" envisages the elaboration of a legislative package for the purpose of transferring the function of direct control (inspection) over the State Budget of the Republic of Armenia to the State Control Service of the Republic of Armenia. Discussions are also underway to involve an international expert on budget program evaluation and monitoring issues. |  |  | In progress | Currently, efforts are being made in this direction to attract donor organizations, in particular, a correspondence was held with the coordinator of the EU SIGMA program, Alastair Swarbrick, in the framework of which the package of legislative acts regulating the sector was transferred to him.
|  | 43.2 Capacity building of specialists in the field of financial-budgetary control |  |  | 2022-2023 |  |  | Specialists in the field of financial-budgetary control have professional skills and have relevant knowledge |  |  | Related to the results of measure 43.1 |  |  | Not started | Currently, efforts are being made in this direction to attract donor organizations, in particular, a correspondence was held with the coordinator of the EU SIGMA program, Alastair Swarbrick, in the framework of which the package of legislative acts regulating the sector was transferred to him.
|  | 43․3 Availability of necessary databases for risk assessment |  |  | 2020-2023 |  | 2022-2023 | Introduction of a new risk system based on complete, substantiated and justified information analysis | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. | By the letter of the RA Ministry of Finance N 01/15-3/18438-2021, dated November 12, 2021, a question was raised to provide access to the RA Ministry of Finance to the data available in the information databases available in RA state bodies, such as “Healthcare Electronic Information ARMED System”, “Unified information database of personal data (social bank)”, "Automated property tax accounting system introduced in RA communities (oracle)", "Data base and register of real estates considered state property", "On land owners, land renters, persons who made real estate purchase and sale transactions", "Property Tax and Land Tax Databases", "Education Management Information System", “Border electronic management information system”, “Taxpayer-3”, “PENTAHO BI information-analytical system of standard reports based on the information available in the "Taxpayer-3" system, Information databases (databases) of "File-online" system for submitting tax calculations electronically, issuing tax invoices electronically. According to the RA Prime Minister recommendation N 02/16.10/39466-2021, dated 16.11.2021 (hereinafter the Recommendation), the relevant bodies of the RA state administration were instructed to discuss the possibility of providing access to the information bases (databases) necessary for the RA Ministry of Finance. Currently, as a result of the discussions organized with the state bodies managing the bases, as well as with the e-Governance infrastructure implementation agency (EKENG) CJSC, the bases have already been received from the State Property Management Committee and the Ministry of Health (partially). At the same time, in accordance with the RA Government Decision N1849-N by the letter N 01/15-3/3535-2022, dated 01.03.2022,a request "Data base interconnection and transfer of personal data belonging to state or local self-government bodies" was submitted to the EKENG CJSC for providing access to the Ministry of Finance for the following databases: • SRC database («taxpayer-3»), • “Healthcare Electronic Information ARMED System”, • “Unified information database of personal data (social bank)”, including "Paros" system, "Pyunik" system, "E-pension" system, Information on registered employees, • ARPIS (Data on land owners who are legal entities, land leasers, cadastral values of immovable properties, legal entities that have made real estate purchase and sale transactions), • Education management information system: As a result of the study of the aforementioned request, an administrative proceeding (case N-006/03/22) was initiated at the Personal Data Protection Agency regarding checking the compliance of personal data processing required by requests for data base interconnection and transfer of personal data belonging to state or local self-government bodies with the RA Law "On Personal Data Protection" requirements. As part of the administrative proceedings, hearings were held at the agency on April 11, 2022. As a result of the aforementioned administrative proceedings, a relevant decision was adopted on May 2 of this year. By the Ministry letter N 01.1/15-3/16183-2022, dated 14.09.2022 to "EKENG" CJSC it was requested to receive the decision adopted as a result of the request, in response to which, according to the received letter N 2763, dated 23.09.2022, "EKENG" CJSC informed that the aforementioned bases cannot be provided According to the RA Prime Minister recommendation N 02/16.10/39466-2021, dated 16.11.2021 (hereinafter the Recommendation), the relevant bodies of the RA state administration were instructed to discuss the possibility of providing access to the information bases (databases) necessary for the RA Ministry of Finance. Currently, as a result of the discussions organized with the state bodies managing the bases, as well as with the Office for the Implementation of Electronic Management Infrastructures (EKENG) CJSC, the bases have already been received from the State Property Management Committee and the Ministry of Health (partially). At the same time, in accordance with the RA Government Decision N1849-N by the letter N 01/15-3/3535-2022, dated 01.03.2022,a request "Data base interconnection and transfer of personal data belonging to state or local self-government bodies" was submitted to the "Electronic Management, Infrastructure Investment Office" CJSC (EKENG) for providing access to the Ministry of Finance for the following databases: • SRC database («taxpayer-3»), • “Healthcare Electronic Information ARMED System”, • “Unified information database of personal data (social bank)”, including: "Paros" system, "Pyunik" system, "El-pension" system, Information on registered employees, • ARPIS (Data on land owners who are legal entities, land leasers, cadastral values of immovable properties, legal entities that have made real estate purchase and sale transactions), • Education management information system: As a result of the study of the aforementioned request, an administrative proceeding (case N-006/03/22) was initiated at the Personal Data Protection Agency regarding checking the compliance of personal data processing required by requests for data base interconnection and transfer of personal data belonging to state or local self-government bodies with the RA Law "On Personal Data Protection" requirements. As part of the administrative proceedings, hearings were held at the agency on April 11, 2022. As a result of the aforementioned administrative proceedings, a relevant decision was adopted on May 2 of this year, but it has not yet been submitted to the RA Ministry of Finance. |  |  | In progress | Currently, the works in this direction are ongoing.
11. PUBLIC ASSETS AND PUBLIC INVESTMENT MANAGEMENT
22. Public assets management | 44. Ensure monitoring of government financial and non-financial assets | 44.1․Elaboration and approval of the methodology of public asset management and legal acts necessary for its introduction | MoF | - | 2020-2022 |  |  | Existing methodology on management of financial and non-financial assets of the Government, and legal acts approved in accordance with the RA legislation | An agreement was reached on the provision of IMF technical assistance for the implementation of the measure, within the framework of which the report "Program Budgeting and Management of Public Assets" was submitted to RA the Ministry of Finance for consideration. | In the framework of IMF technical assistance, the conceptual and methodological approaches to the public asset management were elaborated and submitted to the position of the RA Ministry of Finance. The remarks and suggestions of the RA Ministry of Finance were presented on the latter, on the basis of which the experts were offered to review the report. | In the framework of IMF technical assistance, the conceptual and methodological approaches to the public asset management were elaborated and submitted to the position of the RA Ministry of Finance. |  |  | In progress | According to the results of the study of the proposals regarding the conceptual and methodological approaches to the management of public assets, clarify the next steps to be implemented in that field. | The timing of the measure is short, and at present the conceptual-methodological approaches to public asset management are not specified. At the same time, the role of the RA Ministry of Finance in terms of developing and monitoring the methodology of public asset management needs to be clarified. | To formulate the position of the RA Ministry of Finance on the presented approaches as soon as possible. Based on the results, if necessary, initiate the design of relevant conceptual and legal documents. | (GIZ/IMF/RF MOF)
|  | 44.2 Implementation of trainings on asset management techniques in accordance with the approved legislation | MoF | SB |  |  |  | Specialists trained in accordance with the law on public assets | .The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  |  |  | Not started |  | The implementation of the measure depends on the results of the measure mentioned in pointz 44.1. the implementation of which is assessed as risky | Take measures to implement the measures mentioned in point 44.1 in due time. | GIZ
|  | 44.3 Preparation and monitoring of financial and non-financial asset registers | SB | - |  |  |  | Asset Monitoring Report | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  |  |  | Not started |  | The implementation of the measure depends on the results of the measure mentioned in pointz 44.1. the implementation of which is assessed as risky | Take measures to implement the measures mentioned in point 44.1 in due time.
| 45. Ensuring transparency of the sale, transfer, alienation process and the right to use non-financial assets | 45.1 definition of procedures for the sale, transfer, alienation process and the right to use non-financial assets will be reviewed. | MoF | MoTAI | 2022-2023 |  |  | Procedures for the sale, transfer, alienation process and the right to use non-financial assets are approved. | The activities to be carried out within this measure are the introduction of a public asset management methodology to be developed under measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The works to be carried out in the framework of this measure are the introduction of the public assets management methodology to be elaborated within measure 44.1. The latter is a logical continuation of the aforementioned measure and will be implemented based on the results of that measure. |  |  | Not started |  | The implementation of the measure depends on the results of the measure mentioned in pointz 44.1. the implementation of which is assessed as risky | Take measures to implement the measures mentioned in point 44.1 in due time. | IMF
23. Public Investment Management | 46․ Creating a Legislative Basis: Public Investment Management Methodology | 46.1․ Elaboration of a public investment management manual | MoF | - | December, 2019 |  |  | Public Investment Management Manual has been developed and is ready for testing | 1. Within the framework of the works aimed at the introduction of the public investment program management system, in particular, the elaboration of a methodology for identifying, elaborating, evaluating and setting priorities of public investment programs the draft Public Investment Management Manual (hereinafter the Manual) was developed jointly with the experts of the World Bank (hereinafter the WB). According to the appendix approved by the RA Prime Minister's decision N 5-A of January 9, 2020 "On starting the budget process of 2021" of the RA Prime Minister, for the latter’s testing the RA Ministry of Economy has provided to the RA Ministry of Healthcare, Ministry of Education, Science, Culture, Sports, Ministry of territorial administration and infrastructure, in the defined timeframe "The form for the investment project concept and quality assessment" (the standard form) to present the new projects in excess of 70 million drams in the standard form. The pilot stages of the manual have passed 8 investment projects provided by the mentioned agencies. 2. The testing of the manual with the agencies was carried out in stages, by sectors. In this regard, in the first phase, from January 29 to February 14, 2020, 6 meetings and discussions were held, during which the information on the Manual was provided to the representatives of the relevant agencies, as well as consultancy on the completion of the Form per the Manual. 3. In the second stage, on February 24-28, 2020, a seminar-discussion was held with the participation of WB experts, experimentally selected ministries, representatives of the RA Ministries of Finance, Economy and the Office of the RA Deputy Prime Minister Tigran Avinyan, during which the WB experts gave a detailed reference to the principles of identifying problems within the framework of investment projects, setting goals, and action-intermediate result-end-impact-benefit "logical chain formation. Based on the relevant examples, the mechanisms for calculating the demand-risk analysis, as well as the financial-economic analysis of investment projects were presented. 8 new investment projects submitted by the RA Ministry of Health, the RA Ministry of Education and Science and the RA Ministry of TAI were studied. During the discussions, observations and proposals were submitted for all the projects, as a result of which the representatives of the ministries were offered to amend the provided investment project applications based on the submitted considerations and submit the revised version to the RA Ministry of Economy. 3․ In the 3rd stage, on March 12, 2020, and March 13, a video conference was held at the RA Ministry of Economy with the participation of the staff of the RA Ministry of Health, the RA Ministry of Education and Science and the WB experts. During the video conference, the considerations on the investment projects submitted in accordance with the Standard Form, provided by the agencies, were further discussed, on the basis of which it is planned to finalize the revision of the projects. As a result of the implemented works, the strengths and weaknesses of the Manual were identified, as well as the shortcomings were registered, localizing the Manual as much as possible, taking into account the situation in the Republic of Armenia. The above-mentioned works were summarized in April 2020. |  |  | • Elaboration of a draft Public Investment Management Manual | 2020 | Completed |  |  |  | WB
|  | 46.2․ Testing the Public Investment Management Manual and identifying deficiencies. |  |  | december, 2020 |  |  | Report on testing results and existing deficiencies. | The manual was tested in the following phases Phase 1 1. From January 28 to February 14, 2020 , meetings and discussions were held with the representatives of the RA Ministry of Health, the RA Ministry of Education, Science, Culture and Sport the RA TAI within the introduction of the Public Investment Management System on completing investment projects according to the Model in the framework of the manual test. 2. On February 24-28, 2020, with the participation of representatives of interested state agencies, in particular the RA Ministry of Territorial Administration, the Ministry of Health, the Ministry of ESCS, the Ministry of Finance, the Ministry of Economy, and the Office of the Deputy Prime Minister Tigran Avinyan, 5 seminars-discussions on the new initiatives completed by the relevant agencies in accordance with the form within the framework of the public investment management system implementation. 3. Given the coronavirus situation, further manual testing was performed online. Preliminary evaluation of investment projects has been carried out. 4. Taking into account that as a result of the study of investment projects the indicators of investment projects were not provided with sufficient accuracy, on the initiative of the RA Ministry of Economy organized on June 23, 2020 a remote workshop was organized and held the WB experts, within which the necessary indicators were discussed for each investment project, as a result of which it was decided that the "Human Life Value" indicator is missing in Armenia, while it is necessary for evaluating public investment, in particular, social programs. In this context, a working group has been set up to recruit relevant specialists to calculate this indicator. 5. As a result of the discussions with the selected pilot agencies, the investment project provided by the RA Ministry of Health was selected, additional work was done to include new indicators for the evaluation of the project. ։ The indicators of the considered project of a similar program provided by the WB experts were studied, within the framework of which the indicators became almost 75% comparable. In terms of 25% incomparable indicators ․ Preliminary feasibility study is planned to be carried out on August 3, 2020 with WB expertsto identify the missing indicators, but due to martial law, this process has been postponed to early 2021. In case of absence of "Human Life Value" index for Armenia in the mentioned period, the index calculated by the WB for Armenia will be taken into account ։ 6. As a result of the preliminary feasibility study carried out jointly with the WB experts, the practical testing phase of the Manual will be summarized, the results of which will be included in the Manual (as mentioned in point 46.1). ։ In the context of the above, it will be possible to fully assess the Manual, as a result of which it is planned to carry out the work of circulating the Manual among the relevant departments, summarizing and approving the considerations on the latter. Phase 2 On September 25, 2020, the RA Prime Minister held a consultation, during which the draft concept of public investment management was presented, and as a result the Prime Minister proposed to take note of the draft and instructed to continue the work on strategy revision and finalize the document. In continuation of the work on the introduction of the public investment management system launched in the first half of 2020, the scope of the agencies previously involved in the work on the introduction of the public investment management system has been expanded. In this context, an online discussion was held on November 4, 2020, chaired by the RA Deputy Minister of Economy Avag Avanesyan with the participation of the representatives of the relevant agencies and the second phase of the manual testing works has started During the discussion, the Deputy Minister provided details, in particular, on the purpose of the introduction of the public investment management system, features, provisions of the draft, as well as programs financed from the consolidated budget, the economic profitability of the latter. During the online discussion, clarifications were provided on the methodology of evaluation criteria for public investment programs stipulated by the Project, as well as the scope of competence of each department within the Project, project identification, project evaluation, prioritization and evaluation procedures. The role of the RA Ministry of Finance in the framework of the introduction and operation of the public investment management system was especially emphasized. In this regard, the representative of the RA Ministry of Finance was offered to present the problems and risks that are visible in the Sample and may hinder the budget process. The representative of the RA Ministry of Finance emphasized the process of public investment management, but the latter registered the issue of implementing the budget process on the basis of the Manual as a methodological guide. In this regard, the RA Deputy Minister of Economy pointed out that it can be stated that the process of public investment management is an adjunct to the budget process, does not imply a change in the budget process and the only change is the International Monetary Fund requirement that the list of planned programs be included in the 2022 budget documents. The process of public investment management is regular throughout the year and the identified projects can be included in the list of projects at any time, after passing the relevant procedures. During the online meeting, they also touched upon the issues to be further discussed by the RA Ministry of Finance, in particular, the issue of codes given to the programs at the planning stage (the application submitted to the RA Ministry of Finance and the program that went through the process of public investment management should have the same code, so that in the future they can be easily identified. As a result of the discussion, an agreement was reached between the participants to identify at least three project ideas for each agency on which joint work on the development of exemplary model forms will be carried out. In connection with the above, the RA Ministry of Economy has initiated separate meetings in each agency with the participation of the Deputy Ministers and employees of the relevant units during which the RA Ministry of Economy has presented and continues a detailed information on the introduction of public investment management system. In this regard, a schedule of preliminary meetings has been set for each agency. As of December 2020, separate meetings-discussions were organized with the representatives of the RA Ministry of Education, Science, Culture and Sport, the RA TAI, the RA TAI Water Committee, the RA Ministry of Justice, the RA Ministry of Emergency Situations As a result of these discussions, the mentioned ministries have already provided drafts of public investment programs, relevant lists, around which online substantive discussions have taken place, and provided consulting proposals. It should be noted that the work on the introduction of a public investment management system is ongoing; in 2021, separate meetings with other agencies are also planned. | The process of testing and correcting the shortcomings of the draft Public Investment Management Manual has already been completed. The draft manual is currently being finalized. |  | • The draft Public Investment Management Manual has been tested and shortcomings have been identified | 2021 | Completed |  |  |  | WB
|  | 46.3․ Review and approval of the Public Investment Management Manual |  |  | December, 2020 | December, 2021 | December, 2022 | The Public Investment Management Manual is approved by the RA Government | 1․ As a result of the discussions on the project, as well as the experimental work, it was necessary to amend the Manual. Relevant work is currently underway in the direction of the latter, with the aim of creating an effective system for multifactorial evaluation of public investment programs, based on which the cross-sectoral priorities of those programs are determined. 2. Work has been underway for about 6 months to review the manual, taking into account the sequential implementation of all stages and components of the test, summarizing the results, and making appropriate amendments. The final summarization of the manual is planned to be held by 2nd ten days of Decemeber, 2021 During the testing of the manual, shortcomings were identified, which are being addressed, in particular:  During the testing of the public investment management manual, there was a need to create a legal basis for the introduction of a public investment management system. As a result the RA Prime Minister draft decision "On approving the Procedure for Identifying, elaborating and Evaluating and Determining Priorities of Public Investment Programs in the Republic of Armenia, Methodology for Evaluating Public Investment Programs, and Model form for Elaboration and Evaluation of Public Investment Program" has been elaborated. (hereinafter the Draft).  It is necessary to carry out harmonization and compliance of legislation and legal acts related to the introduction of public investment management system.  In addition to the single Public Investment Management Manual, it is necessary to develop brief methodological manuals / guides for each stage of the Public Investment management process, which will be useful to both public and private sector representatives.  Ensuring the involvement of relevant units of ministries, including financial departments, in training / retraining processes and the continuity of these courses  Establishment of relevant professional sectoral target groups to promote the effective implementation of public investment and to ensure the public investment management process.  In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the performance of statistical work aimed at increasing the accountability of public investments within the framework of the manual. | Within the framework of the introduction of a public investment management system the RA Prime Minister Decree N 472-L, dated May 4, 2021 "On Approving Procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project" (PIM decision) was elaborated and adopted. Based on the considerations presented as a result of the manual testing, the PIM manual was also amended in parallel Work is currently underway to finalize the revision of the Public Investment Management Manual the manual was reviewed once again together with the World Bank experts and finalized, appropriate adjustments have been made, taking into account the results of the sequential implementation of all stages and components of the practical piloting of the manual as well as the provisions and procedure provided by the PIM decision | Given that work is currently being done for the annulment of the RA Prime Minister's decision N 472- Լ, dated May 4, 2021 and its regulations, we consider it appropriate to amend the "Public Investment Management Manual" in the framework of the latter and bring it into line with the provisions and procedure of the decision to be adopted. Currently, work is underway to finalize the revision of the public investment management manual, taking into account the results of the sequential implementation of all stages and components of the practical testing of the manual. |  |  | In progress | 1. Finalization of revision of the public investment management manual. 2. Circulation of the manual, summarization and submission of comments and suggestions. |  |  | WB
| 47. Capacity building of public investment specialists | 47․1․ Elaboration of a capacity building program for public investment specialists for the training on public investment management manual | MoE | - | December, 2020 | December, 2022 |  | The Public Investment Management Manual is approved by the RA Government | 1․In the framework of the introduction of the Public Investment Management System, during the first half of 2020 seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy After the seminars / trainings aimed at capacity building, the needs of public investment specialists were assessed in the framework of which the needs of specialists have been identified, particularly in the component of financial calculations. In this regard, the RA Ministry of Finance is expected to be more actively involved in the implementation of the mentioned event. 2.In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the accountability and statistics of the public investments carried out within the framework of the manual, without which it is possible to record a 70% assessment. 3․in the framework of the introduction of the Public Investment Management System, seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy | 1․ 1․ Within the introduction of the PIM system, as well as in terms of the procedure defined by the PIM decision and completing the Model Form defined by the Decision N 472-Լ, dated May 4, 2021, d 2021, the Public Investment Policy Department of the RA Ministry of Economy conducted workshops and work discussions on capacity building with the participation of representatives of all interested bodies, including local self government bodies according to the agreed program and agenda. In particular, online trainings on public-private partnership with the initiative of the Commercial Law Development Program under the United States Department of Commerce with the participation of relevant bodies (RA Ministry of TAI, RA Ministry of High-Tech Industry, RA Ministry of Education, Science, Culture and Sport, RA MoF, Road Department SNCO, City of Yerevan) Within the framework of the working visit of the World Bank experts to Armenia, a training-workshop was organized on the indicators necessary for the construction of the financial and economic model of public investment programs, calculation mechanisms, in particular, the calculation of the internal rate of economic profitability. | 1․ In the framework of the public investment management system, for the purpose of capacity building, trainings were carried out this year in a format previously agreed upon by the World Bank, the Asian Development Bank and the RA Ministry of Economy, ensuring the continuity of capacity building. 2․ A total of 100 public sector professionals (RA MoH, RA MoESCS , MoES, MoHighTech, MoF and MoE) were trained and capacity building workshops were held with them within the framework of the public investment management system. The training activities are continuous in nature and are planned also during 2023. |  |  | In progress | 1. Periodic implementation of capacity building and ensuring continuity 2․ As a result of the held seminar discussions, courses and workshops, finalization of the work on the elaboration of the capacity building program for public sector specialists 3․ Finalization of videos and guidelines on PIM |  |  | WB
|  | 47.2 Capacity building |  |  | 2020-2021 |  | 2022-2023 | The capacity of public investment specialists is sufficient | Within the framework of the introduction of the Public Investment Management System, the testing of the Public Investment Management Manual, activities aimed at developing the capacity and training of public sector specialists are carried out, which are of a continuous nature and are envisaged during 2021. Taking into account the working meetings held in the agencies, as well as the subsequent discussions, responsible representatives from each agency are invited to participate in the professional training courses. Phase 1․ 1 A total of 40 public sector specialists (RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office) were trained and capacity building workshops were held with them within the framework of introduction of public investment management system. 2․ During the first half of 2020, 16 seminars-discussions / workshops were organized jointly with the RA Ministry of Economy and WB  This year from January 28 to February 14, 6 working discussions were held in the RA Ministry of Economy with the representatives of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI on the completion of a common model form (hereinafter referred to as the Model Form) quality assessment concept of the investment project in the framework of the introduction of the Public Investment Management System From February 24 to 28, this year 5 seminars-discussions on new initiatives completed by the relevant agencies related to the Model form within the framework introduction of the Public Investment Management System were organized and held in the WB Armenia Office with the participation of the representatives of the interested state agencies, in particular, RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office  On March 12 and 13, 2020, 2 video conferences were held at the RA Ministry of Economy with the participation of the WB experts, with the participation of the employees of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, with the WB experts.  On June 23, 2020 organizing 1 online workshop on economic and financial evaluation of investment projects for the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA MTAI with the initiative of the RA MoE and by the WB experts  Conducting a separate remote discussion with the representative of the RA Ministry of Health, during which the indicators of the investment project provided by the RA Ministry of Health were observed, as well as they were compared with the indicators of a similar program.  An online discussion was held with the relevant representatives of the Ministry of Education and Science of the Republic of Armenia, within the framework of which the investment projects with a large social component were considered in detail, peculiarities of applying the standards applicable to them and elaboration/drafting of these projects. In this context, within the framework of the already established experience, work is being done on the evaluation criteria of large social components - programs that do not have primary economic benefits, but provide secondary benefits. Phase 2  During the second phase of the manual testing, 18 discussions were held with the involvement of representatives of about 100 public investment sectors, in particular, representatives of the RA TAI the RA TAI Water Committee, the RA MOESCS, the RA Ministry of Emergency Situations and the Ministry of Justice. | 1. In the first half of 2021, a total of 9 meetings, including online, about 120 public sector specialists (representatives of the public administration system, local self-government bodies) were trained, capacity building workshops were held with the latter in the framework of meetings-discussions on the introduction of the PIM system, as well as the awareness of the procedure stipulated by the PIM decision completion of model form. The mentioned meetings-discussions were conducted both online and in the format of local meetings in the sectorial ministries during which detailed presentation on the information related to procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project was presented. 2. In the second half of 2021 around 9 capacity building courses were organized about 120 public sector specialists with the participation of representatives of the public administration system ։ 3. Working discussions are regularly held in the RA Ministry of Economy with the participation of the representatives of the sectoral ministries in order to improve the legislative framework of the PIM system. |  |  |  | In progress |  |  |  | WB
| 48. The public investment projects included in the 2023 annual budget are prepared in accordance with the requirements of the defined PIM manual | 48.1. Practical application PIM manual in the budget process | MoF | MoE | December, 2021 | December, 2022 |  | The public investment projects included in the 2023 approved budget have been developed in accordance with the requirements of the PIM manual | An agreement has been reached with the IMF for assistance, under which work has begun since October, in 2020. and are under discussion. The measure was included in the draft decision of the RA Government on making changes in the decision 1716-L of the RA Government, within which the term was extended for 1 year and corresponding changes have been made in the titles of the target name and result evaluation indicators. The extension of the term of the measure is conditioned by the one-year extension of the implementation period of the measure "46.3 ․ Review and approval of the Public Investment Management Manual, as well as with the deadlines for organizing the budget process. | The report "Public Investment Management an Budget Process" was developed within the framework of IMF support. The observations of the Ministry of Finance on the latter were presented, which are still under discussion. |  |  |  | In progress | After the approval of the public investment management manual, within the budgetary process, in the framework of the methodological guidelines for the preparation of the state budget, requirements for planning capital expenditures in accordance with the requirements of the manual will be defined to the state bodies. |  |  | (GIZ/IMF/ADB/WB/AFD)
| 49.Monitoring of public investment projects | 49.1 Monitoring of public investment projects | MoF | MoE | 2022-2023 |  |  | Published report on the results of the monitoring of public investment projects | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines. | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines. |  |  |  | Not started |  | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and may require external technical assistance, of which no clarity is currently available. | Depending on the course of the event referred to in point 48.1, submit a proposal to revise the timing of the event as needed. | (GIZ/IMF/ADB/WB)
12․FINANCIAL MANAGEMENT IN SELF LOCAL GOVERNMENT BODIES
24. Efficiency of financial management in local self-government bodies | 50. Development of capacities and professional skills of the administrative staff of local self-government bodies | 50.1․ Implementation of public finance management reform program in local self-government bodies | MoF | MoTAI | 2020-2023 |  |  | Study reports | Within the framework of this measure, the work on PFM reforms in local self-government bodies is currently carried out directly by the RA Ministry of Territorial Administration, which is the coordinator of the measure. Harmonization of program budgeting methodologies of community and national level. 2017 Elaboration of a program budgeting training program . Availability of the 2015 PB curriculum. Organizing and holding training on program budgeting methodology, its application and PB awareness for the administrative staff of the local self-government bodies of the enlarged communities in 2014-2020. 2014-2020 Development of competencies and professional skills of the administrative staff of local self-government bodies. Providing technical assistance, advice to financial managers of municipalities, staff members involved in the process of preparing the annual program budget for 2015 to 2020. 2015-2020 Availability of annual program budgets for large communities Providing technical assistance and consulting on community annual program budget development and holding public hearings in 52 enlarged communities for 2016 to 2020. 2016-2020 Existence of brief program budgets for the mentioned years for all the communities enlarged during those years. Providing technical assistance and consulting on quarterly and annual monitoring and evaluation of community annual program budget plans in enlarged communities for 2016 to 2020 . 2016-2020 Availability of program budget monitoring quarterly and annual plans for all communities enlarged during those years. Implementation of the "Citizen Participation in Community Budgeting" program in 10 pilot communities within the framework of the regional program funded by the Eastern Partnership Regional Public Administration Reform Fund. 2018-2020 May Development of competencies and professional skills of the administrative staff of local self-government bodies with knowledge and experience necessary for the further application of active methods of civic participation in budgeting processes. -Elaboration and publication of a "Participation of Residents in the Local Budgeting Process" participatory budgeting manual. June, 2019-2020 the manual is available Elaboration of "Gender-sensitive budgeting at the community level", GIZ, UNDP 2019-2020 the draft manual is available | 1. Summary of the results of the "baseline study of the current system of internal financial control in local self-government bodies" conducted in September-December, 2020 and discussion of further steps 2. PB budget approval in 52 unified communities in 2022, budget drafting in PB format, public discussions on them 3. Integration of gender sensitive budgeting approaches in 20 community budgets 4. Study on the application of APSAS in 52 merged communities, as well as the applicability of the APSAS developed handbook for communities 5. Summary of the results of the "baseline study of the current status of public investment management in local self-government bodies" conducted in September-December, 2020 and discussion of further steps | 1. Assistance is provided to 10 enlarged communities of RA for the purpose of transition to the APSAS 2. The program budgeting methodology in the local self-government system was revised and aligned with the methodology introduced at the state level. A legal package was elaborated to make the budget program classification mandatory in the local self-government system. 3. The methodological instructions of the RA 2023-2025 Medium-Term Expenditure Framework of local self-government bodies were developed and transferred to the RA communities as a guide. 4. A guide for the organization and implementation of participatory budgeting processes in the communities was elaborated and transferred to the RA communities | 1. Assistance to 10 enlarged communities of RA for transition to the APSAS 2. Review of the methodology of program budgeting in the local self-government system. Elaboration of legal package for PB introduction in communities. 3. Elaboration of methodological instructions of the RA 2023-2025 Medium-Term Expenditure Framework of local self-government bodies. 4. Elaboration of a guide for the organization and implementation of participatory budgeting processes in the RA communities. |  | In progress | 1. Piloting a consolidation methodology in 2 communities 2. Legally mandatory introduction of the program classification of the budget in the system of local self-government 3. Elaboration of MTEF in communities every year 4. Full introduction of participatory budgeting in RA communities |  |  | GIZ
Transparent and participatory budget process plans at the local self government bodies
|  | 50.2․ Monitoring of the public financial management reform program in local self-government bodies and full implementation | [5 empty] | Employees of local self government bodies capable of implementing public finance management reforms | Elaboration of an IPSAS-based accounting manual based on International Public Sector Accounting Standards. Providing the manual to all enlarged communities and interested structures. Preliminary study of the use of IPSAS-based accounting manual and standards in enlarged communities, identification of gaps and submission of recommendations for improving the system operation. Study of the preliminary situation of the property management process of enlarged communities, identification of gaps and submission of proposals for the improvement of the system. Preliminary study of the functions, rights and scope of responsibilities of the administrative heads of the settlements of the enlarged communities and submission of proposals for the improvement of the activities. | 1․ Implementation of capacity building activities for the preparation of community budgets, public discussion, approval, implementation and approval of reports in 52 enlarged communities in the PB format including through online training modules (placed in community management information system) have continued. 2․Elaboration of a database of emergency interventions developed for the administrative leaders of 52 unified communities, based on real experience and cases have continued. 3․Implementation of capacity building activities for the implementation of APSAS in the communities, including through online training modules (placed in community management information system) have continued 4․Elaboration and piloting of consolidated financial reporting methodologies continued in 2 advanced enlarged communities have continued | 1. With the technical support of the GIZ "Good governance for local development" program for the purpose of developing the abilities of local self-government bodies employees in the program classification of the budget in the local self-government system, assistance was provided to 37 of the current 64 enlarged communities of RA in the development of program budgets, summary budgets, as well as gender-sensitive budgets. 2. In order to effectively elaborate the 2023-2025 mid-term expenditure framework of RA local self-government bodies, trainings were organized for 179 representatives of all 71 communities of RA. 3. A pilot introduction of participatory budgeting in the communities is being implemented in three enlarged communities of RA: Abovyan, Armavir and Ashtarak. |  |  | In progress | Support communities as needed 3. After analyzing the results of the pilot introduction of participatory budgeting in three communities of RA, continue th introduction of the mechanism in other communities of RA |  |  | GIZ
13. EXTERNAL CONTROL AND LEGISLATIVE CONTROL
25. Control of the financial-budgetary sphere by the National Assembly | 51. Provide external control (Reports of annual budget and AC ) | 51.1 Review of annual draft budgets | NA (with agreement) | AC (with agreement) | 2019-2023 |  |  | · More effective study of the draft annual budget | In the RA NA Standing Committees and their joint sittings, the preliminary version of the RA 2021 state budget and later on the Draft was discussed | The RA NA Standing Committee on Financial-Credit and Budgetary Affairs in the joint sittings with the sectoral committees of the National Assembly, later also in the sittings of the National Assembly, discussed the RA 2022 the draft state budget. | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs discussed the draft of the 2023 state budget of the Republic of Armenia in joint sessions with the sectoral committees of the National Assembly, later also in the sessions of the National Assembly. |  | Activities for 2020 and 2021 are carried out | It is a periodic process | During 2023, discussions of the preliminary version of the RA 2023 state budget, and later also of the draft, are planned in the standing committees of the RA National Assembly and their joint sessions. 2023թ․ ընթացքում ՀՀ Աժ մշտական հանձնաժողովներում և նրանց համատեղ նիստերում նախատեսվում են ՀՀ 2024 թվականի պետական բյուջեի նախնական տարբերակի, իսկ հետագայում նաև Նախագծի քննարկումներ։
|  | 51.2 Study of the annual report on the execution of the state budget and AC conclusion on the latter and organizing hearings with audited state bodies | [5 empty] | · More Effective Study of AC reports on annual financial statements | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2020 state budget execution process. The monitoring was carried out on the basis of inquiries from the Budget Office commission, each month, through the study and analysis of references with comparative analysis. • The annual report on the execution of the RA 2019 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly. • studied the references provided by the Government on the execution of the quarterly, semi-annual and nine months of the state budget of the Republic of Armenia for 2020 (also discussed at the sitting of the commission), as well as 28 current conclusions of the Audit Chamber on the execution of the first quarter semi-annual of the state budget of the Republic of Armenia 2020, • cooperates with non-governmental organizations ։ | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2021 state budget execution process. The monitoring was carried out on the basis of the study և analysis of the references with the comparative analysis obtained from the Budget Office, each month, The budget office has prepared and provided to the Commission references with comparative analysis on the collection of state budget revenues of 2021, according to the process of expenditure execution, the RA state debt of 2021 and the main socio-economic indicators • the annual report on the execution of the RA 2020 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly, • studied the references on the execution of the first quarter and nine months of the state budget of the Republic of Armenia for 2020, as well as first quarter, semi-annual and nine months of the state budget of the Republic of Armenia 2021, • cooperates with non-governmental organizations ։ | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs: • the annual report on the execution of the RA 2021 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly • discussed the information presented by the Government regarding the execution of the state budget for the first quarter, first half and nine months of 2022 • cooperates with non-governmental and international organizations • monitored the 2022 state budget execution process. The monitoring was carried out based on the study and analysis of the references with the comparative analysis obtained from the Budget Office, each month The budget office has prepared and provided to the Committee references with comparative analysis on the collection of state budget revenues of 2018-2022, the process of 2022 expenditure execution, the RA state debt for 2020-2022 and the main socio-economic indicators | • Establishment of a Subcommittee on Audit Issues in the Composition of the NA Standing Committee on Financial-Credit and Budgetary Affairs • Study of Annual report on the execution of the state budget for 2021 and the AC opinion on the latter. | Activities for 2021 are carried out | It is a periodic process | During 2023 the RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • will discuss the annual report on the execution of the RA 2022 state budget at the joint sittings of the sectoral committees of the National Assembly, and later on at the session of the National Assembly • will continue monitoring the 2023 state budget execution process. The monitoring will be carried out based on the study and analysis of the references with the comparative analysis obtained from the Budget Office, each month, • will study the references submitted by the RA Government on the execution of the first quarter, first half and nine months of the state budget of the Republic of Armenia for 2023 and discuss during the sessions of the Committee,
|  | 51.3 Exercising post-audit control by the Committee | [5 empty] | Exercising post-audit control by the Committee | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, which convened 2 sittings during 2020 and studied 36 current conclusions of the Audit Chamber. of which 28 on the execution of the first quarter and semi-annual of the RA 2020 state budget | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, convened 3 sittings during the seventh convocation of the National Assembly, studied 46 current conclusions of the Audit Chamber. During the eighth convocation of Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly convened 2 sittings, studied 32 current conclusions of the Audit Chamber. | The Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly studied 47 current conclusions of the RA Audit Chamber, the conclusion of the annual execution of the RA 2021 state budget, the annual report on the activities of the RA Audit Chamber for 2021, as well as convened 4 sessions together with the standing committees of the National Assembly. where current conclusions are discussed. |  | Activities for 2021 are carried out | It is a periodic process | During 2023 The Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly will study and discuss current conclusions related to the execution of the first quarter and first half of the RA 2023 state budget.
| 52. Capacity building of the Budget Office, NA deputies and experts of committees | 52.1 Institutional-internal capacity building of the budget office | NA (with agreement) | - | 2019-2023 |  |  | The budget office has the necessary tools to carry out its functions | On September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, the 2020-2023 development strategy of the Budget Office of the RA National was approved, according to which in the context of institutional capacity building of the Budget Office it is planned to expand the functions. In particular, 1. Providing information on the observance of fiscal rules defined by the Government in accordance with parts 8.2 and 8.4 of Article 21 of the Law on the Budget System of the Republic of Armenia and Part 7 of Article 5 of the Law of the Republic of Armenia "on Public Debt" 2. Providing information on the inconsistencies, elimination of distortions, implementation of recommendations in the current conclusions submitted by the Audit Chamber to the National Assembly, 3. Providing opinions to the deputies and factions of the National Assembly - the authors of the draft laws on the significant reduction of the state budget revenues or the increase of expenditures 4. Preparation of references on gender sensitivity of state budget expenditures In order to implement the changes defined by the strategy, a legal package of changes has been developed, according to which corresponding changes and additions are envisaged in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly. It was discussed by the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs, the staff of the National Assembly and other specialists. | On September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, the 2020-2023 development strategy of the Budget Office of the RA National was approved. In order to implement the changes defined by the strategy, a legal package of changes has been developed, according to which corresponding changes and additions are envisaged in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly. The package was submitted to the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs for consideration. For capacity building of the budget office staff, the experts participated in professional capacity building courses. | In the framework of the capacity building of the Budget Office, in cooperation and support with the "New Armenia: Modern Parliament" project of the United Nations Development Office, from May 8 to 13, 2022, the coordinating expert of the Budget Office, Gagik Barseghyan, and the expert Ashot Yeghiazaryan, as part of the National Assembly delegation, visited Austria (Vienna). In the framework of the visit, visits were made to the budget sector committee and budget office of the Austrian parliament, the fiscal council, the budget program evaluation office and the supreme audit body. Within the framework of cooperation with the budget offices of other countries, with the support of the “International Republican Institute”, the Budget Office has started to cooperate with the Budget Office of the US Congress. On March 15 and March 30, 2022, remote discussions took place between the budget offices of the National Assembly and the US Congress. During the discussions, the frameworks of the activities of the two offices were presented. There have also been remote discussions with officials of the Organization for Economic Co-operation and Development (OECD) network of independent financial institutions regarding the prospects of cooperation with them. Organization of 2 workshops for the deputies of the National Assembly, their assistants, experts of the faction and experts of the standing committee. Organization of 2 workshops for the deputies of the National Assembly, their assistants, experts of the faction and experts of the Financial-Credit and Budgetary Affairs standing committee. | • Approval of the Development Strategy for 2020-2023 of the NA Budget Office |  | In progress | In the context of capacity building of the budget office, cooperation with the "New Armenia: Modern Parliament" program of the United Nations Development Office will continue, and a new program will be launched with the support of the USAID. Within the framework of the Organization for Economic Co-operation and Development (OECD) network of independent financial institutions, there is an agreement to hold a teleconference with the Irish Parliamentary Budget Office.
|  | 52.2 Capacity building of NA deputies and experts of committees |  |  | 2020-2023 |  |  | The NA deputies and the experts of the committees effectively carry out the study of the draft annual budget, as well as the control over the execution of the state budget |  | The Budget Office, within the framework of its continuous capacity building function of the National Assembly, organized 2 workshops on budget process of the Republic of Armenia, program and gender-sensitive budgeting for NA deputies, their assistants, factions’ experts, and experts of financial and budgetary supervision standing committee. | During 2022 two workshops were held at the initiative of the NA Standing Committee on Financial-Credit and Budgetary Affairs and the NA Budgetary Office and with the support of the UN Development Program "Modern Parliament for Modern Armenia" program regarding RA budget process, programmatic, SDG and gender sensitive budgeting, strategic planning. The number of members was 59, including members of the National Assembly, experts of the National Assembly's standing committees and factions, employees of the National Assembly's staff. During the workshop, Gagik Barseghyan, coordinating expert of the budget office of the National Assembly, and Ashot Yeghiazaryan, expert, made presentations. | • Organization of 2 workshops for NA deputies, their assistants, factions’ experts, and experts o fStanding Committee on Financial-Credit and Budgetary Affairs |  | In progress | The Budget Office of the RA National Assembly, in the framework of its continuous capacity building function of the National Assembly, envisages seminars, workshops on public finance management, including program budgeting and gender-sensitive budgeting for NA deputies, their assistants, NA staff, standing committees and factions.
26. Independence of the Audit Chamber and external audit of the government's annual financial statements | 53. Defining and implementing 2020-2023 strategic goals of Audit Chamber ․ | 53.1 Strategy of the RA Audit Chamber and elaboration and approval of action plan for its implementation | AC (by agreement) | - | 2019-2020 |  |  | Audit Chamber 2020-2023 ․ Strategy and Action Plan Approved in accordance with ISSAI | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop and approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation. The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed (basis RA Audit Chamber Decision 150-Լ, dated August 7, 2020). | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop and approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation. The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed (basis RA Audit Chamber Decision 150-Լ, dated August 7, 2020). | There were also remote discussions with the representatives of the network of independent financial institutions of the Organization for Economic Co-operation and Development (OECD) regarding the perspectives of cooperation with them. | • Approval of the 2020-2023 strategic development plan and the program of measures for its implementation (Resolution N 150-L of the RA Audit Chamber, dated August 7, 2020) | 2020 | Completed
|  | 53.2 implementation of measures approved by the Audit Chamber strategy for 2020-2023 |  |  | 2020-2023 |  |  | The objectives set by the strategy are implemented in accordance with the defined schedule | The Strategic Development Plan of the Audit Chamber of the Republic of Armenia for 2020-2023, the action plan for its implementation approved by the RA Audit Chamber Decision 150-Լ , dated August 7, 2020 includes all the defined indicators. The Audit Chamber for the implementation of indicators, held an online presentation on the strategy for the external and internal stakeholders of the Audit Chamber (including the Ministry of Finance, the National Assembly, donor organizations, partner accounting bodies) on December 20, 2020. | The Strategic Development Plan of the Audit Chamber of the Republic of Armenia for 2020-2023, the action plan for its implementation approved by the RA Audit Chamber Decision 150-Լ , dated August 7, 2020 includes all the defined indicators. The Audit Chamber for the implementation of indicators, held an online presentation on the strategy for the external and internal stakeholders of the Audit Chamber (including the Ministry of Finance, the National Assembly, donor organizations and partner accounting bodies) on December 20, 2020. Within the framework of the implementation of the Strategic Development Plan, the following activities were carried out during the reporting period with the support of the SIGMA Program: 1) The package of amendments to the articles related to the RA Audit Chamber in the RA Constitution and the RA Law “On Audit Chamber” has been developed, which was officially sent to the RA National Assembly by the RA Audit Chamber On October 7, 2021 and the RA Government, 2) discussions on the structure of the communication strategy of AC and preparations for elaboration were carried out: with the support of the Swedish National Audit Office - 1) 25 employees were trained on "Performance Accounting", 2) Elaboration of the manual for the performance audit of the AC has started. With the support of the United Nations Development Program (UNDP), three experts (qualified auditors) and one IT specialist were involved in the audits of the Audit Chamber. With the joint support of the US Government Accountability Office (GAO) and USAID: 1) Design works of the quality management system of the AC were carried out, 2) Arrangements have been made to modernize the auditing planning process. In order to monitor the implementation of the above measures, the Audit Chamber conducts semi-annual online meetings on the implementation of the strategy with external stakeholders assisting the Audit Chamber (including donor organizations, partner audit bodies). | In the reporting period the Audit Chamber has continued to actively realize the RA Audit Chamber Strategic Development Plan for 2020-2023 and the action plan for its implementation approved by the RA Audit Chamber Decision 150-Լ , dated August 7, 2020. In particular, by the Order of the Chairman of the RA Audit Chamber No. 165-A, dated April 26, 2022, the 2022 action plan ensuring Audit Chamber Strategic Development Plan for 2020-2023, which sets out performance indicators, timelines, responsibilities and sources of support for the planned actions According to the above plan, the following measures were implemented during the reporting period: 1. A package of legal improvements was elaborated and approved, in particular: 1.1 The concept of legal improvement of the field of RA external state accounting was elaborated and approved by the AC Resolution No. 187-L, dated September 14, 2022. 1.2 On the basis of the concept, a legislative package of constitutional articles on the Audit Chamber and legal reforms of the RA Law on AC was elaborated, which was submitted to the RA National Assembly and the RA Government. 1.3 With the support of the EU/OECD SIGMA project, the communication strategy project of the Audit Chamber was elaborated. 2. With the expert support of the US Supreme Audit Chamber. 2.1 "The methodology for the creation of the quality management system in the Audit Chamber and the implementation of the function of the quality management system" was elaborated and approved by the Audit Chamber Decision N145-L, dated June 30. 2.2 Materials for the training of trainers program on the principles of the Code of Ethics were elaborated. 2.3 The procedure for monitoring the practical application of the code of ethics was elaborated and approved. 3. With the expert support of the National Audit Office of Sweden, 3.1 "Performance Audit Methodology" was elaborated and approved by the Audit Chamber Decision No. 146-L dated June 30, 3.2 With the support of Swedish experts, 23 auditors were trained to introduce the Performance Audit methodology, 3.3 a workshop was held with the participation of representatives of 19 AC management staff 4. The risk-based methodology, which is the basis for the preparation of the AC action plan, was reviewed, providing grounds for increased coverage of performance audits in the 2023 action plan. 4. With the support of the MAP project of the United Nations Development Program, 31 employees of the Audit Chamber participated in the courses designed for auditor qualification. 5. With the support of the MAP project of the United Nations Development Program: 5.1 31 employees of the Audit Chamber participated in two rounds of auditor qualification courses. As of December 30, 2022, at least 26 employees have passed two or more qualifying exams. One employee was qualified in the reporting year. 5.2 7 employees of the Chamber of Accounts were involved in data analytics courses. |  |  | In progress | In the near future it is planned: 1. Adoption of the package of legal improvements by the RA NA 2. Improving the methodology of financial and compliance audits 3. Increasing the number of performance audits based on the performance audit methodology 5. Introduction of quality management system 6. Communication strategy approval 7. Improving the accounting planning process, 8. Providing continuous development program with auditor qualification courses: 9. Monitoring of the practical application of the Code of 10. Other measures conditioned by the legal reforms: The success of activities 2-10 mostly depends on 1. measures from the successful process of adoption of legal reforms. 54. AC staff capacity building and professional skills improvement |  |  | (GIZ)
| 54. Capacity building of AC staff and Improving professional skills | 54.1 Development and approval of the capacity building program of the AC staff |  |  | 2022-2023 |  |  | AC auditors perform audits in accordance with ISSAI standards | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFC strategy. | The measure is included in the Strategic Development Plan of the RA Audit Chamber for 2020-2023, and the plan of measures for the implementation of the Strategic Development Plan defines the implementation dates envisaged by the PFMS strategy. | 54.1 the measure is included in the 2020-2023 Strategic Development Plan of the RA Audit Chamber, and the plan of measures for the implementation of the strategic development program defines the dates for the implementation of the measure provided by the PFM system strategy: |  |  | In progress | Elaboration and implementation of the human resources function of the RAAudi Chambe, its strategy, mostly depends on the adoption of the envisaged package of legal reforms. |  |  | (GIZ)
|  | 54.2 Capacity building of AC staff and improvement of professional skills | [5 empty] | Qualified External Auditors | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFC strategy. There are preliminary agreements for providing external support to this measure | The measure is included in the Strategic Development Plan of the RA Audit Chamber for 2020-2023, and the plan of measures for the implementation of the Strategic Development Plan defines the implementation dates envisaged by the PFMS strategy. In the reporting year, with the support of GIZ, 55 employees participated in the auditor qualification course "Fundamentals of Financial Accounting" . | 54.2 the measure is also included in the 2020-2023 Strategic Development Plan of the RA Audit Chamber, and the plan of measures for the implementation of the strategic development program defines the dates for the implementation of the measure provided by the PFM system strategy |  |  | In progress |  |  |  | (GIZ)
14. GOVERNMENT FINANCIAL MANAGEMENT INFORMATION SYSTEM (GFMIS)
27. Government Financial Management Information System (GFMIS) | 55. Introduction of the main components of the GFMIS - Phase 1 | 55.1 Acquirement of consulting services for the revision of GFMIS tender documents | MoF | MoHTI | December, 2020 |  |  | The tender processes were organized and carried out for purchasing consulting support services for GFMIS introduction. | On May 7, 2020 the first stage of the two-stage procurement process for the selection of a consultant assisting the Ministry of Finance in the process of introduction of the GFMIS was organized. 7 organizations applied for pre-qualification, of which 5 became pre-qualified participants, "Harmony" Foundation, Ernst & Young CJSC, AAM Management Information Consulting Ltd., Deloitte Armenia CSJC, Moore Management Consulting Ltd. Further on, the negotiation phase has started. From now on, the stage of negotiations has begun. On 5․11․2020, the pre-qualified participants were provided the invitation of second phase tender. Deadline for submitting bids is set 25.01.2021 by invitation. and as of that day, one of the 5 pre-qualified organizations, the "Harmony" Foundation, has submitted a bid. The latter's bid is under evaluation. | In January-April, 2021 the results of the two-stage procurement process for the selection of a consultant assisting the MoF in the GFMIS introduction process have been summarized. On 20.04.2021 a contract was signed with the winning company for the provision of consulting services in the framework of the GFMIS introduction program. Within the contract, the elaboration of the report of the first stage of the project introduction defined by the contract terms of reference schedule has started in the framework of which the consultant presented the management manual of the GFMIS introduction program. |  | • A tender was held for the selection of a consultant supporting the Ministry of Finance in the process of introducing the GFMIS: • As a result of the tender, a consultant was selected, with whom a contract was concluded ։ | 2021 | Completed |  |  |  | RF/Mof
|  | 55.2 Organization of GFMIS acquistion |  |  | 2020-2021 |  | 2022-2023 | The complete package of documents for the implementation of the GFMIS tender has been drawn up, the tender has been held | Will be implemented 55.1. after the selection of the Consultant presented by the measure within the established timeframe. | The activities of the second stage of the GFMIS introduction, envisaged by the contract signed with the expert, have started per the business process analysis of all modules/subsystems of the GFMIS, diagnosis, identification/formulation of final business processes, definition of alternatives and elaboration of a terms of reference of the version selected by the MoF. | In 2022, the works of 2.1 and 2.2 sub-phases of the 2nd phase of the introduction of the GFMIS under the contract concluded with the Consultant were carried out due to analysis, diagnostics, and description of business processes of all modules/subsystems of GFMIS. Based on the latter, the Consultant elaborated the concept of the introduction of the GFMIS and the optimization of the main modules of the GFMIS. In November-December 2022, the Ministry of Finance initiated the process of involving an international organization/expert for the purpose of expert evaluation of the works carried out in the direction of the introduction of the GFMIS. As a result, an international expert was selected: "PricewaterhouseCoopers" company, Deputy Director for State Reforms and Infrastructure Development Sh. Mukund, to whom the package of documents summarizing the works carried out in the direction of the introduction of the GFMIS were transferred. | The works of the 1st and 2nd sub-phases of the 2nd phase of the introduction of the GFMIS provided for by the contract concluded with the expert, have been completed. The concept of the introduction of the GFMIS and the proposals for the optimization of the main modules of the GFMIS were elaborated and adopted. |  | In progress | As a result of summarizing the work of the 2nd 2.3 sub-phase provided by the contract concluded with the consultant, the terms of reference necessary for the procurement of the software of the modules included in the GFMIS will be elaborated on the basis of which the purchase process will start. |  |  | RF/Mof
| 56. Introduction of the main components of the GFMIS - Phase 2 | 56.1 Start of GFMIS implementation program elaboration |  |  | December, 2022 |  | December 2023 | GFMIS implementation program developed by the company recognized as the winner of the tender within the timeframe set in the ToR. | [5 empty] | Not started |  |  |  | WRF/Mof
|  | 56.2 Training of GFMIS users |  |  | December, 2022 |  | December 2023 | GFMIS users are trained | [9 empty] | RF/Mof

## Used terms
Terms used in the column "Status" of the Report
Completed | The measure is completely done.
In Progress | The works on the implementation of the measure have started,considered to be in progress. The works envisaged within the framework of the measure have not been completed yet.
Not started | The works on the implementation of the measure have not started yet, mainly due to depending on the results of other measures.
It is a periodic process | The actions defined by the measure are periodic processes, which are an integral part of the ongoing functions of the state body. The results of these measures do not have a clear beginning or end.
Not started | No information was provided on the progress of the measure.
Risky | There are risks associated with the on time implemention of the mesaure.