## Лист1
REPORT On the progress of PFMSR Action plan measures to be implemented in 2019-2023 and On the implementation of activities in the first half of 2020
Sector/component | Target | Measures | Performer | Co-performer |  | Outcome evaluation indicators | Relation to PEFA Performance Indicators | Activity Implementation Risks | Risk Mitigation Actions | Reference to Relevant Articles of the RA Government Programme | Source and amount of funding | The course of activities and actions /achievements performed | Actual execution date | Status | Next steps (actions) to be taken | Problems related to the implementation of the measure and Risks. | Risk management measures | The development partner organization supporting the implementation of the measure
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1․ FORECAST OF THE MAIN MACROECONOMIC AND BUDGET INDICATORS, FINANCIAL RISK ACCOUNTABILITY
1. Forecast of macroeconomic and budget indicators | 1. Elaboration of final versions of the model (s), introduction in the MoF and full operation | 1.1 Elaboration of final versions of the DSGE model (s) | MoF | - | December, 2019 | Availability of up-to-date tools for fiscal policy analysis and medium-term macroeconomic forecasts | PI-14 | Risks associated with technical supply (software, high-capacity computers); Risks associated with localization of models Loss of trained personnel and lack of specialists with relevant qualification | • Technical reequipment • Training of the personnel (through attraction of new technical assistance if necessary) and recruitment of new, qualified specialists; * Encouragement of staff | - | To be implemented in the framework of technical support | DSGE model is elaborated | December, 2019 | Completed
|  | 1.2 Introduction of DSGE model (s) and full operation |  |  | 2020-2023 | Introduction of new tools and use in the budget process, more comprehensive and ccurate estimates and analysis of the impact of fiscal policy on the economy և accurate estimates և analysis |  |  |  |  | No additional funding is required (to be implemented in the framework of technical support if necessary) | DSGE model was tested and finalized Preliminary versions of the relevant documents have been developed. Discussions on the development of a working document, elaboration of separate sections were carried out jointly with IMF experts. With the help of the model, the effects of the coronavirus epidemic on the Armenian economy of the multifaceted fiscal measures taken on the were assessed, on the basis of the results, the 2021-2023 MTEF macro-fiscal framework has been drawn up. The preliminary version of the model has already assessed the impact of the tax reforms that came into force this year, as well as other policies (raising the minimum wage, the introduction of a comprehensive health insurance system). |  | In progress | It is envisaged to document the carried out and in progress related analytical-evaluation activity, to elaborate a manual for the use of the model, as well as to elaborate a joint working document of the RA Ministry of Finance and the IMF. It is envisaged to apply the model in the elaboration of the state budget, in the processes of macro-fiscal framework design and impact assessment of fiscal measures. | None |  | IMF
| 2. Assessing the effects of deviations between actual and planned fiscal policies based on macro basis and fiscal rules | 2.1 .Detection of deviations between planned and actually implemented fiscal policy and impact assessment | MoF | - | 2020-2023 | Improved estimates of fiscal risks at the macroeconomic level. |  |  |  |  | No additional funding is required | Activities haven't been carried out to implement the measures |  | Not started | It is planned to carry out fiscal policy monitoring, comparative analysis of actual and planned implemented policies, detection of deviations starting from 2021, after the publication of the official annual figures for 2020. | None |  | IMF
Assessments of the effects of fiscal policy deviations from the planned on the economy
| 3. Ensuring relevant qualified and skilled staff | 3.1. Implementation of measures aimed at raising the qualification of the staff | MoF | - | 2019-2023 | Availability of staff with relevant qualification and skills |  | • Outflow of qualified personnel due to uncompetitive remuneration compared to relevant private sector professionals • Difficulties in recruiting new qualified personnel | • Differentiate between levels and remuneration of policy making units in the MoF of RA and of units requiring technical capacity • Promotion through rewarding and/or in other ways • Collaboration with relevant training institutions |  | To be implemented in the framework of technical support | In connection with the cancellation of previously available courses due to the epidemic in 2020. During the first half of the year, only one employee of the department was trained within the framework of the trainings organized in Vienna (JVI). Employees participated in other available online courses, including regular webinars initiated by JVI. |  | In progress | In case of resumption of trainings by international organizations where the situation after the epidemic is stabilized, during the second half of 2020, the department staff will be trained. | None |  | IMF
· Պարգևատրման և այլ միջոցներով խրախուսում
· Համապատասխան մասնագետներ պատրաստող ուսումնական հաստատությունների հետ համագործակցություն
2 Fiscal risk accountability | 4. Improving the function of fiscal risk assessment | 4․1 Expanding the coverage of fiscal risk assessment, improving the methodology | MoF | - | 2020-2023 | Fiscal risk assessments include an expanded range of fiscal risk sources | PI-10 | Possible failure in collaboration with relevant state agencies or other authorized bodies responsible for exercise of fiscal risk assessment function | Continuous application of the current methodology used for fiscal risk assessment on going working meetings with relevant state governance and other authorized bodies with the aim of implementation of fiscal risk management road map | Chapter 8, Article 8.2 , paragraphs 6 and 7 | To be implemented in the framework of technical assistance | Fiscal risk assessments related to the activities of 20 organizations operating in the infrastructure (energy, transport, water economy) sectors were carried out, which also included the analysis of contingent liabilities arising from the contracts of public-private partnership companies. The latter were reflected in the document RA 2021-2023 MTEF (link: http://www.minfin.am/en/page/petakan_mijnazhamket_tsakhseri_tsragre/). At the same time, the work on expanding the scope of assessment of fiscal risk sources continues. |  | In progress | The range of sources of fiscal risk assessment will continue to expand in the second half of 2020. | None |  | ADB
[6 empty] | Improved fiscal risk methodology | [5 empty] | With the support of ADB Consultants, RA Government draft decision "On approving the methodology for calculating and evaluating the contractual obligations of the Republic of Armenia on n terms of public-private partnership projects"has been elaborated and submitted to the Office of the RA Prime Minister. |  |  | After the approval of the RA Government draft decision "On approving the methodology for calculating and evaluating the contractual obligations of the Republic of Armenia in terms of public-private partnership projects", guidelines will be developed for the implementation of the function. |  |  | ADB/IMF
| 5. Development of analytical skills of fiscal risk assessment specialists | 5․1 Capacity building | MoF | - |  | Specialists with improved analytical skills in assessing fiscal risks |  | Possible failure in providing the full range of technical assistance needed | Proceed with the application of the methodology used for fiscal risk assessment |  |  | 2020 During the first half of the year, one employee of the department was trained within the framework of the courses organized in Vienna (JVI). The employees also participated in the trainings organized by the World Bank in Yerevan. In addition, training is provided as part of ADB's consulting work. |  |  | Improving the capacity of specialists performing PPP projects contingency analysis in the scope of IMF and ADB technical assistance specialists to perform PPP contingency analysis. |  |  | ADB/IMF
2․ STATE REVENUE POLICY, TAX ADMINISTRATION
3. State Revenue Policy | 6. Assessing the needs of the tax environment based on the economic development priorities and opportunities | 6․1 Outline directions for further tax system reforms based on economic development priorities and opportunities | MoE | HTIM, EM, TAIM | May, 2020 | The directions of further reforms of the tax system are outlined | PI-3, PI-19, PI-20 | Improper evaluation of tax environment requirements based on the economic development priorities and possibilities | Regular review and analysis with aim of specifying the policy directions driven by the changes of the environment | Chapter 8, Point 8.1 , paragraph 1 | No additional funding is required | . The draft envisages the introduction of a modern technological procedure (Trade-in system) for the sale of cars between official representations of car manufacturers and individuals։ 2. The draft aims to solve the problem of economic entities arising due to the wording of Article 267, Part 5, Clause 2 of the Tax Code (sectors not considered entities of micro-enterprises) by aligning them with the ICT classifier, as a result of which the predictability of being considered micro-enterprises will increase 3․ The draft envisages applying the amount of natural losses of construction goods to be deducted from the gross income for the purpose of determining the tax base in the case of economic entities engaged in the import or sale of construction materials. 4․ The decision envisages measures aimed at simplifying tax payments, as a result of which the return of funds to the taxpayers' joint accounts will be accelerated, tax liability calculation procedures will be simplified, time will be reduced, additional electronic services will be provided to taxpayers to carry out their operations through mobile devices, etc. |  | In progress | After the discussion with the stakeholders, the draft will be submitted to the RA Government for consideration in accordance with the established procedure.
| 7. Reducing the scope of application of tax benefits | 7.1 Elaboration of RA Law "On Making amendments and supplements to the RA Tax Code" | MoE | - | 2020-2023 | Low-efficiency, non-targeted tax benefits are eliminated |  | Incomplete delivery of results expected from the acceptance of changes of the economic environment | Regular assessments and review with the aim of specification of policy directions determined by the changes of the environment | Chapter 8, point 8.1, paragraph 2 | No additional funding is required | An agreement has been reached with ADB to receive technical assistance for the implementation of the activities in this area. |  |  | It is envisaged that the activities will be completed on the 3rd ten days of June, 2022. | None |  | IMF/ADB
| 8․ Review of turnover tax burden | 8․1 Elaboration of RA Law "On Making amendments and supplements to the RA Tax Code" | MoE | - | 2020-2023 | As a result of the conducted studies, the turnover tax burden has been revised |  | Incomplete delivery of results expected from the acceptance of changes of the economic environment | Regular assessments and review for specification of policy directions driven by, by changes of the environment | Chapter 8, point 8.1, paragraph 1 | No additional funding is required | An agreement has been reached with ADB to receive technical assistance for the implementation of the activities in this area. |  |  | It is envisaged that the activities will be completed on the 3rd ten days of June, 2022. | None |  | IMF/ADB
| 9․ Settlement of issues related to the documentation of transactions for the sale of agricultural products | 9․1 Elaboration of RA Law "On Making amendments and supplements to the Tax Code of the Republic of Armenia" | MoE | - | December, 2021 | Problems with documenting transactions are settled |  | The results expected from the acceptance of changes of the economic environment are not fully ensured | Regular assessments and review with the aim of specification of policy directions determined by changes of the environment | Chapter 8, point 8.1, paragraph 1, paragraph 13 | No additional funding is required | Suggestions for resolving issues related to the documentation of transactions in the sale of agricultural products have already been developed and will be submitted for discussion in the near future. |  | In progress | It is envisaged that the activities will be completed on the 3rd ten days of June, 2022. | None
| 10. Equivalent taxation on visible wealth or property | 9․1 Elaboration of RA Law "On Making amendments and supplements to the Tax Code of the Republic of Armenia" | MoE | - | December, 2020 | Visible wealth or property is taxed adequately |  | Incomplete delivery of results expected from the acceptance of changes of the economic environment | Regular assessment and analysis with the aim specification of policy directions determined by changes of the environment | Chapter 8, point 8.1, paragraph 3 | No additional funding is required | The mentioned measured is already implemented. In particular, on June 25, 2020, the RA National Assembly adopted the RA Law "On Making Amendments and Supplements to the Tax Code of the Republic of Armenia" aimed at reviewing the real estate tax system. | June 25, 2020 | Completed
| 11․ Providing legal basis for the introduction of an income declaration system based on the current economic motives | 11․1 Elaboration of RA Law "On Making amendments and supplements to the RA Tax Code" | MoF | - | December, 2021 | Legal basis for the introduction of an income declaration system based on the current economic motives is ensured |  | The results expected from the acceptance of changes of the economic environment are not fully ensured | Regular review and analysis with the aim of specification of policy directions determined by changes of the environment | Chapter 8, point 8.1, paragraph 3 | No additional funding is required | The action plan required for the introduction of the personal income declaration system was approved by the RA Minister of Finnce Order N 104-Լ, dated April 6, 2020 Studies of the international experience of the personal income declaration system were carried out and the results were presented for discussion, The RA draft law “On Making Amendments and Supplements to the RA Tax Code” aimed at the introduction of personal income declaration system has been elaborated |  | In progress | The works are expected to be completed in the 3rd ten days of June 2021. | None
4. Transparency and compliance of revenue administration | 12. Assessment of tax potential and gap | 12.1. Assessing the tax potential gap for the three major types of taxes (VAT, profit tax, income tax) | MoF | - | 2019-2023 | Availability of tax potential gap assessment methodology for three major types of taxes (VAT, profit tax, income tax); Tax potential gap estimates for the three major types of taxes (VAT, profit tax, income tax) | - | Unavailability of information necessary for assessing the tax gap | Legal regulation of the procedure related to obtaining information from relevant agencies | Chapter 8, point 8.1, paragraph 6 | To be implemented in the scope of technical assistance | In the framework of tax potential gap assessment, the RA Ministry of Finance, in cooperation with the RA State Revenue Committee and the RA Central Bank, assessed the tax potential of the Republic of Armenia, the results of which were discussed with the RA Deputy Prime Minister in December 2019. Based on this, agreements were reached and the RA State Revenue Committee was instructed to conduct a study and present its assessments on the tax potential. During the first half of 2020, the RA MoF did not carry out any work on assessing the tax potential gap. Further activity on assessing the tax potential gap depends on the progress of the work to be carried out by the RA State Revenue Committee. |  | It is a periodic process | It has been an ongoing process since 2020. It is envisaged to have estimates of the tax potential breakthrough for the three major types of taxes (VAT, profit tax, income tax) by December, 2020. | Further work on assessing the tax potential gap depends on the progress of the work to be carried out by the RA SRC | Work with the RA SRC to obtain the required data in a timely manner.
| 13․ Publication of information on tax refunds from the budget to ensure transparency of public finances | 13․1 Publication of data on tax refunds from the state budget on a quarterly basis | SRC | - | 2019-2023 | Relevant published information | PI-9 | The information on taxes refunded from the budget is not published in a timely manner | Setting the precise timeframes of implementation | Chapter 3, the last paragraph of point 3.2, | No additional funding is required | In accordance with the RA SRC Chairman order N 267-A, dated 17.04.2019, the relevant information is published on a monthly basis in the RA SRC official website (http://www.petekamutner.am) in the section "Tax Information", sub-section "Tax Statistics" , part "Tax Statistics data" |  | It is a periodic process | Publication of relevant information on a monthly basis. | None
| 14․ Continuous reduction of the shadow economy, exclusion of privileged taxpayers | 14․1 Enhancing possibility to third party information effective use | SRC | - | 2019-2023 | Reducing the tax shadow Exclusion of taxpayers with privileged status, creating an equal tax environment for all taxpayers | PI -3, PI-19, PI-20 | Operational and financial | Cooperation with public administration bodies of the Republic of Armenia and implementation of activities not prohibited by the RA legislation with the aim of attracting funding | Chapter 8, point 8.1, paragraph 6 |  | 1. In order to ensure access to information to the tax authority from third parties on real estate, their owners, property rights, restrictions, limitations and their changes the RA Government draft decision "On making changes and additions to the RA Government decision N 388-N, dated April 6, 2017 " has been elaborated and sirculated since December, 2019. Taking into account the RA MoF standpoint on the draft that these changes should be initiated by drafting the decision of the RA Government Decision "On Making Amendments to the Decision No. 1337-N, dated October 5, 2017", the elaboration of which was initiated in January 2020, however, given that the RA Cadastre Committee developed the draft decision of the RA Government “On making changes in the RA Government Decision No. 388-N, dated April 6, 2017” and put into circulation in February 2020, thus 1337-N draft will be put into circulation once the draft 388-N regulations come into force 2 Within the framework of the draft joint decision of the RA Central Bank and the MoF On approving "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. 3. During the electronic opening of transit declarations for import transactions within the EEU, mistakes are made by the customs authorities of other EEU member states when filling in the transit declarations and in the future, during the closing of declarations in the Republic of Armenia, the information is entered into the "Taxpayer 3" electronic management system with corresponding shortcomings which creates significant inconveniences in the process of comparing and analyzing the information available in the e-management system Given the importance of the issues raised, it was proposed to enable the electronic tax authority to enter accurate data on the import of goods from the EEU countries, in particular, by manually verifying the data in the "Taxpayer 3" e-government system. |  | In progress | Circulation of the RA Government draft decision "On Making Amendments to the Decision No. 1337-N of the RA Government, adetd October 5, 2017"` after the adoption of the RA draft decision "On Making Amendments" to the RA Government Decision No. 388-N, dated April 6, 2017, and the the entry into force of the regulations envisaged by it. | None
| 15․ Ensuring timely declaration and fulfillment of tax liabilities by taxpayers in full | 15․1 Modernization and capacity building of tax authority analytical and control tools | SRC | - | 2019-2023 | The staff of the tax authority has the necessary capacity to enforce tax legislation There is a revised and constantly improving tax control toolkit |  | Risk management programmes do not address all aspects of revenue collection system | Continuous improvement of risk management programmes with the aim of covering the whole process of revenue collection | Chapter 8,point 8.1,paragraph 7 | To be implemented in the scope of technical assistance | In order to neutralize the risks, a new automated system of inspections was launched in the information system of the RA State Revenue Committee, which enabled the selecton of inspectors to be carried out automatically. At the same time, within the framework of the strategic programs of the State Revenue Committee of RA, the new RCS system were presented to the interested departments in order to have their comments and remarks . 2. By the order of the Chairman of the State Revenue Committee of RA "On introduction of Power BI and reporting-analytical system, creation of analytical tools, as well as regulation of separate departments in order to respond to the technical problems "dated March 23, 2020 and by the order N 260 of the Chairman of SRC, the new Power BI reporting-analytical system was launched under SRC electronic system. Based on the above-mentioned order, 5 analytical tools have already been developed during the launching of the system, as well as there were revealed significant problems in the e-government system of SRC, the settlement of which is in progress. |  | In progress | It is planned to work on the creation of a new ՌՉՍ system program, as well as to resolve the existing problems in the Power BI reporting-analytical system. | None
3․ STRATEGIC PLANNING, DRAWING UP MEDIUM-TERM EXPENDITURE FRAMEWORK AND STATE BUDGET
5. Program budgeting և strategic planning | 16․ Objectives and results of all budget programs included in the 2023 state budget are in line with existing sectoral strategies and cover all existing strategies that have an impact on budget revenues and expenditures | 16․1․ Review / develop budget programs in line with existing strategic policy | MoF | SB | 2020-2022 | Availability of conformity assessment | PI-2, PI-4, PI-5, PI-8, PI-16, PI-17 | · Lack of qualified staff for revision/ development of budget programmes; • Possible failure in development of legal acts | · Involvement of qualified specialists; · Involvement of experts; · Continue using the methodology still in effect under the current legislation | Chapter 8, point 8.2, paragraph 1, 2, 3, 4 and 5 | To be implemented in the scope of technical assistance | By RA Prime Minister By Recommendation No. 02 / 08.5 / 35060-2020, dated 21.07.2020, all SBs were asked to harmonize the financial assessments of the sector strategies with the MTEF. As of 13.08.2020, the measure is implemented i in 18 out of 37 SB having submitted the report on PFMSR progress report and the presented budget programs correspond to the policy directions defined by the main strategies of the PA. Work is underway in 12 bodies to implement the measure: analysis of budget programs from the point of view of compliance with existing strategic documents is carried out. 2 There is a process of reviewing strategies / policy directions in connection with the reorganization and legislative changes in the SB. |  | In progress | After the completion of the recommendation or in parallel with it (until the beginning of 2021) it is planned to carry out self-assessments of the compliance of the sectoral policy, budget programs, on the basis of which the situation will be assessed, further actions will be clarified. | The results of the self-assessments may not be sufficient, and their results may require the involvement of external support for the implementation of the measure | Initiate self-assessment as soon as possible. Discuss with PIO the possibility of providing technical assistance for external evaluation of compliance with budget programs and policies.
All the programs included in the 2023 state budget are in line with the existing strategies
The 2023 budget programs fully cover all existing strategies that have an impact on budget revenues and expenditures.
All programs included in the 2023 state budget (except for administrative programs) have program passports, which are submitted to the RA NA attached to the 2023 draft state budget
|  | 16․2 Identification of practical problems related to the current PB methodology and its application | MoF | - | 2020-2022 | Availability of a report on the study of the problems and existing gaps related to the PB Methodology and its application" | [5 empty] | The possibility of providing external technical assistance for the implementatio of studies related to introduction of the PB methodology problems and gaps related to its application is currently being discussed with partner international organizations. In parallel, it is envisaged that by the end of the year, self-assessments will be carried out on introduction of the PB methodology and the existing gaps and problems related to its application. |  | In progress | Based on the results of external evaluations and self-assessments, if necessary, a schedule of measures to improve the PB methodology and its application will be developed. | External evaluations require technical assistance, but the source is not specified. It will not be possible to carry out the external evaluation work on its own without the technical assistance provided by PIO | In case of not being provided with technical assistance by the PIO, the main source of assessment of the problems and gaps of the PB methodology and its application will be the self-assessments of state bodies. | After discussions with the IMF an agreement has been reached on the possibility to be provided with technical assistance for implementing studies on problems and gaps related to PB methodology introduction and its application
Availability of list of measures and schedule to improve PB methodology and its application, schedule
The measures to improve the PB methodology are implemented in accordance with the schedule of measures
|  | 16․3․Measures aimed at developing human resources | MoF | - | 2020-2023 | Institutional capacity assessment report(s) on existing human resources in accordance with the PB embedded system requirements |  | Training courses do not provide necessary and sufficient knowledge to the specialists | Involvement of trainers with necessary skills |  |  | The possibility of being provided with external technical assistance for the implementation of the institutional capacity assessment of the existing human resources and for the implementation of the elaboration of capacity development program in accordance with the requirements of the embedded PB, is currently being discussed with partner international organizations. It is envisaged that in parallel, internal assessments of relevant capacities in state bodies will be carried out by the end of the year. Based on the results of the above-mentioned external-internal evaluations, an appropriate capacity building program will be developed. |  | In progress |  | External technical assistance is needed to implement the measure but its source is currently unclear. | In case of not being provided with technical assistance by the PIO, the main source of institutional capacity assessment for existing human resources in accordance with th eembedded PB system will be the self-assessments of state bodies.
Availability of up-to-date program for capacity building
Capacity building measures are implemented in accordance with the approved program
| 17․ As of the end of the 2023 budget year, there is a regular budget program evaluation process in all state bodies responsible for budget programs. | 17․1․ Development of budget program evaluation guidelines | MoF | - | December, 2022 | The concept of evaluating budget programs is available |  | Lack of relevant staff necessary for assessment of budget programmes | • Recruitment of staff with necessary skills; • Training of existing staff | Chapter 3, point 3.2, paragraph , Chapter 8, point 8.2, paragraphs 2 and 3 | TO be implemented within the framework of technical assistance | An agreement was reached with the German International Cooperation Agency (GIZ) to provide technical assistance to the MoF in the activities for elaboration of the budget program monitoring, evaluation concept, methodology, as well as the system introduction measure schedule. In this regard, the terms of reference of the above-mentioned activities has already been discussed, the relevant consultant is expected to be selected, the actual works will start this year in September. |  | In progress |  | None |  | (GIZ)
Budget program evaluation guidelines have been developed
|  | 17․2․ Introduce a process of regular evaluation of budget programs | MoF | PA | December, 2023 | Availability of a schedule and measures for the implementation of budget program evaluation functions | [5 empty] | The activities to be carried out within the framework of the event are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. |  | Not started |  | None
As of the end of the 2023 budget year, each state body responsible for budget programs has a regular program evaluation process.
As of the end of the 2023 budget year, at least 1 budget program implemented by each state body responsible for budget programs has been piloted in accordance with the approved guidelines.
6. MTEF process, budget discipline and transparency | 18․ Programs / measures arising from the mandatory obligations of the state are identified and registered | 18․1 Identification and registration of programs / measures arising from the mandatory obligations of the state | MoF | MoF | December, 2021 | Appropriate methodology is available and procedures are developed |  | · In some state agencies the mandatory and discretionary expenses are properly differentiated | · Provision of methodological support by MoF | Chapter 3, point 3.2, paragraph 7, | TO be implemented within the framework of technical assistance | 2021-2023 MTEF and 2021 The methodological instructions for preparing and submitting budget applications already contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. However, the latter needs further clarification or revision in practical terms. In this regard, discussions are currently underway with partner international organizations to provide external advisory support for the implementation of the above-mentioned methodological work. |  | In progress | Implementation of methodology improvement works with external consultation | None
[6 empty] | Within the framework of the 2022 budget process, the mandatory obligations of the state are identified and registered |  |  |  | Chapter 8, point 8.2, paragraphs 2, 3
| 19. Introduction of a joint process of drafting the MTEF and annual budget | 19.1․ Creating a legal basis and elaborating methodology for ensuring a single process of drafting the MTEF and annual budget | MoF | - | 2021 | The activities on drafting of the MTEF and annual budget is carried out by a single process |  | · The SAs of the RA fail to fulfil their responsibilities within the timeframe set due to the lack of appropriate capacity | · Provision of relevant support by the RA MoF or experts |  | TO be implemented within the framework of technical assistance | Starting from 2020, the activitoes of drafting the MTEF and annual budget is already carried out by a single process, for which the legal basis is the schedule set by the decision of the RA Prime Minister on starting the 2021.budget process. After summarizing the results of the 2021 budget process, the expediency of making relevant amendments to the Law "On RA Budget System" will be considered. Accordingly, if necessary, a package of relevant changes will be elaborated and submitted for approval. | August 2020 | Completed | After summarizing the results of the 2021 budget process, if necessary, a package of relevant changes will be elaborated and submitted for approval. | None
| 20․ Simplified budget and simplified budget execution reports are available to public | 20․1 Developing and publicizing the simplified version of the state budget and the budget execution report | MoF | - | Within one month after the adoption of the 2021 RA state budget (Publication of the Simplified Budget) 2021 (Publication of the Simplified Budget Report) | Simplified Budget for 2021 և Budget Execution Reports are published on the official website of the MoF Discussions were held with CSOs on simpliied budget and simplified budget execution reports (at least twice a year) |  | · The simplified version of the state budget and budget execution reports are not accessible and for the general public | · Provision of professional clarifications on simplified version of state budget by MoF | Chapter 3, point 3.2, paragraph 7 | TO be implemented within the framework of technical assistance | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021: For this purpose, with the support of the GIZ the methodological instructions for the preparation of sectoral budget projects by the state bodies within the framework of the drafting of the RA 2021 draft state budget and MTEF 2021-2023 were posted on the official website of the MoF link: http://www.minfin.am/website/images/website/documents/Metodakan2021%20(2).docx), as well as it was officially provided to the public authorities. |  | In progress | The elaboration of the simplified version of the state budget execution report is planned to start after the adoption of the report on the execution of the 2021 RA state budget. | None
| 21. Civil society organizations are more actively involved in the budget process | 21.1.Disclosure of information on budget proposals | SBs | - | 2020-2023 | Budget proposals of RA state bodies are posted on their websites and are available for CSOs |  | · The budget bids of the RA state agencies are not published on their web-sites within the timeframe set and are not accessible for the civil society | · Issuance of relevant instruction by the RA Prime Minister | Chapter 3, point 3.2, paragraph 7; | No additional funding is required | The measure on the 2021 budget process has been implemented According to the schedule approved by the RA Prime Minister's decision N 5-A, dated January 9, 2012 "On starting the RA 2021 budget process", clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. Within the framework of the 2021 budget process, the budget proposals of the requesting state bodies were published on their websites, in a place accessible to CSOs. | January 2020 in terms of the 2021 budget process | It is a periodic process |  | None
|  | 21.2. Establishment of a platform (ies) for discussing budget proposals with CSOs | SBs | - | 2020-2023 | RA state bodies have platforms to discuss budget proposals with CSOs. The budget proposals of the RA state bodies include the results of the discussions on the applications with the CSOs. |  | · The state agencies avoid discussing their budget bids with the CSOs or refuse to accept the recommendation submitted by the latter | · Issuance of relevant instruction by the RA Prime Minister |  |  | According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9 "On starting the budget process of the Republic of Armenia for 2021", a requirement was set by state bodies to place their budget applications on their official websites. In order to ensure the process of public discussions on budget proposals of state bodies, with the support of GIZ the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF 2021-2023 and 2021 state budgets (link http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA MoF and provided to all state bodies. At the same time, according to the preliminary agreement, within the framework of the GIZ support, it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the state budgeting process. According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. Nevertheless, conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process. |  | In progress |  | Conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process. | Fixing mandatory requirements for conducting discussions with CSOs on budget proposals of state bodies within the framework of each annual budget process the requirements for publicizing its results in the Law "On the RA Budget System ". The corresponding draft has been developed and it is envisaged to submit it to the RA NA for approval along with the draft law on the RA 2021 state budget. | GIZ
7․ Automate the process of calculating the cost of budget programs | 22. Within the framework of the 2023 budget process, the processes of calculation (expenditure) of budget programs / measures are carried out through a unified automated system. | 22.1 Step-by-step introduction of an automated budgeting system | MoF | - | Within one month after the adoption of the 2021 report on the execution of the RA state budget July | The automated budgeting system has been tested and is ready for implementation. Within the framework of the 2023 budget process, expenditure budgeting were implemented through an automated expnditurebudgeting system. |  | · Inadequate quality of the automated system of budget programmes cost estimation | · Applying to the software maintenance company for troubleshooting the problems, fixing the defects; Conduction of regular control by the maintaining company; · Identification of defects and their elimination | Chapter 8, 8.2 point, paragraph 2 | State Budget 72 mln.AMD | The elaboration and testing of the automated budget expenditure planning system by the RA Ministry of Finance (Authorized Body) has already been completed in December 2019. The system allows applicant bodies to submit online cost-benefit calculations online as part of budget funding bids, using pre-designed batch և quota agreed with the Authorized Body in formats preliminary elaborated by applicant bodies and agreed with authorized body , as well as enables the respective competent users of the applicant body and the authorized body approve / reject, as well as summarize the data of the received proposals according to the program, operational-economic classifiers, allowing to receive the necessary details of the openings of the numbers of programs / measures In the first half of 2020, professional meetings were held with the representatives of the applicant bodies on the elaboration of templates for the calculation and substantiation of expenditures on the programs and measures included in the budget proposals for the importing into the system after which the RA MoF together with the applicant bodies, started the work of elaborating samples of budget programs and measures calculation of cost-measures to be included in the budget proposals and submitting to the RA MoF which were planned to be completed by February 20, 2020. All samples agreed and approved by the RA MoF have already been imported into the System, and based on the data provided by the Applicating Bodies, users have been created in the system, defining the relevant authorities. In accordance with the RA Prime Minister recommendation the applicant bodies were istructed to submit to the RA MoF within 5 days incomplete or rejected samples of budget programs and measures calculation of cost-measures to be included in the budget proposals (It has already been submitted by 37 bodies, which are being studied by the employees of the Ministry of Defense of the Republic of Armenia, and about 11 bodies have not yet submitted a response letter) and data of employees authorized to work with the System to organize training in order to use the System. It should also be mentioned that on 03.08.2020 a training on system operation (filling / sending data) has already been organized for the RA Police, and in the near future it is planned to organize a training for other law enforcement agencies (RA Ministry of Defense, National Security Service, State Security Service, etc.)The trainings are continuous (Trainings will be organized for the relevant employees of the RA Ministry of Finance (approval / rejection)). |  | In progress | Testing of automated expenditure budget planning system. The introduction of an automated expenditure budget planning system in the applicant bodies is planned to be completed by third ten days of December, 2020.
4․ BUDGET EXECUTION PROCESS CONTROL, TREASURY SYSTEM
8. Budget Execution Reports | 23. Preparation of reports on the execution of the RA state budget by program classification | 23․1 Adaptation of the electronic budget reporting system to the requirements of program budgeting | MoF | - | December, 2019 | Availability of reports on the execution of the RA state budget by program classification | PI-8, PI-28 | Receiving hard copies of reports from key performance indicators is highlighted in the reports received by chief managers of budget appropriations (if the connection failure is observed only with the chief managers of budget appropriations | Provision of instructions related to the necessary information on KPIs, as well as on analytical and other possibilities presented in the reports submitted by the chief managers of budget appropriations | Chapter 8, point 8.2, paragraph 4 | RA State Budget 28 mln. AMD | The measure is completed, and the reports on the execution of the first quarter of the RA 2019 state budget in program format on the execution of both financial and performance indicators have been submitted by the bodies responsible for the execution of the programs through the electronic budget reporting system. Before that, the system was tested, on April 1-3, 2019 trainings were organized for 64 specialists responsible for preparing report, the system was introduced in all state bodies, and the latter were assisted in the introduction and operation of the system. As a result, the quarterly (incremental) reports on the execution of the RA 2019 state budget were submitted to the RA Prime Minister's Office in program format. During the year, activities hav been carried out to solve the problems identified during the operation of the system. | December, 2019 | Completed
9. Arrears monitoring and management | 24. Registration and monitoring of expenditure arrears | 24.1 Expenditure arrears accountung | MoF | SB | 2020-2023 | The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses | PI-22 | Government bodies submit inadequate information on expenditure arrears to MoF | Control over the expenditure arrears by the heads of state governance bodies | Chapter 8, point 8.2, paragraph 4 | No additional funding is required | The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses. Each year the chief budget executive body submits to the Budget Execution Department information on the absence of arrears on state budget expenditures, which is recorded in the reports on the exeution of the RA state budget. (link: http://www.minfin.am/hy/page/byujei_operativ_hashvetvutyunner/): During the reporting period, there were no cases of insufficiency of funds or non-payment due to other unjustified reasons, which in turn will lead to accumulation of budget expenditure arrears. |  | It is a periodic process | Inclusion of information on arrears in the quarterly reports on the execution of the RA state budget. Make In the RA Government draft decision "On Measures Ensuring the Execution of the RA State Budget for 2021", make an addition in the point addressed to the heads of the public authorities and territorial administration bodies, on providing summary information on expenditure arrears together with explanations submitted to the RA Ministry of Finance on the expenditures analysis of the programs implemented by the chief budget executive bodies, the monitoring of the implementation of quarterly (increasing) thresholds on their measures, and the reasons for non-implementation. | None
Information on arrears is included in the reports on the execution of the RA state budget
10. Payroll controls | 25. Personnel records and payroll data coordination and implementation of changes in the accounting information system | 25․1 Elaboration of a system for integration of the human resources database into accounting software / AS modules | SBs | CSB | 2020-2023 | Terms of reference for human resource database / accounting information program module integration system is elaborated and approved | PI-23 | Staff and payroll data are not matched through software or other IT systems | Establishment and control over the timetable for introduction of a system of integration of databases with the accounting software modules | Chapter 8, point 8.2, paragraph 5 | RA State Budget (the amount of funding will be determined by each of the state agencies in the frame of the ToR) | In most of the SBs the system is embedded, all the processes related to the personnel registration and salary fund data are carried out through the system. Work is being done to identify the state bodies where the transfer of human resources data is not carried out through the accounting information program, and an inventory of the current state of transfer of personnel data to the accounting is made |  | In progress | Elaboration and approval of implementation plan, terms of reference in each state body | None
|  | 25․2 System introduction and maintenance |  |  |  | The system is embedded and all processes related to personnel records and payroll data are carried out through the system
| 26. Payroll audit | 26․1 Implementation payroll audit by the Internal Audit | MoF | SB, CSB | 2021-2023 | Data transfer and comparison deficiencies are identified |  | No payroll audit is conducted | The Internal Audit Departments of state agencies include payroll audits in their annual programmes |  | No additional funding is required | During 2019, a payroll audit was conducted in 1 SB |  | In progress | 3 The internal audit department of the PA plans to conduct an annual payroll audit | None
The reports provide recommendations on payroll control
| 27. Ensuring the accountability of the calculation of salaries and equivalent payments | 27.1 Notification of data on salaries received to employees, calculation of equivalent payments, income received | MoF | SB | 2021-2023 | Employees receive information each month about the calculation and payment of income received during the previous month |  | Employees do not get any information about their income via e-mail | Modification of the introduced accounting software |  | No additional funding is required | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries during the first half of 2020. |  | In progress | Steps have also been taken in the SBs to make changes in AS, as a result of which employees will receive electronic information on salaries. | None
5. PUBLIC DEBT | [13 empty] | 0
Public Debt Management | 28. Improving the RA Law "on Public Debt" | 28․1 Conformity of the RA Law "on Public Debt" to the standards applied by international financial institutions | MoF | - | December, 2022 | Improving debt statistics by clarifying the definitions used in the RA Law on Public Debt ("Public Debt" and "Government Debt") | PI-13 | The RA National Assembly does not adopt the Draft Law on Public Debt | Organization of joint discussions with the RA National Assembly; Restatement/revision of the draft law in case of necessity | Chapter 1, point 2, paragraph 3 | No additional funding is required | Discussions are underway with international financial institutions to obtain technical assistance for the implementation of the measure |  | In progress |  | External technical assistance is needed to implement the measure, but its source is currently unclear. | Continue negotiations with PIOs. If necessary, submit proposals for revising the dates of the measure
| 29. RA Government debt portfolio exchange rate risk mitigation | 29․1 Increasing the share of deficit financing in the state budget each year at the expense of net domestic borrowing | MoF | - | December, 2023 | The share of deficit financing in the state budget at the expense of net domestic borrowed funds is at least 50.0% |  | Decline of demand for state treasury bonds; Volatility in financial market | Coordination of fiscal and monetary policies |  | No additional funding is required | The share of deficit financing at the expense of net domestic borrowing was forecasted and presented at 94.5% for 2021 in the MTEF 2021-2023 2021-2023The share of deficit financing at the expense of net domestic borrowing was forecasted and presented at 82.4% for 2022 in the MTEF 2021-2023. The share of deficit financing at the expense of net domestic borrowing was forecasted and presented at 100.0% for 2023 in the MTEF 2021-2023: | July 10. 2020 | It is a periodic process | The share of deficit financing at the expense of net borrowed funds will be presented in the RA 2021 draft state budget within the period defined by the RA Minister of Finance order N56-A, dated 26.02.20. | None
6. PUBLIC SECTOR ACCOUNTING
12. Public Sector Accounting | 30.Monitoring the annual financial statements of public sector organizations | 30․1 Monitoring the financial statements of public sector organizations by the MoF | MoF | - | 2019-2023 | · Financial statements in accordance with the RA Public Sector Accounting Standard (IAS) | PI-29 | • Insufficient number of employees for monitoring of financial statements of all organizations; • Some organizations have not made а transition to the new public sector accounting system | Recruitment of employees with relevant skills Issue instructions for the authorized bodies to ensure the transition Clearly define the qualification enhancement procedure | Chapter 8, point 8.2, paragraph 4 | No additional funding is required | In April 2020, a letter was sent to public sector organizations to submit their 2019. 2019 transaction log and financial statements for monitoring purposes. The already submitted financial statements are monitored, and after summarizing the results, they are submitted in writing to the relevant public sector organizations. At the same time, based on the monitoring results the 9th և 10th issues of the Professional Directory were prepared in 2020 and sent to the public sector organizations. |  | It is a periodic process |  | None
|  | 30․2 Methodology review (as needed) | MoF | - |  | Improved regulatory framework | [5 empty] | The draft law "On Making Amendments to the Law on Accounting of Public Sector Organizations" has been developed by the Ministry of Finance. The draft has already been approved by the RA NA Standing Committee on Finance and Credit, has been included in the agenda of the regular sittings of the RA NA for discussion in the first reading, which will take place in autumn, 2020. |  | In progress | A review of the public sector accounting methodology will be carried out as necessary | None
|  | 30.3 Implementation of the qualification process for chief accountants of public sector organizations | MoF | - | 2020-2023 | Qualified Chief Accountants of Public Sector Organizations | [5 empty] | The qualification procedure of the public sector accountant, the list of questions included in the questionnaire և the composition of the qualification commission were approved by the orders of the RA Minister of Finance. About 25 applications have been received to participate in the Public Sector Accountant qualification examination, but due to the state of emergency, no examination has been conducted yet. After the end of the state of emergency, the planned examinations will be held as soon as possible. |  | In progress | After the end of the state of emergency, the planned examinations will be held as soon as possible. The process of qualification of chief accountants of public sector organizations is regular. It is envisaged to organize and conduct qualification exams for public sector accountants at least 4 times a year. | Extension of the state of emergency. | Consider the possibility of organizing qualification exams online
| 31. Preparation of interim consolidated financial statementss at the ministry level | 31․1 Development of a methodology for consolidating financial statements | MoF | - | 2022-2023 | Consolidation methodology | PI-29 | Some organizations have not made a transition to the new public sector accounting system; Lack of capacities necessary for procurement or development of the software for carrying the consolidation process | Instruct the authorized bodies for ensuring the transition; Study on effectiveness of the use of such software in other countries and exchange of experience |  | To be implemented in the frame of technical assistance | The draft consolidation methodology has been developed and will be reviewed by international experts as part of the activity on the introductionof the GFMIS. The tender of international experts involved in the GFMIS consolidation methodoloogy review is not over yet, no expert has been selected. |  | In progress | It is envisaged that the draft will be reviewed by 3rd ten days of December 3, 2020 within the framework of the works carried out for the implementation of the GFMIS | The tender of international experts involved in the GFMIS consolidation methodoloogy review is not over yet, no expert has been selected.
|  | 31․2 Development or acquisition of a joint computer program for the purpose of consolidation | MoF | - |  | Software necessary for consolidation | [5 empty] | The software needed for consolidation can be obtained with the appropriate financial resources. At the same time, this operation is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. |  | In progress |  | The tender of international experts involved in the GFMIS consolidation methodoloogy review is not over yet, no expert has been selected. The software needed for consolidation can be obtained with the appropriate financial resources. | Initiate negotiations with PIOs to identify sources of funding for the software. Consider the possibility of developing a relevant software module within the GFMIS. If necessary, submit a proposal to review the implementation dates of the measure.
|  | 31․3 Preparation of interim consolidated financial statements at the ministry level | MoF | - | December, 2023 | Interim consolidated financial statements are submitted at the ministerial level | [5 empty] | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 և 31.2. |  | Not started | Preparation of consolidated financial statement at the level of at least one ministry, in case of software program, including the ministry and its SNCOs. | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 և 31.2. | Depending on the course of the measures mentioned in points 31.1 and 31.2, submit a proposal, if necessary, to review the deadlines for the implementation of the measure.
7. CORPORATE ACCOUNTING AND AUDIT
13.Regulation of corporate accounting and audit activity | 32. Introduction of public control system over accounting and auditing activities | 32․1 Completion of the necessary sub-legislative framework | MoF | - | 2020-2021 | New specialized structures for sector regulation and control - Public oversight board model, | - | Non approval of the laws by the RA National Assembly (RA NA) Insufficient capacities of employees | Detailed presentation of advantages of public control system during the discussion of the legislative package at the RA NA; Training of employees | - | To be implemented in the frame of technical assistance | Currently, the RA Government draft decision "On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Computer Software Enabling Accounting" has been submitted to the expert opinion of the RA Ministry of Justice. The draft minimum list of data included in the register of expert accountants, auditors and auditing companies has been developed, which must be approved by the Public Oversight Board in accordance with the Law. The public oversight board has been formulated in accordance with the Orders of the RA Minister of Finance, dated June 30, 2020 . The schedule of the latter was approved by the RA Minister of Finance order No. 196-L, dated July 8, 2020 No. 196-L. Legal acts related to the extension of qualification certificates of accountants-auditors have been developed and approved. By the RA Minister of Finace order 119-Ա, dated April 20, 2020 AAAA is accredited as a specialized body accredited within the meaning of the RA Law on Accounting և Regulation of Auditing Activities and Public Control. |  | in progress | Implementation of the process of accreditation of specialized structures. Organizing the process of establishing the Public Oversight Board (elaboration of the charter and necessary legal acts, formation of the Public Oversight Board staff). | None
Effective audit quality control system
adjusted scope of organizations subject to mandatory audit
|  | 32․2 Staff training |  |  |  | Appropriate level of capacity | [5 empty] | In April-May, 2020, online seminars-discussions were organized for the employees of the Accounting and Auditing Activity Regulation Department on the requirements of the main provisions of the 3 new laws regulating the areas of accounting and auditing activities. |  | in progress |  | None
8. FINANCIAL MANAGEMENT AND CONTROL OF STATE ORGANIZATIONS: STATE NON-Commercial ORGANIZATIONS (SNCO) | [15 empty] | None
14. Financial Management and Control of state organizations accountability of state non-commercial organizations | 33. Improving the system of accountability and monitoring of the financial and economic activities of SNCOs | 33․1 Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | MoF | - | 2020-2023 | Existence of an up-to-date system for monitoring the financial and economic activities of SNCOs | PI-8 | Lack of technical assistance; Law quality of reports submitted by state government bodies; | Attraction of financial support and involvement of experts through development partners Development of guidelines for submitted reports | Chapter 8, point 8.2, paragraph 4 | To be implemented in the framework of technical assistance | In the first half of 2020, surveys were conducted in the field of activity of state non-commercial organizations to develop a system of non-financial (productive) indicators. At the same time, discussions were held with a number of authorized bodies. The measure will take place after the implementation of 33.1.1 և 33.1.2 stages |  | In progress |  | None
9. PUBLIC PROCCUREMENT
15. Upgrading the e-procurement system | 34. New e-procurement system software | 34․1 Development and implementation of new e-procurement system software | MoF | - | December, 2020 | New existing e-procurement software | PI-24 | Lack of financial resources | Applying the public-private partnership model | Chapter 8, point 8.2, paragraph 8 | RA state budget or other sources of financing not prohibited by the RA legislation | Activities have been carried out with donor organizations to develop a business model and terms of reference for the introduction of a new e-procurement system. In particular, an agreement was reached with the European Bank for Reconstruction and Development to elaborate a new e-procurement software system with the latter's technical and financial assistance, according to which the it is expected to obtain from EBRD business model rationale for the introduction of the new e-procurement system. Given that there is no response from the bank yet, the technical task of selecting a consultant for the implementation of the consultant in the framework of the introduction of the GFMIS envisages the elaboration of a business model for the introduction of the e-procurement system, provided that it will not be implemented by the consultant. Given that there is no response from the bank yet, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model և technical task for the implementation of the e-procurement system, provided that it will not be implemented by the consultant if they are implemented by the EBRD. The issue related to the substantiation of the business model proposed by the bank is currently being discussed, after the clarification of which the relevant decision will be made. |  | It is risky |  | External technical assistance is required for the implementation of the measure, for which there is currently no clarity. The deadlines are short, there is a risk of securing the event on time. | To speed up the issue of the justification of the business model proposed by the EBRD and make a decision. If necessary, make an offer to extend the term.
16. Procuurement planning | 35. Improving the procurement planning system | 35․1 Develop RA Government draft decision on the introduction of a unified planning system for determining the estimated prices of items with similar characteristics automatically | MoF | - | December, 2020 | The similar needs of customers are met with items with the same characteristics and estimated prices |  | Lack of possibility for introduction of a unified system for determining and planning of estimated prices | Introduce the system into the current e-procurement framework | Chapter 1, point 2, paragraph 2 | No additional financing is required | The relevant proposals for the implementation of the mentioned measure were received and summarized from the RA public administration bodies based on the letter 01/26-1/3308-2020 of the RA Minister of Finance, dated 21.03.2020. |  | In progress | As a result of the discussion of the proposals, RA Government draft decision will be elaborated and submitted to the RA Governmentfor consideration | None
17. Procurement Appeal System | 36. Improving the procurement appeal system | 36.1 Making changes in the RA Law on Procurement | MoF | - | December, 2021 | Functional and independent appeal system |  | The RA National Assembly (RA NA) does not adopt the draft law | Organizing joint discussions with the RA National Assembly (RA NA) of the Republic of Armenia and revision of the draft Law in case of necessity | Chapter 8, point 8.2,paragraph 12 | No additional funding is required | The RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Amendments to the RA Law on State Duty", "On Making Amendments an supplements to the RA Civil Procedure Code" have been elaborated and submitted to public government bodies, international donor organizations and civil society for consideration. Discussions with the EU SIGMA Program Expert Group are ongoing. |  | In progress | Discussions with the EU SIGMA Program Expert Group are ongoing. After completing those discussions and summarizing the received proposals, the packages of the mentioned projects will be summoned up and submitted to the RA Government for discussion in the prescribed manner. | None
10. PUBLIC INTERNAL FINANCIAL CONTROL AND FINANCIAL-BUDGETARY OVERSIGHT
18. Financial management and control | 37. Ensuring the introduction of financial management and control system | 37․1 Testing of FMS system methodology | MoF | - | December, 2020 | · Piloted methodology of FMS | PI-25 | Impediments in piloting the FMC methodology | Defining the milestones and rules for pilot implementation of FMC legislation | Chapter 8, point 8.2, paragraph 4 | To be implemented in the frame of technical assistance | As of 2019, there are still draft legal acts for the introduction of the FMS, which need to be reviewed once again, considering them from the point of view of the implementation of the PB system, discussing them with the Civil Service Office. In order to test the FMS system, an agreement was reached in 2019 with the RA Ministry of Education and Science (there is an official letter from the Ministry of Finance and an agreement with the pilot ministry) to pilot the above methodology. The second state body that was selected and an agreement reached with the latter's representatives is the RA Ministry of Labor and Social Affairs. |  | It is risky | Complete the pilot work, and as a result, complete the methodology approval work. | The deadlines required for the measure are short and there is a risk of ensuring the measure on time | To speed up the work related to the testing of the FMS system methodology , to assess the realism of the implementation of the measure and make a proposal for extension of the term if necessary.
|  | 37․2 Adoption of FMS Concept and FMS Legislative Acts |  |  | 2021-2022 | · Adopted FMC concept and legislation |  | Lack of technical assistance from development partners for elaboration of FMC legislation | Apply to development partners for receiving technical assistance with the aim of development of FMC Legislation |  | To be implemented in the frame of technical assistance | During 2018-2019 the draft FMS concept was elaborated with the support of GIZ |  | In progress
|  | 37․3 Introduction of FMS system in public sector organizations | MoF | SB | Beginning from 2022 | · The process of introducing the FMS system is carried out according to the set schedule |  | Introduction of FMC system in public sector organization is not carried out in a proper manner | Provision of support by CHU; Monitoring of the FMC system introduction process; Designating a persons in charge |  | To be implemented in the frame of technical assistance | As the measure is related to event 37.1, the work related to this event will start after the testing of the FMS system methodology and adoption of FMS concept and relevant legislation |  | Not started |  | The deadlines required for the measure are short and there is a risk of ensuring the measure on time | Accelerate as much as possible the process of adopting the necessary legal acts related to the introduction of the FMS and make a decision. If necessary, make an offer to extend the term.
19. Public sector internal audit | 38․ Carrying out external evaluation of the quality of internal audit | 38․1 Approval of the external audit quality assessment methodology | MoF | - | December, 2019 | Order approved by the RA Minister of Finance "On approving the procedure for conducting external evaluation of the internal audit quality | PI-26 | The methodology for external quality assessment of the internal audit is not available | Designate persons in charge to ensure the implementation of measures | Chapter 8, point 8.2, paragraph 4 | No additional financing is required | In the context of this measure, with the support of the World Bank, an external quality assessment manual was developed, which was piloted in 2 organizations of the RA public sector. RA Minister of Finance draft order has been elaborated. The draft order was discussed with the representatives of state bodies, was finalized and is ready for approval. |  | It is expired |  | The necessary deadlines for the implementation of the measure have expired and the measure was not implemented within the set deadlines. | Accelerate the approval of the order on the procedure for conducting the external evaluation of the internal audit quality as much as possible Propose an extension at the same time.
|  | 38․2 Carrying out external evaluation of the quality of internal audit in public sector organizations |  |  | 2020-2022 | All public sector organizations where an internal audit system is in place will be subject to external evaluation by the MoF. |  | No or partial external assessment of the quality of internal audit activities is conducted | Scheduling of activities, distribution of responsibilities between the implementers |  | No additional financing is required |  |  | Not started |  | The deadlines required for the measure are short and there is a risk of ensuring the measure on time | Accelerate the approval of the order on the procedure for conducting the external evaluation of the internal audit quality as much as possible Propose an extension at the same time.
Report on the quality of internal audit of the RA public sector
| 39․ Ensuring Internal Audit and External Audit Cooperation | 39․1 Define internal audit and external audit cooperation procedures | MoF | AC (by agreement) | PB | Joint order of the RA Minister of Finance and the Chairman of the RA Audit Chamber "On approving the order of internal-external audit cooperation" |  | The procedures of cooperation between the internal and external auditors are not defined or applied in practice | Scheduling of activities; distribution of responsibilities between the implementers |  | To be implemented in the frame of technical assistance | The procedure for internal-external audit cooperation has been under development since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version և after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. |  | In progress | Make the document complete, submit to the RA Audit Chamber and Sbsfor consideration and submit the revised document for approval as a result of discussions
| 40. Emphasis on Performance Audit Capability and Provide practical application of 30% of the annual plan | 40․1 Approval of performance audit methodology | MoF | - | 2019-2020S | Approved order of the RA Minister of Finance "On approving the performance audit manual" |  | Performance Audit Methodology is not available | Scheduling of activities; distribution of responsibilities between the implementers |  | No additional financing is required | RA Minister of Finance draft order "On approving the performance audit manual" has been developed, which is in the process of revision, within the framework of which it is necessary to ensure the connection of the performance audit with the embedded PB system, which which will provide an opportunity to comprehensively assess the results of the programs of the PBs implementing budget programs considering it not only in the context of financial but also in the context of non-financial performance indicators. |  | It is risky | In order to implement this measure, it is necessary to cooperate with the RA Audit Chamber, WB and GIZ | The deadlines required for the implementation of the event are short, taking into account the work done, the status of the work to be carried out, there is a risk in terms of ensuring the event within the set timeframe. | It is necessary to speed up the discussions with the relevant bodies as much as possible, to complete the revision of the manual, and to submit the manual to the Minister's approval by December of this year. If necessary, make an offer to extend the term.
|  | 40․2 Increasing the role of performance auditing in internal audit legislation |  |  | December. 2020 | Requirement stipulated in the internal audit legislation, according to which the performance audit will make up 30% of the annual internal audit program |  | Performance audit is not included in the Internal Audit Annual Programme or it makes up less than 30% of the Annual Programme | Scheduling of activities; distribution of responsibilities between the implementers |  | No additional financing is required |  |  | It is risky |  | Although no information has been provided on the measure, the deadlines required for the measure are short and there is a risk of ensuring the event on time. | It is necessary to speed up the issue of drafting the necessary legislative changes, ensuring their adoption, and making a decision.If necessary, make an offer to extend the term.
|  | 40.3 Development of performance auditing skills of internal auditors operating in RA public sector organizations |  |  | 2020-2023 | Internal auditors in RA public sector organizations trained in performance auditing |  | Internal auditors working in public sector organizations do not have the knowledge necessary for implementation of performance audit | Scheduling of activities; distribution of responsibilities between the implementers |  | To be implemented in the framework of technical assistance | PA |  | No information provided
| 41. Development of professional knowledge and skills of internal auditors | 41․1 Elaborating a program for developing the professional knowledge and skills of internal auditors | MoF | - | December, 2020 | Internal auditors' professional knowledge and capacity are assessed, needs identified, development plan approved |  | Internal auditors' professional knowledge and capacity building programme is not available | Scheduling of activities; distribution of responsibilities between the implementers |  | To be implemented in the framework of technical assistance |  |  | It is risky |  | Although no information has been provided on the measure, the deadlines required for the measure are short and there is a risk of ensuring the event on time. | It is necessary to speed up the assessment of the professional knowledge and capacity of Internal Auditors as much as possible, identify the needs and approve an appropriate program. If necessary, make a proposal to revise the deadline.
|  | 41․2 Optimization of continuous professional training courses for internal auditors |  |  | 2020-2022 | The internal auditors have the requirements of the RA legislation on internal audit, international advanced experience, theoretical knowledge of internal audit and practical skills. |  | Continuous professional development courses do not provide the internal auditors with necessary and sufficient knowledge | Scheduling of activities; distribution of responsibilities between the implementers |  | To be implemented in the framework of technical assistance |  |  | No information provided
|  | 41․3. Elaboration of an online information system for the continuous professional training of internal auditors |  |  | 2020-2021 | Internal auditors undergo an annual continuousprofessional training program through an online information system |  | The continuous professional development courses for internal auditors are not organized online | Scheduling of activities; distribution of responsibilities between the implementers |  | To be implemented in the framework of technical assistance |  |  | No information provided
|  | 41․4 Review of the Public Sector Internal Auditor Qualification Procedure |  |  | December, 2021 | Internal auditor qualification system based on relevant international approaches |  | Lack of technical support for establishing qualification procedures in line with best international practices | Apply to development partners with the aim of receiving technical assistance |  | To be implemented in the framework of technical assistance |  |  | No information provided
20. Central harmonization unit (CHU) | 42. CHU personnel recruitment and capacity building | 42․1 CHU personnel recruitment and capacity building | MoF | - | 2019-2021 | Necessary capacities are available in CHU | PI-25, PI-26 | Professional capacities of the CHU are not sufficient to ensure the exercise of authorities by the latter The CHU has no insight on PIFC problems; PIFC experts have no possibility to raise questions related to the existing problems | Designating responsible persons to ensure the implementation of relevant activitie Engaging international experts for addressing the issues raised | Chapter 8, point 8.2, paragraph 4 | To be implemented in the framework of technical assistance | The relevant subdivision, which was carrying out the functions of the CIA, was dissolved on February 24 of this year and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CIA. |  | In progress | Organizing training courses for CHU personnel recruitment and capacity building
Financial and budgetary oversight | 43․ Ensuring effective financial and budgetary control activities | 43․1․ Review of financial-budgetary control legislation, update, development of new methodology for implementation of financial-budgetary control | MoF | - | 2020-2021 | By-laws defining the modern methodology of financial and budgetary control | - | Lack of technical assistance for development of a financial-budgetary oversight (inspection) methodology that complies with best international practices | Apply to development partners with the aim of receiving technical assistance for development of financial-budgetary oversight (inspection) methodology | Chapter 8, point 8.2, paragraph 4 | To be implemented in the framework of technical assistance | In the context of this group of measures, the main problems in the system of financial-budgetary control were formulated in 2018-2019. The RA Government decision "On defining the procedure of financial and budgetary control of the Republic of Armenia" and declaring null and void the RA Government decisions dated July 11, 2002 N 1112 N and February 23, 2012 N 207 " has been elaborated which is under discussion |  | In progress | Clarify the priorities and Implement updating of the legal framework in parallel with the development of human resources and, if possible, the introduction of a qualification system.
|  | 43.2 Capacity building of specialists in the field of financial-budgetary control |  |  | 2022-2023 | Specialists in the field of financial-budgetary control have professional skills and have relevant knowledge |  | Insufficient number of specialists for conduction of trainings; Inadequate quality of trainings and modules Restricted access to databases | Involvement of qualified specialists; Training needs assessment; Revision of the training programme and modules |  | To be implemented in the framework of technical assistance |  |  | Not started
|  | 43․3 Availability of necessary databases for risk assessment |  |  | 2020-2023 | Introduction of a new risk system based on complete, substantiated and justified information analysis |  | Restricted access to databases | Apply to relevant state agencies, Treasury and the RA State Revenue Committee for receiving necessary information |  | To be implemented in the framework of technical assistance | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. |  | In progress
11. PUBLIC ASSETS AND PUBLIC INVESTMENT MANAGEMENT
22.Public asset management | 44. Ensure monitoring of government financial and non-financial assets | 44.1․Elaboration and approval of the methodology of public asset management and legal acts necessary for its introduction | MoF | - | 2020-2022 | Existing methodology on management of financial and non-financial assets of the Government, and Legal acts approved in accordance with the RA legislation | PI 21 | ·The legislation on asset management is not available No relevant asset management staff for conducting trainings is available | Apply to development partners with the aim of receiving relevant technical assistance Recruitment of staff with relevant skills | Chapter 8, point 8.2, paragraph 6 | To be implemented in the framework of technical assistance | Measures for the introduction of the public asset management system were envisaged by the second PFMS strategy of the RA Government and the relevant action plan, but they were not implemented due to lack of technical assistance during 2016-2018. The elaboration of a public asset management methodology requires the involvement of external experts with relevant experience in the field of public asset management, for the purpose of which discussions are currently underway with partner international organizations to carry out this work with their support. |  | It is risky |  | The timing of the measure is short and its implementation requires external technical assistance, the clarity of which is currently unclear. The role of the MoF in terms of elaboration and monitoring of public asset management methodology, distribution of those roles among the subdivisions of the Ministry needs to be clarified. In particular, there are potential crossings in these functions to the functions of the Ministry's budget process organization, budget execution reports, as well as the functions of accounting auditing activities regulating and reporting monitoring departments. The staff responsible for monitoring the budget asset management methodology of the Budget Process Management Department of the RA Ministry of Finance is not staffed; the existing capacities are not sufficient to ensure the implementation of the | Continue the ongoing work to ensure external technical assistance. As soon as possible, recruit the staff of the Budget Process Management Department of the RA Ministry of Finance, responsible for monitoring the public asset management methodology. Within the framework of the measure, set a task to clarify the role of the RA Ministry of Finance in terms of public asset management and monitoring functions, as well as to clarify the distribution of roles to ensure those functions among the subdivisions of the MoF Depending on the progress of these works, if necessary, submit a proposal to review the timing of the event. | Discussions were held to develop a methodology for managing public assets, and an agreement was reached with the IMF to carry out this work with the support of the latter.
|  | 44.2 Implementation of trainings on asset management techniques in accordance with the approved legislation | MoF | PB |  | Specialists trained in accordance with the law on public assets |  | No relevant asset management staff for conducting trainings is available | Recruitment of staff with relevant skills |  |  | . | The works have not started | IT is risky |  | The implementation of the measure depends on the results of the event mentioned in points 44.1. | Depending on the course of the measure referred to in paragraph 44.1, submit a proposal as necessary to review the timing of the event.
|  | 44.3 Preparation and monitoring of financial և non-financial asset registers | PB | - |  | Asset Monitoring Report | [5 empty] | The activities to be carried out within the framework of this measure are the implementation of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure | Activities haven't started yet | It is risky |  | The implementation of the measure depends on the results of the event mentioned in points 44.1. | Depending on the course of the measure referred to in paragraph 44.1, submit a proposal as necessary to review the timing of the measure
| 45. Ensuring transparency of the sale, transfer, alienation process and the right to use non-financial assets | 45.1 The definition of procedures for the sale, transfer, alienation process and the right to use non-financial assets will be reviewed. | MoF | TAIM | 2022-2023 | Procedures for the sale, transfer, alienation process and the right to use non-financial assets are approved. |  | Alienation of non-financial assets is not carried out in compliance with the established procedures | Monitoring of asset alienation and identification of reasons for failure to conduct the monitoring; Submission of reports; Setting precise timeframes and instructions | Chapter 8, point 8.2, paragraph 6 | To be implemented in the framework of technical assistance | The activities to be carried out within the framework of this measure are the introduction of a public asset management methodology to be developed under measure 44.1. The latter is a logical continuation of the above-mentioned event, it will be implemented based on the results of that event. | Activities haven't started yet | It is risky |  | The implementation of the measure depends on the results of the measure mentioned in points 44.1. | Depending on the course of the measure referred to in paragraph 44.1, submit a proposal as necessary to review the timing of the measure
Public investment management | 46․ Creating a Legislative Basis: Public Investment Management Methodology | 46.1․ Elaboration of a public investment management manual | MoE | - | December, 2019 | The Public Investment Management Manual has been developed and is ready for testing | PI-11, PI-4 | • Possible failure in development of guidelines for economic analysis of investment projects; • Possible failure in activities aimed at development of guidelines for assessment of the full cycle of programme expenditures | Continue using the methodology still in effect under the current legislation; Continue using the cost evaluation methodology still in effect under the current legislation | Chapter 8, point 8.2, paragraph 6 | To be implemented in the framework of technical assistance | 1. Within the framework of the works aimed at the introduction of the public investment program management system, in particular, the elaboration of a methodology for identifying, elaborating, evaluating and setting priorities of public investment programs The draft Public Investment Management Manual (hereinafter referred to as the Manual) was developed jointly with the experts of the World Bank (hereinafter referred to as the WB). According to the appendix approved by the RA Prime Minister's decision N 5-A of January 9, 2020 "On starting the budget process of 2021" of the RA Prime Minister, for the latter’s testing the RA Ministry of Economy has provided to the RA Ministry of Healthcare, Ministry of Education, Science, Culture, Sports, Ministry of territorial administration and infrastructure, in the defined timeframe "The form for the investment project concept and quality assessment" (the standard form) to present the new projects in excess of 70 million drams in the standard form. The pilot stages of the manual have passed 8 investment projects provided by the mentioned departments. 2. The testing of the manual with the agencies was carried out in stages, by sectors. In this regard, in the first phase, from January 29 to February 14, 2020, 6 meetings and discussions were held, during which the information on the Manual was provided to the representatives of the relevant agencies, as well as consultancy on the completion of the Form per the Manual. 3. In the second stage, on February 24-28, 2020, a seminar-discussion was held with the participation of WB experts, experimentally selected ministries, representatives of the RA Ministries of Finance, Economy and the Office of the RA Deputy Prime Minister Tigran Avinyan., During which the WB experts gave a detailed reference to the principles of identifying problems within the framework of investment projects, setting goals, և action-intermediate result-end-impact-benefit "logical chain formation։ Based on the relevant examples, the mechanisms for calculating the demand-risk analysis, as well as the financial-economic analysis of investment projects were presented. 8 new investment projects submitted by the RA Ministry of Health, the RA Ministry of Education and Science and the RA Ministry of TAI were studied. During the discussions, observations and proposals were submitted for all the projects, as a result of which the representatives of the ministries were offered to amend the provided investment project applications based on the submitted considerations and submit the revised version to the RA Ministry of Economy. 3․ In the 3rd stage, on March 12, 2020, and March 13, a video conference was held at the RA Ministry of Economy with the participation of the staff of the RA Ministry of Health, the RA Ministry of Education and Science and the WB experts. During the video conference, the considerations on the investment projects submitted in accordance with the Model Form, provided by the agencies, were further discussed, on the basis of which it is planned to finalize the revision of the projects. As a result of the implemented works, the strengths and weaknesses of the Manual were identified, as well as the shortcomings were registered, localizing the Manual as much as possible, taking into account the situation in the Republic of Armenia. The above-mentioned works were summarized in April 2020. |  | Completed | 2․ As a result of the work carried out within the framework of the manual testing and model form consideration, the investment project provided by the RA Ministry of Health was selected. A more in-depth preliminary feasibility study is planned in the 3rd ten days of August, 2020 together with WB experts. 2․ In the middle of September 1, 2020, as a result of the work carried out in the direction of testing and evaluation of the Manual, the Manual will be summarized and finalized. 3․ Preparation of a summary report of the activities carried out within the framework of the manual test ։ 4․Round table discussion with WB experts to make appropriate adjustments and finalize the work done. |  |  | WB
|  | 46.2․ Testing the Public Investment Management Manual Identifying shortcomings |  |  | December, 2020 | Report on testing results and existing deficiencies. | [5 empty] | The manual was tested in several stages: 1. This year from January 28 to February 14, within the framework of the introduction of the Public Investment Management System, discussions were held with the representatives of the RA Ministry of Health, the RA Ministry of Education and Science and the RA Ministry of Territorial Administration and Infrastructure to complete the investment projects in accordance with the form. 2. This year from February 24 to 28, with the participation of representatives of interested state agencies, in particular the RA Ministry of Territorial Administration and Infrastructure, the RA Ministry of Health, the RA Ministry of Finance, the RA Ministry of Economy, the office of Deputy Prime Minister Tigran Avinyan 5 seminars-discussions on new initiatives completed in accordance with the model form by the agencies were held in the frames of introduction of public investment management system 3. Taking into account the situation caused by the coronavirus, further testing of the Manual was carried out online. Preliminary evaluation of investment projects has been carried out. 4. Considering that as a result of the study of investment projects the indicators of investment projects were not provided with sufficient accuracy, by the initiative of the RA Ministry of Economy a remote workshop was organized by the WB on June 23, 2020 within the framework of which the necessary indicators were discussed for each investment project, as a result, it was decided that the "Human Life Value" index is missing in Armenia, while it is necessary for evaluating public investment, in particular, social programs. In this context, a working group has been set up to recruit relevant specialists to calculate this indicator. 5. As a result of the discussions with the selected pilot agencies, the investment project provided by the RA Ministry of Health was selected; additional work was done to include new indicators for the evaluation of the project.։ The indicators of the considered project of a similar program provided by the WB experts were studied, within the framework of which the indicators became almost 75% comparable. In terms of 25% incomparable indicators preliminary feasibility study Is planned to carry out with the WB experts in the 3rd ten days of August , 2020 to identify missing indicators. In the absence of the "Human Life Value" indicator for Armenia during the mentioned period, the indicator calculated by the WB for Armenia will be taken into account. 6. As a result of the preliminary feasibility study carried out jointly with the WB experts, the practical testing phase of the Manual will be summarized, the results of which will be included in the Manual. (as mentioned in point 46․1)։ As a result of the above, it will be possible to fully evaluate the Manual, as a consequence of which it is planned to carry out the work of circulating the Manual among the relevant agencies, summarizing and approving the considerations regarding the latter. |  | In progress | Involvement of other relevant agencies in the work carried out jointly with the RA Ministry of Health, the RA Ministry of Education, Science, Culture and Sport and the RA Ministry of Territorial Administration and Infrastructure, selected on a pilot basis within the framework of testing the Public Investment Management Manual. 2․Carrying out a preliminary feasibility study on the investment project provided by the RA Ministry of Health together with the WB experts. 3․Involvement of a relevant specialist to calculate the 2020 "Human Life Value" index. 4․"Human Life Value" Index calculated in the first half of 2021. |  |  | WB
|  | 46.3․ Review and approval of the Public Investment Management Manual |  |  | December, 2020 | The Public Investment Management Manual is approved by the RA Government | [5 empty] | ․1․As a result of the discussions on the project, as well as the experimental work, it became necessary to amend the Manual. Relevant work is currently underway in the direction of the latter, with the aim of creating an effective system for multifactorial evaluation of public investment programs, based on which the cross-sectoral priorities of those programs are determined. 2. Work has been underway for about 6 months to review the manual, taking into account the sequential implementation of all stages and components of the test, summarizing the results, and making appropriate amendments. The final discussion of the manual is planned to be held in October-November, 2020., taking into account the comments of all experts. Within the framework of the introduction of the Public Investment Management System, the RA Prime Minister draft decision "On Approval of the Procedure for Assessing the Impact of the RA Public Investment projects and Determining Priorities and Criteria for Evaluating Public Investment projects", which is in the stage of internal discussion and finalization in the RA Ministry of Economy, after which it will be presented to the office of RA Deputy Prime Minister Mher Grigoryan to ensure the further process. |  | In progress | 1. Completion of the review of the Public Investment Management Manual and Joint discussion with relevant stakeholders and WB experts. 2. Circulation of the manual, summarizing remarks and suggestions and submission to the RA Prime Minister's Office. 3. Finalization of discussions on the RA Prime Minister draft decision "On Approval of the Procedure for Assessing the Impact of the RA Public Investment projects and Determining Priorities and Criteria for Evaluating Public Investment projects" and submission to the Office of the RA Deputy Prime Minister to ensure the further process. |  |  | WB
| 47. Capacity building of public investment specialists | 47․1․ Elaboration of a capacity building program for public investment specialists for the training on public nivestment management manual | MoF | - | December, 2020 | The Public Investment Management Manual is approved by the RA Government |  | Lack of relevant specialists for conducting trainings; Inadequate quality of the training organized and modules | Involvement of qualified specialists; Training needs assessment; Review of the training programme and modules |  | To be implemented in the framework of technical assistance | 1․Within the framework of the introduction of the Public Investment Management System, seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy After the seminars / trainings aimed at capacity building, the needs of public investment specialists were assessed in the framework of which the needs of specialists have been identified, particularly in the component of financial calculations. In this regard, the RA Ministry of Finance is expected to be more actively involved in the implementation of the mentioned event. 2. In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the accountability and statistics of the public investments carried out within the framework of the manual, without which it is possible to record a 70% assessment. | December,2020 | In progress | 1․Development of methodology and training program aimed at capacity building of public investment specialists jointly with the RA Ministry of Economy and the RA Ministry of Finance to conduct once again trainings for the representatives of the interested agencies within the framework of the Model form. 2․Finalization of the elaboration of a program for capacity building of public sector specialists as a result of the conducted seminars, trainings and workshops 3․Capacity building of specialists of the RA Ministry of Economy in order to set the necessary criteria for risk management, evaluation of investment projects. 4․Creation of a database of public investment projects in order to increase the accountability and transparency of the processes of implementation of public investment projects. 5․Development of guidelines arising from the manual |  |  | WB
|  | 47.2 Capacity building |  |  | 2020 -2021 | The capacity of public investment specialists is sufficient | [5 empty] | 1. A total of 40 public sector specialists (RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office) were trained and capacity building workshops were held with them within the framework of introduction of public investment management system. 2. During the first half of 2020, 16 seminars-discussions / workshops were organized jointly with the RA Ministry of Economy and WB  This year from January 28 to February 14, 6 working discussions were held in the RA Ministry of Economy with the representatives of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI on the completion of a common model form (hereinafter referred to as the Model Form) quality assessment concept of the investment project in the framework of the introduction of the Public Investment Management System From February 24 to 28, this year 5 seminars-discussions on new initiatives completed by the relevant agencies related to the Model form within the framework introduction of the Public Investment Management System were organized and held in the WB Armenia Office with the participation of the representatives of the interested state agencies, in particular, RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office  On March 12 and 13, 2020, 2 video conferences were held at the RA Ministry of Economy with the participation of the WB experts, with the participation of the employees of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, with the WB experts.  On June 23, 2020 organizing 1 online workshop on economic and financial evaluation of investment projects for the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA MTAI with the initiative of the RA MoE and by the WB experts  Conducting a separate remote discussion with the representative of the RA Ministry of Health, during which the indicators of the investment project provided by the RA Ministry of Health were observed, as well as they were compared with the indicators of a similar program.  An online discussion was held with the relevant representatives of the Ministry of Education and Science of the Republic of Armenia, within the framework of which the investment projects with a large social component were considered in detail, peculiarities of applying the standards applicable to them and elaboration/drafting of these projects. In this context, within the framework of the already established experience, work is being done on the evaluation criteria of large social components - programs that do not have primary economic benefits, but provide secondary benefits. |  | In progress | 1 Within the framework of the 2nd stage of the implementation of the model form, the latter is planned to be circulated among all agencies and conduct of training courses on model form within which it is planned to form target groups for professional discussions. 2. Regular implementation of capacity building and ensuring continuity. |  |  | WB
| 48. The public investment projects included in the 2020 annual budget are prepared in accordance with the requirements of the defined PIM manual | 48.1. Practical application PIM manual in the budget process | MoF | MoE | December, 2021 | The public investment projects included in the 2022 approved budget have been developed in accordance with the requirements of the PIM manual |  | Impossibility of recruiting and retaining qualified staff | Additional incentives created for such employees; Involvement of other employees in the evaluation of investment programmes and in the assessment of the full cycle of programme expenditures Conducting trainings for monitoring of public investment programmes |  | No funding is required |  | Activities haven't started yet | It is risky |  | Within the framework of the measure defined by point 46.3 Strategy Action Plan, the deadline for submitting to approval the PIM manual developed under the responsibility of the RA Ministry of Economy is December 2020. Within the framework of this measure in order to ensure the development of public investment programs in the 2022 budget process in accordance with the requirements of the PIM manual, i.e to integrate the requirements of the PIM manual within the budget process, it is necessary that the relevant institutional mechanisms, functional responsibilities, necessary capacities are developed and available from the beginning of the 2022 budget process. The 2022 budget process will most likely start in December 2020-January 2021. This means that, if the PIM manual is approved within the set deadline, there may be risks in terms of ensuring its effective integration into the budget process within the framework of this measure. On the other hand, depending on the results of the measure defined in point 46, the implementation of this measure may require external technical assistance, about which there is currently no clarity. | In order to reduce the mentioned risks, it is necessary to negotiate with the responsible subdivision of the RA MoE, so that, if possible, the PIM manual is approved earlier than the deadline set by the action plan. On the other hand, depending on the volume and scope of the existing institutional mechanisms, functional responsibilities and capacity changes deriving from the manual, it may be necessary to review andpostpone the deadlines set for the implementation of this measure at the end of the year. Initiate negotiations with PIO to clarify the possibility of technical assistance for the implementation of the measure. | Discussions were held to ensure the practical application of the PIM manual in the budget process, and an agreement was reached with the IMF to carry out this work with the support of the latter.
| 49. Monitoring of public investment programs | 49.1 Monitoring of public investment programs | MoF | MoE | 2022-2023 | Published report on the results of the monitoring of public investment projects |  | Insufficient capacities for monitoring of public investment programmes | Conducting trainings for monitoring of public investment programmes |  | No funding is required | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines. | Activities haven't started yet | It is risky |  | The implementation of the measure depends on the results of the measure mentioned in points 48.1. On the other hand, depending on the outcome of the measure set out in paragraph 48.1, the implementation of this measure may require external technical assistance, of which there is currently no clarity. | Depending on the course of the measure referred to in paragraph 48.1, submit a proposal to review the timing of the measure, as appropriate. Initiate negotiations with GMOs to clarify the possibility of technical assistance for the implementation of the measure. | In order to monitor the implementation of public investment projects, discussions have been carried out and an agreement was reached with the IMF on the implementation of it with their assistance.
12․ FINANCIAL MANAGEMENT IN SELF LOCAL GOVERNMENT BODIES
24. Efficiency of financial management in local self-government bodies | 50. Development of capacities and professional skills of the administrative staff of local self-government bodies | 50.1․ Implementation of public finance management reform program in local self-government bodies | MoF | MTAI | 2020-2023 | Study reports | PI-7 | Lack of technical assistance for rolling out the Public Financial Management Reform Programme in local self-government bodies in compliance with best international practices | Apply to development partners for receiving technical assistance | - | To be implemented in the frame of technical assistance | • Organizing training for the administrative staff of the local self-government bodies of the enlarged communities on program budgeting methodology, its application and raising awareness on PB (about 20 communities in the first half of 2020): • Providing technical assistance և advice to the financial managers of the municipalities and to the staff members involved in the process of preparing the annual program budget: • Providing technical assistance and consulting on the development of a brief annual community program budget and holding public hearings in 52 enlarged communities: • Providing technical assistance and consulting on annual community program budget monitoring and development of evaluation plans in large communities: • Elaboration and publication of a "Residents' Participation in the Local Budgeting Process" participatory budgeting manual (The manual is available): • Elaboration of a manual on “Gender Budgeting at the Community Level” (The manual has been elaborated and is being translated into English): |  | In progress |  |  |  | GIZ
Transparent և participatory budget process plans at the local self government bodie
|  | 50.2․ Monitoring of the public financial management reform program in local self-government bodies and full implementation |  |  |  | Employees of local self government bodies capable of implementing public finance management reforms | [5 empty] | Study of the preliminary status of the use of IFRS-based accounting manual and standards in large communities, identifying gaps and making recommendations for improving the system Study of the preliminary situation of the property management process of large communities, identification of gaps and submission of proposals for the improvement of the system. Preliminary study of the functions, rights and scope of responsibilities of the administrative heads of the settlements of the enlarged communities and submission of proposals for the improvement of the activities. |  | In progress |  |  |  | GIZ
13. EXTERNAL CONTROL AND LEGISLATIVE CONTROL
25. Control of the financial-budgetary sphere by the National Assembly | 51. Provide external control (Reports of annual budget and AC ) | 51.1 Review of annual draft budgets | NA (by agreement), | AC (by agreement) | 2019-2023 | · Տmore effective study of the draft annual budge | PI-18, PI-31 | The RA NA is given insufficient time for thorough review of Draft Annual Budgets and AC financial statement | Effective use of the time provided by the Constitution (from October 1 to the end of the autumn session of the RA National Assembly) to the RA NA for the discussion of draft annual budget; A Budget Office, with qualified and skilful staff, will contribute to effective discussions on annual budget drafts in the RA NA; Implementation of an audit approach for budget execution that will allow to carry out a comprehensive audit of the state budget execution process (for the first quarter, first six months, nine months and one year period), providing an opportunity to the RA National Assembly to review relevant AC studies within a reasonable timeframe | - | To be implemented in the frame of technical assistance |  |  | It is a periodic process | In the RA NA Standing Committees, in their joint sittings, discussions of the preliminary version of the RA budget in the last ten days of August are envisaged, and later discussions of the draft within the terms defined by the legislation.
|  | 51.2 Study of the annual report on the execution of the state budget and AC conclusion on the latter and organizing hearings with audited state bodies |  |  |  | · More Effective Study of AC reports on annual financial statements | [5 empty] | 51.2 Study of report on state budget execution and AC conclusion on the latter and Organizing hearings with audited state bodies • A more effective review of the AC reports on annual financial statements ․Ensuring transparency in external control, legislative hearings on annual budgeting, during which members of non-governmental or civil society organizations can testify : NA (by agreement) 2019-2023 RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2020 state budget execution process. The monitoring was carried out on the basis of inquiries from the Budget Office commission, each month, through the study and analysis of references with comparative analysis. The Budget Office has prepared and provided to the Commission with references with comparative analysis of the collection of state budget revenues for 2020, including operative information on tax revenues and state duties, and according to the process of expenditure directions, as well as the state debt of the Republic of Armenia for 2020 and the main socio-economic indicators; • The annual report on the execution of the RA 2019 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly. The Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly of the Republic of Armenia envisages discussions on the execution of the first quarter of the 2020 state budget, the first nine months of the first half of the year. 2020 | 2020 (In the first half of the year it is provided for the 2019 budget) | It is a periodic process
|  | 51.3 Exercising post-audit control by the Commission |  |  |  | Implement effective post-audit oversight by the Commission | [5 empty] | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, which convened 2 sittings in the reporting period and studied 11 current conclusions of the Audit Chamber. The Standing Committee on Financial-Credit and Budgetary Affairs convened 3 sittings during the reporting period, discussing 3 current conclusions of the Audit Chamber. |  | It is a periodic process
| 52. Capacity building of the Budget Office, NA deputies and experts of committees | 52.1 Institutional-internal capacity building of the budget office | NA (by agreement), | - | 2019-2023 | The budget office has the necessary tools to carry out its functions |  | Budget Office with insufficient number of staff members and capacities | Expansion of functions and responsibilities, and conducting trainings with the aim of enhancement of the Budget Office capacities, involvement of relevant experts in case of necessity |  | To be implemented in the frame of technical assistance | On September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, the 2020-2023 development strategy of the Budget Office of the RA National was approved, according to which in the context of institutional capacity building of the Budget Office it is planned to expand the functions. In particular, 1. Providing information on the observance of fiscal rules to the deputies, factions and standing committees of the National Assembly defined by the Government in accordance with parts 8.2 and 8.4 of Article 21 of the Law on the Budget System of the Republic of Armenia and Part 7 of Article 5 of the Law of the Republic of Armenia on Pulic Debt 2. Providing information to the Standing Committees on the inconsistencies, elimination of distortions, implementation of recommendations in the current conclusions submitted by the Audit Chamber to the National Assembly, 3. Providing opinions to the authors of the draft laws authored by the deputies and factions of the National Assembly on the significant reduction of the state budget revenues or the increase of expenditures 4. Preparation of references on gender sensitivity of state budget expenditures ։ In order to implement the changes defined by the strategy, a legal package of changes has been developed, according to which corresponding changes and additions are envisaged in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly. The package was submitted to the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs for discussion. |  | In progress | The legal package envisaging amendments in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly will be put into circulation by the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs with the expectation of approval by the National Assembly. However, in order to make the most of these changes, it is necessary to study international best practices (for example, Austria, Scotland, Canada, USA) in order to introduce the appropriate set of tools in parallel with the definition of functions. The study of international experience should be carried out through reciprocal visits and the invitation of highly qualified international consultants. In parallel with the expansion of functions, it is necessary to develop the internal capacity of the budget office ։ In particular, it is necessary to 1․ Acquisition or elaboration of models for analysis , 2․ Adobe Illustrator continuous software package maintenance and acquisition of other new software packages, 3․ Staff training, including participation in trainings organized by the best international specialists and leading organizations, training and study visits 4․ Participation in international networks, including the OECD of Parliamentary Budget Offices, Global andregional networks 5. Support to the work of the Budget Office by a highly qualified international expert (preparation of opinions on significant reduction of state budget revenues in draft laws, increase of expenditures, as well as preparation of analytical references on gender sensitivity of state budget expenditures), including involvement of that expert in the work process։
|  | 52.2 Capacity building of NA deputies and experts of committees |  |  | 2020-2023 | The NA deputies and the experts of the committees effectively carry out the study of the draft annual budget, as well as the control over the execution of the state budget |  | Lack of financial resource for organization of trainings | Involvement of technical assistance for conduction of trainings, recruitment of relevant experts as needed, including from the budget office |  |  |  |  | Not started | The Budget Office of the National Assembly of the Republic of Armenia, within the framework of its continuous capacity building function of the National Assembly, envisages seminars, workshops on public finance management, including program budgeting, gender-sensitive budgeting for NA deputies, their assistants, NA staff, standing committees and factions. Within the framework of the UN Development Program "New Armenia - Modern Parliament", trainings are planned for the NA deputies Ժ experts of the committees.
26. Independence of the Audit Chamber and external audit of the government's annual financial statements | 53. Defining and implementing 2020-2023 strategic goals of Audit Chamber ․ | 53.1 Strategy of the RA Audit Chamber and elaboration and approval of action plan for its implementation | AC (by agreement) | - | 2019-2020 | Audit Chamber 2020-2023 ․ Strategy and Action Plan Approved in accordance with ISSAI | PI-30 | Legislative and institutional reforms do not comply with the ISSAI standards | Review of the Law on Chamber of Audit and by-laws within the timeframe established by the Action Plan of the RA AC Strategy |  | To be implemented in the frame of technical assistance | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop և approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation ։ The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed. | The second quarter of 2020 | Completed | It was planned to submit to the Audit Chamber the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and the action plan for its implementation, which was implemented
|  | 53.2 ․ implementation of measures approved by the Audit Chamber strategy for 2020-2023 |  |  | 2020-2023 | The goals set by the strategy are implemented in accordance with the set schedule |  |  |  |  | To be implemented in the frame of technical assistance | drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation include the targets set by these measures | The dates of the measure will be specified in the annual action plan of the strategy, the preparation of which is in progress. | In progress | After the approval of the strategic development plan and action plan for its implementation An annual plan of measures for the implementation of the strategy will be drawn up, which will specify the terms of implementation of these points
| 54.Capacity building of AC staff and Improving professional skills | 54.1 Development and approval of the capacity building program of the AC staff |  |  | 2022-2023 | AC auditors perform audits in accordance with ISSAI standards |  | Insufficient quality of AC audit reports | Training of relevant staff of AC, involvement of experts in case of necessity |  | To be implemented in the frame of technical assistance | Measure 54.1 is included in the draft of the Strategic Development Plan of the RA Audit Chamber for 2020-2023, the draft of the action plan of which defines the terms of implementation of the event envisaged by the PFMS strategy. 5 |  | In progress
|  | 54.2 Capacity building of AC staff and improvement of professional skills |  |  |  | Qualified External Auditors | [5 empty] | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the event envisaged by the PFC strategy. 5 |  | In progress
14. GOVERNMENT FINANCIAL MANAGEMENT INFORMATION SYSTEM (GFMIS)
27. Government Financial Management Information System (GFMIS) | 55.Introduction of the main components of the GFMIS - Phase 1 | 55.1 Revision of GFMIS tender documents | MoF | HTIM | December, 2020 | The complete set of tender documents for the development of the GFMIS tender implementation package has been revised and made complete. | - | Low quality of the GFMIS tender documentation | Conducting expert assessment of GFMIS tender documentation | Chapter 3, point 3.2, paragraph 6 | 15.4 mln. USD including 7.2 mln. USD through the WB PSMP-3 project, 8.2 mln.USD-from Russian Federation | On May 7 of this year, the first stage of the two-stage procurement process for the selection of a consultant assisting the Ministry of Finance in the process of introduction of the GFMIS was organized. By the Decision N 1, dated 05․03․2020 of the two-stage tender evaluation commission approved the pre-qualification announcement for the acquisition of consulting services within the framework of the GFMIS introduction program. 7 organizations applied for pre-qualification, of which 5 became pre-qualified participants. The stage of negotiations with them has started, which is in progress. | The first stage of the two-stage tender for the selection of a consultant in the process of introduction of the GFMIS was held on 07-05-2020. | In progress |  | None |  | WB/RF/MoF
|  | 55.2 Purchase of GFMIS |  |  | 2020-2021 | The complete set of tender documents for the development of the GFMIS tender implementation package is complete, the tender is held |  | The estimated price of GFMIS presented by the consultant exceeds the amount of the WB loan | Negotiating with other donors to provide the gap in the financing | Chapter 8, point 8.2, paragraph 2 |  | The measure will be done after Consultant selection according 55.1 measure |  | Not started |  |  |  | WB/RF/MoF
|  | 55.3 GFMIS introduction testing |  |  | December, 2021 | GFMIS embedded in accordance with the terms of reference |  | The company recognized as the winner of the tender does not ensure the development of a GFMIS software within the timeframe set in the ToR and of appropriate quality | Conducting expert evaluation of reports submitted by the company recognized as the winner of the tender with the aim of quality assurance; Implementing activities aimed at elimination of inconsistencies emerged |  |  |  |  | Not started |  |  |  | WB/RF/MoF
| 56. Introduction of the main components of the GFMIS - Phase 2 | 56.1 Full introduction of GFMIS |  |  | December, 2022 | GFMIS embedded in accordance with the terms of reference |  | Low quality of GFMIS modules | Elimination of inconsistencies by the developing company |  |  |  |  | Not started |  |  |  | WB/RF/MoF
|  | 56.2 Training of GFMIS users |  |  | December, 2022 | GFMIS users are trained |  | Organized trainings do not provide the specialists with sufficient knowledge | Involvement of trainers with necessary skills |  |  |  |  | Not started |  |  |  | WB/RF/MoF
|  | 56.3 GFMIS service |  |  | December, 2023 | Existence of a properly functioning GFMIS automated system |  | Problems emerging in the course of GFMIS maintenance | Eradication of emerging inconsistencies by the maintaining company |  |  |  |  | Not started |  |  |  | WB/RF/MoF