## PFM
REPORT FOR THE FIRST HALF OF 2021 On the implementation of the action plan measures to be implemented in PFMSR 2019-2023
Sector/component | Target | Measures | Performer | Co-performer | Deadline | Deadlines revised by the RA Government Decision N 283 -Լ, dated 04․03․2021 | Outcome evaluation indicators | Progress of measures and done activities/achievements (30.12.2020) | Progress of measures and done activities/achievements (30.06.2021) | Actual execution date | Status (see used terms) | Next steps (activities) | Issues and risks related to measure implementation | Risk management measures | Development partner organization supporting the implementation of the measure present (suggested)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1․ FORECAST of MACROECONOMIC AND BUDGET INDICATORS, FINANCIAL RISK ACCOUNTABILITY
1. Forecast of macroeconomic and budget indicators | 1. Elaboration of final versions of the model (s), introduction in the Ministry of Finance and full operation | 1.1 relaboration of final versions of DSGE models | MoF | - | December, 2019 |  | Availability of up-to-date tools for fiscal policy analysis and medium-term macroeconomic forecasts | DSGE model is elaborated | DSGE is elaborated |  | Completed
|  | 1.2 Introduction and full operation of DSGE models |  |  | 2020-2023 |  | Introduction of new tools and use in the budget process, more comprehensive and accurate estimates and analysis on impact of fiscal policy on the economy | DSGE model was tested and finalized during 2020 (as a result of joint working discussions with IMF experts) . Preliminary versions of relevant documents have been developed. Discussions on the elaboration of a working document and elaboration of separate sections were carried out jointly with IMF experts. With the help of the model, the effects of the coronavirus multifaceted fiscal measures on the Armenian economy were assessed. Based on the results, the 2021-2023 MTEF macro-fiscal framework was created (including the preliminary version of the draft law on the state budget for 2021). Later, in the conditions of new information available and current developments, re-evaluations were carried out through the model, on the basis of which the macro-fiscal framework underlying the 2021 State Budget was formed. An accompanying analytical and evaluation document and model manual has been developed. Discussions on the development of a working document and elaboration of separate sections were carried out jointly with IMF experts. The model assesses the social, economic and financial impacts of the implemented and to be implemented fiscal measures. Based on the results, the 2021-2023 MTEF macro-fiscal framework was created (including the preliminary version of the draft law on the state budget for 2021). Later, in the conditions of new information available and current developments, re-evaluations were carried out through the model, on the basis of which the macro-fiscal framework underlying the 2021 State Budget was formed | In the first half of 2021, the model was used in the process of building the 2022-2024 macro-fiscal framework, a quantitative assessment of the impact of the forecast fiscal measures was carried out, and a forecasting policy scenario was developed. The final documentation of the related analytical-evaluation activities performed during the elaboration of the model, in particular, the article "Estimates of Fiscal Multipliers for Armenia" (Estimates of Fiscal Multipliers for Armenia), as well as development of a manual for using the model was carried out (The article was presented at the 11th annual conference of the Armenian Economic Association). The final editing of the joint working document of the RA Ministry of Finance and the IMF was carried out together with the IMF experts. |  | In Progress | It is envisaged to: a/ continuously apply the model in budget processes (Formation of macro-fiscal framework underlying the MTEF and budget message) b/ use the model for the assessment of policy/measures/shock impacts derived from the imperative of time c/ Publication of the joint work document of the RA MoF and IMF (The Fiscal Strategy Model: A Structural Framework for Fiscal Policy Analysis in Armenia) and the article "Evaluation of the fiscal multipliers of Armenia" | None |  | IMF(RF MOF)
| 2. Assessing the effects of deviations between fiscal policies planned and actually implemented on the basis of macro-founders and fiscal rules | 2.1 . Detection of deviations between planned and actually implemented fiscal policy and impact assessment | MoF | - | 2020-2023 |  | Improved estimates of fiscal risks at the macroeconomic level. | It is envisaged to implement starting from 2021, within 10 days after the publication of the annual state budget indicators, within 15 days after the publication of the annual GDP. | Based on the actual data of 2020, the deviations of the planned and actual fiscal policies and their macroeconomic impacts were assessed. The results of the assessment were presented in the form of a presentation, as well as were included in the annual report of 2020 state budget. |  | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | In the future, it is planned to carry out the activities regularly, each year when the official indicators of the previous year are published. | None |  | IMF
Assessments of the effects of fiscal policy, deviations from the planned ones on the economy
| 3. Ensuring staff with relevant qualifications and skills | 3.1. Implementation of measures aimed at raising the qualification of the staff | MoF | - | 2019-2023 |  | Availability of staff with relevant qualification and skills | During 2020, no business trips were carried out due to the limitations caused by the limitations caused by the coronavirus. In January, only one employee of the Macroeconomic Policy Department was trained within the framework of the trainings organized by IMF in Vienna (JVI). However, employees participated in other available online courses, including regular webinars initiated by JVI. Employees were encouraged through the remuneration fund provided to the department, as well as other promotional methods were applied. | Conditioned by the changes in the IMF training format due to the epidemic, only one employee of the Macroeconomic Policy Department was trained in the JVI organized online course in the first half of 2021. Employees also participated in other available online courses, as well as regular webinars initiated by JVI. One employee of the Department participated in the "Continuous Professional Training Course for Specialists Involved in the Introduction of Public Sector Program Budgeting" and received a certificate. During the first half of 2021, within the framework of bilateral cooperation between the Financial Research Institute of the Ministry of Finance of the Russian Federation 6 employees of the department participated in the regular weekly trainings and discussions under the program "Analysis of the socio-economic indicators of the Republic of Armenia, development and support of the budget revenue forecasting system". |  | In Progress | In case of resuming trainings by international organizations, the staff of the department will also be trained in the format of business trips In the future, it is planned to regularly carry out actions aimed at raising the professional capacity and qualifications of the staff. | None |  | IMF(RF MOF)
| 4. Improving the function of fiscal risk assessment | 4․1 Expanding the coverage of fiscal risk assessment, improving the methodology | MoF | - | 2020-2023 |  | Fiscal risk assessments include an expanded range of fiscal risk sources | Fiscal risk assessments related to the activities of 20 organizations operating in the infrastructure (energy, transport, water economy) sectors were carried out, which also included the analysis of contingent liabilities arising from the contracts of public-private partnership companies. The latter were reflected in the document RA 2021-2023 MTEF (link: http://www.minfin.am/en/page/petakan_mijnazhamket_tsakhseri_tsragre/). At the same time, the work on expanding the scope of assessment of fiscal risk sources continues. | Fiscal risk assessment activities related to the activities of organizations operating in infrastructure (energy, transport, water economy) and other sectors, including the analysis of contingent liabilities arising from public-private partnership format, as well as contracts with the right to purchase electricity; which were reflected in the document of RA MTEF 2022-2024. The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in terms of public-private partnership projects was approved by RA Government decision N1785-Լ , dated 06․11․2020. for the implementation of the functions assigned to the RA Ministry of Finance by the RA Law "On Public-Private Partnership". At the same time, the methodology for setting the maximum permissible limit of RA public-private partnership liabilities was approved by RA Government Decision N955-L, dated 10.06.2021 With the support of ADB consultants the RA Minister of Finance draft Order "On Approving Methodological Guide for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" was elaborated A brief overview of the assessment of the relevant range of specific fiscal risks was implemented. |  | In Progress | Expansion of the scope of fiscal risk assessment sources will continue. | None |  | ADB(IMF)
[7 empty] | Improved fiscal risk methodology | The methodology for calculating and evaluating the contingent liabilities of the Republic of Armenia in terms of public-private partnership projects was approved by RA Government decision N1785-Լ , dated 06․11․2020. With the support of ADB consultants the RA Minister of Finance draft Order "On Approving Methodological Guide for Identification, Assessment, Monitoring and Accountability of Contingent Liabilities under Public-Private Partnership projects and Methodological Tool for Measuring Fiscal Risks, Monitoring and Accountability under PPP projects" | With the support of ADB consultants the RA Government draft Decision "On approving the methodology of calculation and evaluation of RA contingent liabilities on public-private partnership programs" was elaborated and submitted to the RA Government |  | In Progress | Guidelines will be developed for the implementation of the function. after the approval of RA Government draft Decision "On approving the methodology of calculation and evaluation of RA contingent liabilities on public-private partnership programs" | None
| 5. Development of analytical skills of fiscal risk assessment specialists | 5․1 Capacity building | MoF | - |  |  | Specialists with improved analytical skills in assessing fiscal risks | During the second half of the year, 2020, one employee of the department was trained within the framework of the trainings organized in Vienna (JVI). In addition, the relevant specialists of the department (3 specialists) participated in the PFRAM2.0 training course on fiscal risk assessment of PPPs organized by the IMF (developed by the WB և IMF) ։ The employees also took part in the trainings organized by the World Bank in Yerevan. In addition, training is provided as part of ADB's consulting work. | During the first half of 2021 in the scope of online JVI organized courses 2 employees of the Department were traimed, Besides 3 employees of the Deparment participated in "Financial Analysis" and "Financial Modeling" courses organized by the International Academy of Business, as well as in the course on public-private partnership in the scope of the Commercial Law Development Program under the US Department of Commerce. |  | In Progress | The trainings for the purpose of enhancing the professional capacities and qualifications of the personnel are of continuous nature. | None |  | ADB/IMF
2․ STATE REVENUE POLICY, TAX ADMINISTRATION
| 6. Assessing the needs of the tax environment based on the economic development priorities and opportunities | 6․1 Outline directions for further tax system reforms based on economic development priorities and opportunities | MoE | MoHTI, MoE, MoTAI | May, 2020 |  | The directions of further reforms of the tax system are outlined | At present, clarifications are being carried out on the Armenian economic policy, based on which the proposals on further directions of tax reforms will be derived. | As a result of the measure, the RA Ministry of Economy studied the directions of further reforms of the tax system based on the priorities and opportunities of economic development and the directions of the tax system reforms were reflected in the concept of the RA economic policy developed by the RA Ministry of Economy, which currently has the status of the RA Government draft decision. | 2020-12-01 | Completed |  |  |  | (RF MOF)
| 7. Reducing the scope of application of tax benefits | 7.1 Elaboration of the RA draft law "On Making Amendments to the RA Tax Code" | MoF | - | 2020-2023 |  | Low-efficiency, non-targeted tax benefits are eliminated |  | Activities are underway to reduce the scope of application of tax privileges. In particular, the first phase of technical assistance of work with ADB in this direction has been completed, as a result of which a preliminary report has been submitted by ADB experts. As a result of the discussions, the RA Ministry of Finance submitted remarks and suggestions on the Report. The document is currently under study. |  | In progress | Elaboration of an action plan for the implementation of the measure and submission to the RA Prime Minister | None |  | ADB
| 8․ Review of turnover tax burden | 8․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | 2020-2023 |  | As a result of the conducted studies, the turnover tax burden has been revised | The measure is implemented with the technical assistance of ADB, for which relevant international experts were involved, with whom a number of working meetings were held. At the same time, the measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. According to the measures 2 and 3 of the appendix approved by point 1 of that decision, by the third ten days of May 2021, the RA Ministry of Finance must develop draft laws envisaging increase of the turnover tax rates, decrease of the turnover tax threshold. | Work is underway to review the turnover tax burden. In particular, the first phase of the work with the ADB for receiving technical assistance in this direction has been completed, as a result of which a preliminary Report was submitted by ADB experts. As a result of the discussions, the RA Ministry of Finance submitted remarks and suggestions on the Report. The Final Report was submitted by ADB on June 18, 2021, which presented recommendations, analysis, studies and Relevant calculations on turnover tax burden. The Report is currently being studied by us. |  | In progress | Elaboration of an action plan for the implementation of the measure and submission to the RA Prime Minister | None |  | ADB
| 9․ Settlement of issues related to the documentation of transactions for the sale of agricultural products | 9․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2021 |  | Issues related to documenting transactions are settled | Measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to the 6th measure of the appendix approved by point 1 of the same decision, by 3rd ten days of May, 2021 the RA Ministry of Finance should develop a draft law on the regulation of issues related to the documentation of transactions for the sale of agricultural products and submit to the RA Government for consideration. | Activities are underway to resolve issues related to the documentation of transactions for the sale of agricultural products. In this context, please be informed that the measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to Annex 6 approved by Clause 1 of the same Decision it is defined that the RA Ministry of Finance must elaborate and submit to the RA Government a draft law envisaging regulations related to the documentation of transactions for the sale of agricultural products. At the same time, we would like to inform you that in the framework of the mentioned measure, a draft action plan for the implementation of the measures will be submitted by the RA Ministry of Finance to the RA Prime Minister's Office. |  | In progress | Elaboration of an action plan for the implementation of the measure and submission to the RA Prime Minister | None
| 10. Equivalent tax on visible wealth or property | 10․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2020 |  | Visible wealth or property is taxed adequately | On June 25, 2020, the RA National Assembly adopted the RA Law "On Making Amendments to the Tax Code of the Republic of Armenia" aimed at reviewing the real estate tax system. | On June 25, 2020, the RA National Assembly adopted the RA Law "On Making Amendments to the Tax Code of the Republic of Armenia" aimed at reviewing the real estate tax system. | 2020 | Completed
| 11․ Providing legal bases for the introduction of the income declaration system based on the current economic motives | 11․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | MoF | - | December, 2021 |  | Legal bases for the introduction of the income declaration system based on the current economic motives is ensured | The action plan necessary for the introduction of the individual income declaration system was approved by the order No. 104-L of the RA Minister of Finance, dated April 6, 2020. b. Studies of the international experience of the system of income declaration of individuals were carried out and the results were submitted for discussion, c. The RA draft law “On Making Amendments and Addenda to the RA Tax Code” aimed at the introduction of the system of income declaration of individuals has been elaborated. At the same time, please be informed that measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020. In particular, according to the 5th measure of the appendix approved by point 1 of the decision, by the 3rd ten days of September, 2021, the draft law envisaging introduction of the income declaration system based on the current economic motives shoud be elaborated and submitted to the RA Governemnt for consideration. | Work is underway to provide a legal basis for the introduction of an economically motivated income declaration system. In particular: a/ The action plan necessary for the introduction of the individual income declaration system was approved by the order No. 104-L of the RA Minister of Finance, dated April 6, 2020, b. Studies of the international experience of the system of income declaration of individuals were carried out and the results were submitted for discussion, c. The RA draft law “On Making Amendments and Addenda to the RA Tax Code” aimed at the introduction of the system of income declaration of individuals has been elaborated. At the same time, please be informed that measures aimed at reducing the tax policy gap was approved by the Decision No. 1455-L, dated December 30, 2020 In particular, according to the 5th measure of the appendix approved by clause 1 of the Decision, the draft law envisaging introduction of the income declaration system based on the current economic motives shoud be elaborated and submitted to the RA Governemnt for consideration. |  | In progress | Elaboration of an action plan for the implementation of the measure and submission to the RA Prime Minister | None
4. Revenue Transparency and Compliance | 12. Tax potential and gap assessment | 12.1. Assessment of tax potential and gap for the three major types of taxes (VAT, profit tax, income tax) | MoF | - | 2019-2023 |  | Existence of tax potential and gap assessment methodology for three major types of taxes (VAT, profit tax, income tax); Tax potential and gap estimates for the three major types of taxes (VAT, profit tax, income tax) | In the framework of tax potential gap assessment, the RA Ministry of Finance, in cooperation with the RA State Revenue Committee and the RA Central Bank, assessed the tax potential of the Republic of Armenia, the results of which were discussed with the RA Deputy Prime Minister in December 2019. Based on this, agreements were reached and the RA State Revenue Committee was instructed to conduct a study and present its assessments on the tax potential. In this regard, the RA State Revenue Committee in 2020 carried out works on assessing the tax potential on VAT and tax gap, and submitted the results to the Office of the RA Deputy Prime Minister. In order to prove the implementation of the structural benchmark approved in the framework of the program with the IMF, a brief reference on the tax gap assessments and completed activities package of the RA Ministry of Finance and SRC was submitted to the IMF. which were the basis for considering the status of structural benchmarking to be "pending" in the IMF's third review report under the program signed with the IMF and published in December, 2020 . A more comprehensive reference is currently being drawn up on the activities done to assess the tax potential and gap which needs to be submitted to the IMF in order to consider the above structural benchmarl "completed" in future IMF reports. | During the first half of 2021 for the purpose of updating tax potential and gap assessment the RA SRC was requested information which was received and currently is under elaboration. After processing and summarizing the information, 2019 and 2020 tax potential and gap assessment will be implemented. |  | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | After processing and summarizing the information received from the RA SRC, 2019 and 2020 tax potential and gap assessment will be implemented. Using the methodology developed by the RA MoF, it is envisaged to regularly, every year, carry out tax potential and gap assessment work based on the information received from the RA State Revenue Committee. | Activities related to tax potential and gap assessment depend on the process of works to be carried out by the RA State Revenue Committee | Work with the RA State Revenue Committee to obtain the required data in a timely manner. | IMF
| 13․ Publication of information on tax refunds from the budget to ensure transparency of public finances | 13․1 Publication of data on tax refunds from the state budget on a quarterly basis | SRC | - | 2019-2023 |  | Relevant information published | In accordance with the RA SRC Chairman order N 267-A, dated 17.04.2019, the relevant information is published on a monthly basis in the RA SRC official website (http://www.petekamutner.am) in the section "Tax Information", sub-section "Tax Statistics" , part "Tax Statistics data" | In accordance with the RA SRC Chairman order N 267-A, dated 17.04.2019, the relevant information is published on a monthly basis in the RA SRC official website (http://www.petekamutner.am) in the section "Tax Information", sub-section "Tax Statistics" , part "Tax Statistics data" |  | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | Publication of relevant information on a monthly basis. | None
| 14․ Continuous reduction of the shadow economy, exclusion of privileged taxpayers | 14․1 Expand opportunities for access to third party information and for effective use | SRC | - | 2019-2023 |  | Reducing the tax shadow Exclusion of taxpayers with privileged status and creating an equal tax environment for all taxpayers | 1. In order to ensure access to information to the tax authority from third parties on real estate, their owners, property rights, restrictions, limitations and their changes the RA Government draft decision "On making changes and additions to the RA Government decision N 388-N, dated April 6, 2017 " has been elaborated and sirculated since December, 2019. Taking into account the RA MoF standpoint on the draft that these changes should be initiated by drafting the decision of the RA Government Decision "On Making Amendments to the Decision No. 1337-N, dated October 5, 2017", the elaboration of which was initiated in January 2020, however, given that the RA Cadastre Committee developed the draft decision of the RA Government “On making changes in the RA Government Decision No. 388-N, dated April 6, 2017” and put into circulation in February 2020, thus 1337-N draft will be put into circulation once the draft 388-N regulations come into force 2 Within the framework of the draft joint decision of the RA Central Bank and the MoF On approving "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. 3. During the electronic opening of transit declarations for import transactions within the EEU, mistakes are made by the customs authorities of other EEU member states when filling in the transit declarations and in the future, during the closing of declarations in the Republic of Armenia, the information is entered into the "Taxpayer 3" electronic management system with corresponding shortcomings which creates significant inconveniences in the process of comparing and analyzing the information available in the e-management system Given the importance of the issues raised, it was proposed to enable the electronic tax authority to enter accurate data on the import of goods from the EEU countries, in particular, by manually verifying the data in the "Taxpayer 3" e-government system. | 1. The Ra Government draft Decision "On Making Supplements to the RA Governmnet Decision N1337-Ն, dated October 5, 2017" was elaborated by the RA SRC and adopted by the RA Government Decision 159-Ն, dated 11.02.2021, as a result of which the tax authority will be provided with access to information on real estate owners, cadastral assessment. Within the framework of the draft joint decision of the RA Central Bank and the MoF On approving "On Approval of the Procedure for Classification of Financial Assets of Financial Institutions and formation of reserves for possible losses" it has been proposed to submit the information on the pardoned liabilities of the legal entity or sole proprietor, as well as of the pardoned liabilities of individuals who are not sole proprietors or notaries, to the tax authority. It was also proposed to establish a monthly periodicity for the submission of information until the 20th of the month following the given month, taking into account the deadline for submitting the income tax calculation provided for in Article 156, Part 1 of the Code to the tax authority and the need to ensure data compatibility. According to the draft of the amended Decision, the information on the pardoned liabilities of legal entities by individual organizations to individual entrepreneurs will be provided to the RA State Revenue Committee on an annual basis by February 20 of the year following the given year. 3. In accordance with the Clause 122, Annex 1 of the RA Government Decision 596-Ն, dated 19.03.2015, copies of issued construction or demolition permits shall be submitted to the tax authority by the competent bodies issuing construction permits of the Republic of Armenia. There are problems with the format and content of the information presented in this process. In order to regulate the receipt of information, the draft decision on making changes to RA Government Decision No. 596-N, dated 19.03.2015 was developed and put into circulation. By the adoption of the decision, the RA State Revenue Committee will also be provided with information on economic entities that are contractors in the construction of territories. 4․A request was sent to 32 government agencies to assess the scope for expanding information received from third parties and to identify opportunities for further cooperation. Based on the responses received from the authorized bodies, the following directions were outlined for the expansion of the information received from third parties and relevant letters were sent to develop the legal basis for the exchange. a) Information on the owners of vehicles (including legal entities) reflected in the electronic information database of the "Traffic Police" service of the RA Police, as well as the persons operating them (including the addressees of the administrative act) b) Information available in the unified e-government system of civil acts registration in the RA Ministry of Justice c) Fees, dividends and other similar information of citizens submitting declarations in the register of the RA Commission for the Prevention of Corruption d) Information on final acts of public objects approved within the sphere of urban development existing in the RA Urban Development, Technical and Fire Safety Inspection Body, in the field of transport control for taxis of 5-7-seater vehicles, as well as the number of design documents of the objects submitted to the inspection body for the purpose of disclosure. e) RA State Cadastre Committee to get the complete history of real estate transactions: 5. Commission for Prevention of Corruption informed on 13.04.2021 that they can not provide complete data yet, as the database does not provide such an opportunity yet. Work is underway to create a new system. 6․In June, 2021 the tax authority prepared an application for basic interconnection of data belonging to state or local self-government bodies and transfer of personal data for the purpose of using the web services of the Civil Status Acts Registration Agency of the RA Ministry of Justice, the RA Cadastre Committee, and the RA Police. On 25.06.2021, the application was sent to "EKENG" CJSC to ensure the further process. Database interconnection and personal data transfer integration technical manuals of Police, Civil Status Acts Registration Agency and Cadastre were sent to RA SRC by "EKENG" CJSC by email |  | In progress | After receiving the answers to the inquiry to assess the scope of the information received from third parties, measures will be taken to obtain information relevant to the tax control process available in the databases of the mentioned bodies. | None
| 15․ Ensuring timely declaration and fulfillment of tax liabilities by taxpayers in full | 15․1 Modernization and capacity building of tax authority analytical and control tools | SRC | - | 2019-2023 |  | The staff of the tax authority has the necessary capacity to enforce tax legislation There is a revised and constantly improving tax control toolkit | 1.The Order 260-A was approved by the RA SRC Chairman on 23.03.2020 , which provides for the development and automation of risk-taking analytical tools. Built-in "Big Data" analytical processing system (Big Data Analytics - Power BI)is installed, which allows analytical work, creating reports with different criteria. At present, a total of 24 reporting items are included in the analytical system of large databases, including 4 on foreign economic activity. New approaches have been used in the risk management system based on large-scale data analysis to more effectively target risks. 2. The automated system for conducting cameralistic studies has been introduced and tested in the e-government system of the tax authority. During the testing, the problems that hindered the operation of the system were identified, and work is underway to solve them. 3. The current procedure of tax risk assessment carried out during tax administration has been studied in detail and the risk assessment and realization procedure, including the toolkit has been completely revised by the Order No. 195-A, dated February 28, 2020. 4. The current procedure of the automatic monitoring system used during the tax administration has been studied in detail in 2020. The procedure for implementing and monitoring risk assessment was completely revised by the Order No. 300-A, dated April 6, 2020, while partially changing the risk assessment toolkit. At the same time, the criteria for assessing risk based on monitoring results, supplementing the system with new criteria characterizing the real risk of taxpayers was revised by the decision No. 1151-A of the RA SRC Chairman dated 08.12.2020 5.The description of the planning process of complex tax inspections based on risk criteria was studied in 2020 and the new procedure was approved by the order No. 460-A of the head of tax authority, dated May 25, 2020, according to which the priority of inclusion in the annual program of inspections was given to the taxpayers who declared the highest sales turnover, as well as to the taxpayers in the high risk zone. 6. A new automated system of inspections has been launched in the information system of the tax authority since March, 2020 as a result of which it has been possible to selectively include inspectors in complex tax inspections automatically. 7. Regulation on the organization, conduct and realization of tax audits and studies,which, in addition to a number of procedural regulations was reaffirmed by the Order 80-A of the head of tax authority, dated January 30, 2020 which has been adapted to the new structure of the tax authority. 8. The cooperation of the units carrying out tax administration and units carrying out legal, investigative proceedings of the tax body has been regulated by the SRC Chairman Order 419-A, dated May 20, 2020. | 1. The Order 260-А was approved by the RA SRC Chairman on 23.03.2020 , which provides for the development and automation of risk-taking analytical tools. Built-in "Big Data" analytical processing system (Big Data Analytics - Power BI)is installed, which allows analytical work, creating reports with different criteria. At present, a total of 40 reporting items are included in the analytical system of large databases, including 6 on foreign economic activity. New approaches have been used in the risk management system based on large-scale data analysis to more effectively target risks. 2. The current procedure of tax risk assessment carried out during tax administration has been studied in detail and the risk assessment and realization procedure, including the toolkit has been completely revised by the Order No. 195-A, dated February 28, 2020. 3. The current procedure of the automatic monitoring system used during the tax administration has been studied in detail in February-March of 2020 and the procedure for implementing and monitoring risk assessment was completely revised by the Order No. 300-A, dated April 6, 2020, while partially changing the risk assessment toolkit. At the same time, the risk criteria existing in the monitoring center, were supplemented and brought at least to the threshold set by the measurable strategy (61 criteria) by the decision No. 1151-A of the RA SRC Chairman dated 08.12.2020 on making changes to Order 300-А, dated 06.04.2020. In May-June, 2021, a tender was announced for the acquisition of consulting services for the development and introduction of new risk assessment criteria in the above-mentioned automatic notification system. The procurement procedure is at the stage of signing the contract. 4. The description of the planning process of complex tax inspections based on risk criteria was studied in 2020 and the new procedure was approved by the order No. 460-A of the head of tax authority, dated May 25, 2020, according to which the priority of inclusion in the annual program of inspections was given to the taxpayers who declared the highest sales turnover, as well as to the taxpayers in the high risk zone. 5. A new automated system of inspections has been launched in the information system of the tax authority since March, 2020 as a result of which it has been possible to selectively include inspectors in complex tax inspections automatically. 6. Regulation on the organization, conduct and realization of tax audits and studies,which, in addition to a number of procedural regulations was reaffirmed by the Order 80-Ա of the head of tax authority, dated January 30, 2020 which has been adapted to the new structure of the tax authority. 7. The cooperation of the units carrying out tax administration and units carrying out legal, investigative proceedings of the tax body has been regulated by the SRC Chairman Order 419-А, dated May 20, 2020. |  | In progress | The analytical tools will be constantly adapted to the current legal regulations | None |  | IMF
3․ STRATEGIC PLANNING, DRAWING UP MEDIUM-TERM EXPENDITURE FRAMEWORK AND STATE BUDGET
| 16․ Objectives and results of all budget programs included in the 2023 state budget are in line with existing sectoral strategies and cover all existing strategies that have an impact on budget revenues and expenditures | 16․1․ Review / develop budget programs in line with existing strategic policy | MoF | SBs | 2020-2022 |  | Availability of conformity assessment | By RA Prime Minister By Recommendation No. 02 / 08.5 / 35060-2020, dated 21.07.2020, all SBs were asked to harmonize the financial assessments of the sector strategies with the MTEF. As of 13.08.2020, the measure is implemented in 18 out of 46 SB having submitted the report on PFMSR progress report and the presented budget programs correspond to the policy directions defined by the main strategies of the PA. Work is underway in 28 bodies to implement the measure: analysis of budget programs from the point of view of compliance with existing strategic documents is carried out. 2 There is a process of reviewing strategies / policy directions in connection with the reorganization and legislative changes in the SB. The responsible unit of the RA Ministry of Finance has developed a measure of self-assessments of the conformity of the sectoral policy of the public authority and the compliance of the budget programs, which has been filled in by the public authorities and submitted to the MoF. | In the framework of the measure with the support of the UNDP, an inventory of the RA strategic documents is carried out, the policy frameworks defined by them (goals, results, targets, etc.) are mapped, and the compliance of the budget programs related to them is assessed. |  | In Progress |  | None |  | IMF(UNDP/RF MOF)
All the programs included in the 2023 state budget are in line with the existing strategies
The 2023 budget programs fully cover all existing strategies that have an impact on budget revenues and expenditures.
All programs included in the 2023 state budget (except for administrative programs) have program passports, which are submitted to the RA NA together with the 2023 ․ draft state budget
|  | 16․2 Identification and regulation of practical problems related to the current PB methodology and its application | MoF | - | 2020-2022 |  | Existence of a report on the study of the PB methodology, the existing gaps related to its application | The measure is implemented with the technical support of the IMF, within the framework of which IMF experts conducted a study of the gaps and problems of the PB methodology and its application. The preliminary results of the study, including the recommendations on measures to improve the application of the "B methodology" were submitted to the MoF: The MoF is currently studying the assessments presented by the experts, the approaches and the issues of their practical application. At the same time, it is envisaged that in parallel with this work, self-assessments will be carried out on the gaps and problems of the introduction of the PB methodology in the state bodies, and its application. Based on the results of the above-mentioned external assessments and self-assessments, a schedule of measures to improve the application of the PB methodology will be developed as necessary. | The measure is implemented with the technical support of the IMF, within the framework of which IMF experts conducted a study of the gaps and problems of the PB methodology and its application and suggestions were made to improve the PB methodology . At the same time, self-assessments were carried out in state bodies in the format provided by the RA MoF, which are being summarized. |  | In Progress | Based on the results of external evaluations and self-assessments, a list of measures and schedule of PB methodology and a list of measures to improve its application will be developed. | None |  | GIZ(IMF/RF MOF)
Existence of list of measure and schedule of PB methodology and its application improvement
The measures to improve the PB methodology are implemented in accordance with the schedule of measures
|  | 16․3․ Measures aimed at developing human resources | MoF | - | 2020-2023 |  | Institutional Capacity Assessment Report on Existing Human Resources (s) in line with the PB embedded system requirements | The possibility of being provided with external technical assistance for the implementation of the institutional capacity assessment of the existing human resources and for the implementation of the elaboration of capacity building program in accordance with the requirements of the embedded PB, is currently being discussed with partner international organizations. It is envisaged that in parallel, internal assessments of the relevant capacities in the state bodies will be carried out. Based on the results of the above-mentioned external-internal evaluations, an appropriate capacity building program will be developed. | In the framework of the measure, self-assessments were carried out in the state bodies on the basis of the self-assessment format of deficiencies and gaps provided to the state bodies, including in terms of human resource capacity, which are being summarized At the same time, within the framework of the "Program of measures aimed at capacity building of human resources in the RA state bodies from the point of view of full implementation of program budgeting" defined by the RA Government Decision No. 1223-L dated 12.09.2019, continuous professional trainings in the field of CB are regularly carried out. |  | In Progress | Based on the proposals received from the DPOs and state bodies, a human resource development program in the PB direction will be developed as needed. | None |  | (IMF/WB)
Availability of an up-to-date capacity building program
Capacity building activities are implemented in accordance with the approved program
| 17․ As of the end of the 2023 budget year, there is a regular budget program evaluation process in all state bodies responsible for budget programs. | 17․1․ Development of budget program evaluation guidelines | MoF | - | December, 2022 |  | The concept of evaluating budget programs is available | Within the measure the activities for elaboration of the budget program monitoring and evaluation concept, methodology, as well as the system introduction measure schedule are being implemented with the technical assistance of GIZ. In the scope of the technical assistance, the draft budget program monitoring, evaluation concept has been elaborated and submitted to MoF which is currently being studied and discussed by the MoF. After clarifying the approaches to the concept, the relevant methodology and action plan will be developed by the experts. | Within the framework of the technical assistance of the GIZ, a draft methodology of the budget program monitoring and evaluation concept was elaborated by the experts. The documents are currently under discussion. |  | In Progress | Finalization of project evaluation concept and methodology documentation projects and their piloting | None |  | GIZ
Budget program evaluation guidelines have been developed
|  | 17․2․ Introduce a process of regular evaluation of budget programs | MoF | SB | December, 2023 |  | Existence of a schedule and measures for the implementation of budget program evaluation functions | The activities to be carried out within the framework of the event are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. | The activities to be carried out within the framework of the measure are the activities for the introduction of the monitoring of the budget programs to be developed within the framework of the 17.1 measure, the evaluation concept, methodology and the schedule of measures. The latter is a logical continuation of the above-mentioned measure, it will be implemented based on the results of that measure. |  | Not started |  | None |  | GIZ
As of the end of the 2023 budget year, each state body responsible for budget programs has a regular program evaluation process.
As of the end of the 2023 budget year, at least 1 budget program implemented by each state body responsible for budget programs has been assessed experimentally in accordance with the approved guidelines.
6. MTEF process, budget disciplinary and transparency | 18․ Programs / measures arising from the manadatoy obligations of the state are identified and registered | 18․1 Identification and registration of programs / measures arising from the mandatory obligations of the state | MoF | SBs | December, 2021 |  | Appropriate methodology is available and procedures are elaborated | The methodological instructions for preparing and submitting budget applications in the framework of the 2021 and 2022 budget processes already contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. The programs / measures arising from the mandatory obligations of the state within the 2021 budget process have already been identified in accordance with the current methodology. At present, work is being carried out with the technical assistance of the IMF to improve the above-mentioned methodology and its application, within which a document of studies and recommendations has been submitted to the RA MoF. The document is currently being studied and discussed by the MoF. After clarifying the approaches to the methodological issues presented in the document, if necessary, necessary work will be undertaken to review the methodology for identifying and registering the programs / measures arising from the mandatory obligations of the state, and to localize the new methodology. | The methodological instructions for preparing and submitting budget applications in the framework of the 2021 and 2022 budget processes already contain the methodology for identifying and accounting for programs / measures arising from the mandatory obligations of the state. The programs / measures arising from the mandatory obligations of the state within the 2021 budget process have already been identified in accordance with the current methodology. At the ame time, work is being carried out with the technical assistance of the IMF to improve the above-mentioned methodology and its application, within which a document of studies and recommendations has been submitted to the RA MoF, as well as on July 28, 2021, the pilot work on the separation of mandatory and discretionary budget expenditures according to the methodology proposed by the IMF was launched, following the example of the budget programs of the RA MoF. |  | In Progress | As a result of piloting, review of the mandatory և discretionary budget expenditure classification methodology as needed (as needed). | None |  | IMF
In the framework of the 2022 budget process, the mandatory obligations of the state are identified and registered
| 19. Introduction of a single process of drafting the MTEF and annual budget | 19.1․ Creating a legal basis and elaborating methodology for ensuring a single process of drafting the MTEF and annual budget | MoF | - | 2021 |  | The single process of drafting the MTEF and annual budget is carried out | Since 2020 the MTEF and annual budget drafting is being carried out in a single process for which the schedules established by the RA Prime Minister's decisions on starting the budget processes of 2021 and 2022 serve as a legal basis. After summarizing the results of the 2021 budget process, the expediency of making relevant amendments to the Law "on the Budgetary System of the Republic of Armenia" will be considered. Accordingly, if necessary, a package of relevant changes will be developed and submitted for approval. | Since 2020 the MTEF and annual budget drafting is being carried out in a single process for which the schedules established by the RA Prime Minister's decisions on starting the budget processes of 2021 and 2022 serve as a legal basis. | 2021-06-01 | Completed |  |  |  | IMF
| 20․ Simplified budget and simplified budget execution reports are available to public | 20․1 Elaborating and publicizing the simplified version of the state budget and the budget execution report | MoF | - | Within one month after the adoption of the 2021 RA state budget (Publication of the Simplified Budget) 2021 (Publication of simplified budget report ) |  | Simplified Budget for 2021 and Budget Execution Reports are published on the official website of the MoF Discussions have been held with CSOs on simplified budget and budget execution reports (at least twice a year) | Within the framework of the measure, according to the schedule approved by the RA Prime Minister's decision N 5-A , dated January 9, "On starting the 2021 budget process", it is defined that within ten days after the adoption of the law on the 2021 state budget, the RA MoF develops and publicizes the citizen's budget for 2021: For this purpose, with the support of the GIZ the methodological instructions for the preparation of sectoral budget projects by the state bodies within the framework of the drafting of the RA 2021 draft state budget and MTEF 2021-2023 were elaborated posted on the official website of the MoF link: http://www.minfin.am/website/images/website/documents/Metodakan2021%20(2).docx), as well as it was officially provided to the public authorities. Based on the information provided to the Ministry of Finance by state bodies in accordance with the methodological guidelines for the preparation of sectoral draft budgets "Citizen Budget 2021" was elaborated and published on the official website of the Ministry of Finance. (available at the following link: https://minfin.am/website/images/website/byuje%20ev%20krknaki%20harkum/Citizen_budget_Final_V%20_01.02.2021_compressed.pdf ): | In the framework of elaboration of draft MTEF 2021-2023 and RA 2021 state budget based on the information provided by state bodies to the RA Ministry of Finance in accordance with the methodological guidelines for the preparation of sectoral drafts of the Citizen's budget, “Citizen’s Budget 2021” was elaborated by the RA MoF and published on the official website of the RA MoF (https://minfin.am/website/images/website/byuje%20ev%20krknaki%20harkum/Citizen_budget_Final_V%20_01.02.2021_compressed.pdf). After the approval of the report on the execution of the state budget for 2020, a simplified version of that report was elaborated and posted on the official website of the RA Ministry of Finance (https://minfin.am/hy/page/2020_tvakani_petakan_byujei_parzecvats_hashvetvutyun) | January 2020, June 2020 | It is a periodic process (The actions planned for the first half of 2021 have been carried out) |  | None |  | (RF MOF)
| 21. Civil society organizations are more actively involved in the budget process | 21.1.Disclosure of information on budget proposals | SBs | - | 2020-2023 |  | RA state bodies have platforms to discuss budget proposals with CSOs. | The measure on the 2021 budget process has been implemented. According to the schedule approved by the RA Prime Minister's decisions on starting the RA 2021 and 2022 budget process, clear requirements are set for posting the budget proposals of the RA state bodies on their websites, holding discussions with CSO on budget proposals and submission to the RA MoF Information on the results of those discussions together with the proposals. The measure on the 2021 budget process has been implemented. In order to ensure the public discussions on budget applications of state bodies, with the support of the GIZ, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting state budgets (link: http://www.minfin.am/ website / images / website / byuje_amsakan / PB% 20instructions% 20for% 202021% 20budget% 20process-1% 20 (1) .docx): The latter were posted on the MoF official website and provided to all state bodies. At the same time, according to the preliminary agreement with GIZ it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the budgeting process. | The measure was implemented in terms of 2021 - 2022 budget processes. According to the schedules approved by the RA Prime Minister's decisions on starting the budget processes of the Republic of Armenia for 2021 and 2022, clear requirements have been set for posting the budget applications of the state bodies on their websites, discussing the budget applications with CSOs and submitting the information on the results of those discussions together with the applications to the RA MoF. According to the schedules approved by the RA Prime Minister's decisions on starting the budget processes of the Republic of Armenia for 2021 and 2022, clear requirements have been set for posting the budget applications of the state bodies on their websites In order to ensure the process of public discussions on the budget applications of state bodies, with the support of the GIZ, the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of MTEF and budget programs of state bodies within the framework of drafting the draft state budget (http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA Ministry of Finance and provided to all state bodies. | January 2020, June 2020 | (The actions planned for the first half of 2021 have been carried out) |  | None |  | (RF MOF)
|  | 21.2. Establishment of a platform (s) for discussing budget proposals with CSOs | SBs | - | 2020-2023 |  | The budget proposals of the RA state bodies include the results of the discussions on the applications with the CSOs. | According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9 "On starting the budget process of the Republic of Armenia for 2021", a requirement was set by state bodies to place their budget applications on their official websites. In order to ensure the process of public discussions on budget proposals of state bodies, with the support of GIZ the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF 2021-2023 and 2021 state budgets (link http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA MoF and provided to all state bodies. At the same time, according to the preliminary agreement, within the framework of the GIZ support, it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the state budgeting process. According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. Nevertheless, conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process. Conditioned by that, according to the methodological instructions of MTEF 2022-2024 (including the state budget of the Republic of Armenia for 2022), it is envisaged that state bodies will organize discussions with CSOs. | According to the schedule approved by the RA Prime Minister's decision N 35 -A, dated January 9 "On starting the budget process of the Republic of Armenia for 2021", a requirement was set by state bodies to place their budget applications on their official websites. In order to ensure the process of public discussions on budget proposals of state bodies, with the support of GIZ the RA Ministry of Finance has developed methodological guidelines for ensuring public participation in the process of elaboration of budget programs of state bodies within the framework of drafting MTEF 2021-2023 and 2021 state budgets (link http://www.minfin.am/website/images/website/byuje_amsakan/PB%20instructions%20for%202021%20budget%20process-1%20(1).docx): The latter were posted on the official website of the RA MoF and provided to all state bodies. At the same time, according to the preliminary agreement, within the framework of the GIZ support, it is planned to design and develop an electronic platform / toolkit for ensuring the participation of CSOs in the state budgeting process. According to the schedule approved by the RA Prime Minister's decision N 5 -A, dated January 9, 2012 "On starting the budget process of the Republic of Armenia 2021" it has been defined that in the framework of the elaboration of the draft MTEF (including the RA 2021 state budget), the state bodies hold discussions on budget proposals in the spheres under their competence with interested CSOs (including a summary of comments submitted, acceptance or rejection of proposals) will submit the information to the MoF. | January 2020, June 2020 | It is a periodic process (The actions planned for the first half of 2021 have been carried out) |  | Conditioned by the coronavirus in the Republic, the state bodies did not discuss their budget proposals with CSOs as part of the 2021 budget process. | Fixing mandatory requirements for conducting discussions with CSOs on budget proposals of state bodies within the framework of each annual budget process the requirements for publicizing its results in the Law "On the RA Budget System ". The corresponding draft has been developed and it is envisaged to submit it to the RA NA for approval along with the draft law on the RA 2021 state budget. | GIZ (RF MOF)
7․ Automate the process of calculating the cost of budget programs | 22. Within the framework of the 2023 budget process, the processes of calculation (expenditure) of budget programs / measures are carried out through a unified automated system. | 22.1 Step by stem introduction of Automated system of calculating the cost of budget programs | MoF | - | Within one month after the adoption of the 2021 report on the execution of the RA state budget July |  | The automated budgeting system has been tested and is ready for implementation. Within the framework of the 2023 budget process, expenditure budgeting were implemented through an automated expnditure budgeting system. | The elaboration and testing of the automated budget expenditure planning system by the RA Ministry of Finance (Authorized Body) has already been completed in December 2019. The system allows applicant bodies to submit online cost-benefit calculations online as part of budget funding applications using pre-designed batch and quota agreed with the Authorized Body in formats preliminary elaborated by applicant bodies and agreed with authorized body , as well as enables the respective competent users of the applicant body and the authorized body approve / reject, as well as summarize the data of the received proposals according to the program, operational-economic classifiers, allowing to receive the necessary details of the openings of the numbers of programs / measures. In 2020 professional meetings were held with the representatives of the applicant bodies on the elaboration of templates for the calculation and substantiation of expenditures on the programs and measures included in the budget proposals. During the training after it, the RA MoF together with the applicant bodies, started the work of elaborating and submitting the templates to the RA Ministry of Finance. All samples agreed and approved by the RA MoF have already been imported into the System. At the same time, based on the data provided by theapplicant bodies, users were created in the system, defining the relevant authorities. | In 2019, an automated budget planning system (hereinafter referred to as the System) has been developed, the testing and introduction of which is currently being implemented in the territorial administration bodies of the RA public authority As part of this work, online trainings were conducted with all applicant bodies on the use of the automated system for the introduction of cost calculation-justification and budget program costing in terms of programs and measures included in the budget applications. |  | In Progress | Operation of an automated budget processing system.
4․ BUDGET EXECUTION PROCESS CONTROL, TREASURY SYSTEM
8. Budget Execution Reports | 23. Preparation of reports on the execution of the RA state budget by program classification | 23․1 Adaptation of the electronic budget reporting system to the requirements of program budgeting | MoF | - | December, 2019 |  | Existence of reports on the RA state budget execution by program classification | The measure is completed, and the reports on the execution of the first quarter of the RA 2019 state budget in program format on the execution of both financial and performance indicators have been submitted by the bodies responsible for the execution of the programs through the electronic budget reporting system. Before that, the system was tested, on April 1-3, 2019 trainings were organized for 64 specialists responsible for preparing report, the system was introduced in all state bodies, and the latter were assisted in the introduction and operation of the system. As a result, the quarterly (incremental) reports on the execution of the RA 2019 state budget were submitted to the RA Prime Minister's Office in program format. During the year, activities have been carried out to solve the problems identified during the operation of the system. | The measure is completed, and the reports on the execution of the first quarter of the RA 2019 state budget in program format on the execution of both financial and performance indicators have been submitted by the bodies responsible for the execution of the programs through the electronic budget reporting system. | 2019 | Completed
9. Arrears monitoring and management | 24. Arrears monitoring and management | 24.1 Registration of expenditure arrears | MoF | SB | 2020-2023 |  | The RA public authorities and territorial administration bodies carry out the registration of arrears on expenses | The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses. Each year the chief budget executive body submits to the Budget Execution Department information on the absence of arrears on state budget expenditures | The measure is on regular basis. The RA public authorities and territorial administration bodies carry out the accounting of arrears on expenses. Each year the chief budget executive bodies submit to the RA MoF information on the arrears related to state budget expenditures. Information on arrears is included in the relevant reports on the exeution of the RA state budget. | 2020 | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | Identifying and neutralizing the risks of incurring arrears | None
Information on arrears is included in the reports on RA State Budget execution
10. Payroll controls | 25. Personnel records and payroll data coordination and implementation of changes in the accounting information system | 25․1 Elaboration of a system for integration of the human resources database into accounting software / AS modules | SB | CSO | 2020-2023 |  | Terms of reference for human resource database / accounting information program module integration system is elaborated and approved | As of 2020 In 5 SBs the system is embedded, all the processes related to the personnel registration and salary fund data are carried out through the system, activities are being carried out for system introduction in 5 SBS, in 2 SBs there is an issue of software, terms of reference is being elaborated. The other SBs did not provide information on the measure implementation. According to the information provided by the CSOs, terms of reference of integration system of human resources database with accounting Information System Module was developed for the implementation of the event. The latter stipulates that the relevant employee of the accounting unit will receive an automatic notification about the necessary function performed by the personnel management units in order to make the required changes in the electronic accounting program. | In order to develop the best mechanism for data transfer between the Civil Service Information Platform (hereinafter the Platform) and the accounting information systems used in state bodies, and to ensure its further implementation, discussions were organized with the participation of representatives of the RA MoF, Civil Service Office and Platform development company representatives. As a result of the discussion, a working group was set up to systematically organize the work aimed at achieving the goals set within in the framework of this measure. The working group has already carried out a number of activities. At the same time, the data entry on civil servants on the Platform, as well as the detection and improvement of the system as a result of its operation, continued. |  | In Progress | It is on the agenda of the working group set up to achieve the goals within the framework of this measure to study the accounting information systems used (if available) in public bodies for comparing the data (fields) in those systems with the human resources database (data) on the Platform. In order to implement the above-mentioned steps, a discussion was initiated with the participation of the specialists developing the "Armenian Programs" accounting program and the members of the above-mentioned working group. | None
|  | 25․2 Introduction and maintenance of the system |  |  |  |  | The system is embedded and all processes related to personnel records and payroll data are carried out through the system | The system was launched in the fourth quarter of 2020, and data entry by government agencies on the information platform is currently underway. At the same time, the system is in re-testing process in order to identify problemns and give them relevant solutions.
| 26. Payroll audit | 26․1 implementation of payroll audit by the Internal Audit | MoF | SB, CSO | 2021-2023 |  | Data transfer and comparison deficiencies are identified | Payroll audit was not carried out in most of SBs having provided information, due to liquidation of the internal audit unit and following the long-term process of organizing procurement procedures and concluding contracts as a result of oursourcing the function. At the same time, payroll audit is envisaged in the annual Internal Audit Plan for 2021 in 11 PMs that provided information. | A corresponding working group has been set up jointly with the Civil Service Office of the RA Prime Minister Office to identify shortcomings in the transfer and comparison of salary data. Within the framework of the measure, the RA state bodies were offered to envisage the implementation of salary audits in the annual internal audit work programs. In 36 of 48 state bodies it is already planned to oerform salary audit by the 2021-2022 annual program. |  | In Progress |  | None
The reports provide recommendations on payroll control
| 27. Ensuring the accountability of the calculation of salaries and equivalent payments | 27.1 Notification of data on calculation of salaries equivalent payments and received income received to employees, | MoF | SB | 2021-2023 |  | Employees receive monthly information on the calculation and payment of income received during the previous month | As a result of the changes initiated in the employee remuneration calculation program in the RA Ministry of Finance, starting from March 2020, employees receive information on the income received during the previous month by e-mail every month. Steps have also been taken in the SBs to make changes in the AS, as a result of which employees will receive electronic information on salaries during 2020. | Steps have been taken in the PBs to make changes in AP, as a result of which employees will receive electronic information on salaries during the first half of 2021. |  | In Progress | Inform the PBs and the CSO by the letter of the RA Minister of Finance on taking measures to ensure that the employees are provided with appropriate notices in the process of calculating their remuneration. Monitoring of steps taken by PBs and CSO. If necessary, initiate the recommendation of the RA Prime Minister to ensure the measure | None
5. PUBLIC DEBT
11. Public debt management | 28. Improving the RA Law "on Public Debt" | 28․1 Conformity of the RA Law "on Public Debt" to the standards applied by international financial institutions | MoF | - | December, 2022 |  | Improving debt statistics by clarifying the definitions used in the RA Law on Public Debt ("Public Debt" and "Government Debt") | The preliminary version of the RA draft Law "On Public Debt" has been elaborated. Discussions are underway with international financial institutions to obtain technical assistance for the implementation of the measure | The preliminary version of the RA draft Law "On Public Debt" has been elaborated. Discussions are underway with international financial institutions to obtain technical assistance for the implementation of the measure |  | In progress | As a result of discussions, the RA draft law "On Public Debt" will be finalized | Further delays in receiving technical assistance may pose risks for the timely implementation of the measure (December 2022). | Rapid organization of activities arising from technical assistance. | (ADB/WB/EU)
| 29. RA Government debt portfolio exchange rate risk mitigation | 29․1 Increasing the share of deficit financing in the state budget each year at the expense of net domestic borrowing | MoF | - | December, 2023 |  | The share of deficit financing in the state budget at the expense of net domestic borrowed funds is at least 50.0% | The share of deficit financing in the state budget at the expense of net domestic borrowing was 84.7% in 2020 | The share of deficit financing in the state budget at the expense of net domestic borrowing was 84.7% in 2020 | July 10 2020 | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | Deficit financing program in the 2021 state budget at the expense of net domestic borrowing makes 43.9% due to the issuance of large volume of Eurobonds , however, the share of actual performance by the end of the year is projected to be at least 50.0% due to underperformance of PIU programs. The weight of deficit financing in the RA 2022 and 2023 draft state budget at the expense of net domestic borrowing will be presented in the term defined by the order of the RA Minister of Finance, in accordance with the target | None
6. PUBLIC SECTOR ACCOUNTING
12. Public Sector Accounting | 30. Monitoring the annual financial statements of public sector organizations | 30․1 Monitoring the financial statements of public sector organizations by the MoF | MoF | - | 2019-2023 |  | · Financial statements in accordance with the RA Public Sector Accounting Standard (IAS) | In April 2020, a letter was sent to public sector organizations to submit their 2019 transaction log and financial statements for monitoring purposes. The already submitted financial statements are monitored, and after summarizing the results, they are submitted in writing to the relevant public sector organizations. At the same time, based on the monitoring results the 9th և 10th issues of the Professional Directory were prepared in 2020 and sent to the public sector organizations. | The measure is on regular basis Monitoring of 2020 operations logs and financial statements of public sector organizations has been implemented, as well as the 11th issue of the Professional Newsletter was prepared and provided to public sector organizations. | 2020 | It is a periodic process (The actions planned for the first half of 2021 have been carried out) | At the end of each year, public sector organizations submit the package of their operations log and financial statements which are monitored by the RA MOF. Errors and inaccuracies in the above information are identified and reported to the appropriate organizations to avoid similar errors in the future. | None
|  | 30․2 Methodology review (as needed) | MoF | - |  |  | Improved regulatory framework | The draft law "On Making Amendments to the Law on Accounting of Public Sector Organizations" has been developed by the Ministry of Finance which has been approved by the RA NA bu first reading on September 18, 2020. | The RA law ՀՕ-84-Ն "On Making Amendments to the Law on Accounting of Public Sector Organizations" elaborated by the RA MoF was adopted by the RA National Assembly on March 4, 2021, as well as a number of by-laws have been developed and approved on the basis of these changes. | 2021-03-01 | In progress | A review of the public sector accounting methodology will be carried out if needed | None
|  | 30.3 Implementation of the qualification process for chief accountants of public sector organizations | MoF | - | 2020-2023 |  | Qualified Chief Accountants of Public Sector Organizations | During 2020, 10 qualification exams for public sector accountants were held, as a result of which 54 people were qualified. | During the first half of 2021, 27 qualification exams for public sector accountants were held, as a result of which 112 people were qualified. Currently, 166 people are qualified as public sector accountants in Armenia. | 2020 | It is a periodic process (The actions planned for the first half of 2021 have been carried out) |  | None
| 31. Preparation of interim consolidated financial statementss at the ministries level | 31․1 Development of a methodology for consolidating financial statements | MoF | - | 2022-2023 |  | Consolidation methodology is available | The draft consolidation methodology has been developed and will be reviewed by international experts within the activity for the introduction of the GFMIS. | The draft consolidation methodology has been developed and will be reviewed by international experts within the activity for the introduction of the GFMIS. |  | In progress |  | None |  | (GIZ/WB)
|  | 31․2 Development or acquisition of a joint computer program for the purpose of consolidation | MoF | - |  |  | Computer program necessary for consolidation | this measure is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. | This measure is also part of the GFMIS as the consolidation of financial statements is a separate module of the GFMIS. |  | In progress |  | None
|  | 31․3 Preparation of interim consolidated financial statements at the ministries level | MoF | - | December, 2023 |  | Interim consolidated financial statements at the ministries level are submitted | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. |  | Not started |  | The implementation of the measure depends on the implementation of the measures mentioned in 31.1 and 31.2. | Depending on the course of the measures mentioned in points 31.1 and 31.2, submit a proposal, if necessary, to review the deadlines for the implementation of the measure.
7. CORPORATE ACCOUNTING AND AUDIT
13. Regulation of corporate accounting and audit activity | 32. Introduction of public control system over accounting and auditing activities | 32․1 Completion of the necessary sub-legislative framework | MoF | - | 2020-2021 |  | New specialized structures for sector regulation and control - Public oversight board model | The RA Government decision 1336-N, dated August 13, 2020 "On Defining the Procedure for Determining Compliance with the Requirements of the Legislation Regulating the Accounting Sphere of Computer Software Enabling Accounting" was elaborated and approved. 4 sessions of public oversight board were held as a result of which Decision 1-Լ "On defining the Procedure for Maintaining the Register of Auditors, Expert Accountants, Audit Organizations, and Minimum List of Data Included in It" was adopted on August 31, 2020 and Decision 2-Լ "On approving the decision N 6-L of October 26, 2020 of the Board of the Chamber of Auditors and Expert Accountants of Armenia" was adopted on November 11. Legal acts related to the extension of qualification certificates of accountants and auditors have been developed and approved. The draft decision of the AOB "On approval of the procedure for conducting mandatory inventory of assets and liabilities" has been developed, which is currently under discussion. | In order to regulate the areas of accounting and auditing activities, the RA Audit Chamber, expert accountants, have developed a number of legal acts, which have been submitted to the Public Oversight Board of Accounting and Auditing activity for approval. During the first half of 2021, 3 sessions of the Oversight Board took place, as a result of which 8 decisions of the Oversight Board were adopted. At the same time, the legal acts related to the extension of the qualification certificates of accountants and auditors were elaborated and approved. |  | In progress | In the near future, it is planned to discuss the draft legal acts elaborated by the Audit Chamber and Expert Accountants and approval by the Public Oversight Board in accordance with the established procedure. |  |  | (WB/RD MOF)
Effective audit quality control system
adjusted scope of organizations subject to mandatory audit
|  | 32․2 Staff training |  |  |  |  | Appropriate level of capacity | During 2020, remote seminars were organized for the employees of the RA Ministry of Finance on the requirements of the main provisions of the new laws regulating the areas of accounting and auditing. | No trainings have been held during the first half of 2021 |  | In progress | The measure is on regular basisn. In the near future it is planned to organize seminars for staff training.
8. FINANCIAL MANAGEMENT AND CONTROL OF STATE ORGANIZATIONS: STATE NON-Commercial ORGANIZATIONS (SNCO)
14. Financial Management and Control of state organizations accountability of state non-commercial organizations | 33. Improving the system of accountability and monitoring of the financial and economic activities of SNCOs | 33․1 Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | MoF | - | 2020-2023 |  | Availability of an up-to-date system for monitoring the financial and economic activities of SNCOs | In order to implement reforms in the system of public financial management, a system of fiduciary control of state non-commercial organizations has been developed since 2010 in the field of financial management and control of state organizations. In view of testing the elaborated system in practice and elaborating fiduciary control effective system, In 2010, the RA Government, with the support of the World Bank, initiated the "Piloting of Fiduciary Control Systems of SNCOs" project. At this stage, the elaborated system is being studied, work is being done to modernize it and bring it in line with the current system of SNCO activities. Studies have been conducted in the field of activity of state non-commercial organizations in order to elaborate a system of non-financial (productive) indicators. | Studies have been conducted in the field of activity of state non-commercial organizations in order to elaborate a system of non-financial (outcome) indicators. |  | In progress | It is planned to implement the measure within the ADB technical assistance. |  | Continue negotiations with PIOs. If necessary, submit proposals for revising the dates of the measure. | ADB
9. PUBLIC PROCCUREMENT
15. Upgrading the e-procurement system | 34. New e-procurement system software | 34․1 Development and introduction of new e-procurement system software | MoF | - | December, 2020 | December, 2021 | New existing e-procurement software | Activities have been carried out with donor organizations to develop a business model and terms of reference for the introduction of a new e-procurement system. In particular, an agreement was reached with the European Bank for Reconstruction and Development to elaborate a new e-procurement software system with the latter's technical and financial assistance, according to which it is expected to obtain from EBRD business model rationale for the introduction of the new e-procurement system. Given that there is no response from the Bank yet, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model and terms of reference for the implementation of the e-procurement system, provided that it will not be implemented by the consultant if implemented by the EBRD. The issue related to the substantiation of the business model proposed by the Bank is currently being discussed, after the clarification of which the relevant decision will be made. | As a result of work with donor organizations an agreement has been reached with the EBRD to implement the systems development with the latter's financial and technical assistance. As a result of the meetings with the Bank's experts, an agreement was reached that the Armenian side will be provided with additional substantiations on the proposed business model of the system, which have not been received yet. Given the mentioned, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model and terms of reference for the implementation of the mentioned systems, provided that it will be implemented if the EBRD does not provide appropriate assistance or the business model proposed by the EBRD is not considered acceptable by the RA Government. |  | Not started. | The contract with the consultant has been signed, the work has started | The implementation of the measure depends on the results of the implementation of the measure mentioned in points 55.1. | Depending on the course of the measure referred to in point 55.1, submit a proposal as necessary to review the timing of the measure
16. Procuurement planning | 35. Improving the procurement planning system | 35․1 Develop RA Government draft decision on the introduction of a unified planning system for determining the cost estimates of items with similar characteristics automatically | MoF | - | December, 2020 | December, 2021 | The same needs of customers are met with items with the same characteristics and cost estimates | The relevant proposals for the implementation of the mentioned measure were received and summarized from the RA public administration bodies based on the letter 01/26-1/3308-2020 of the RA Minister of Finance, dated 21.03.2020. | As a result of work with donor organizations An agreement has been reached with the EBRD to implement the systems development with the latter's financial and technical assistance. As a result of the meetings with the Bank's experts, an agreement was reached that the Armenian side will be provided with additional substantiations on the proposed business model of the system, which have not been received yet. Given the mentioned, the terms of reference for selecting a consultant within the framework of the implementation of the GFMIS envisages the development of a business model and terms of reference for the implementation of the mentioned systems, provided that it will be implemented if the EBRD does not provide appropriate assistance or the business model proposed by the EBRD is not considered acceptable by the RA Government. |  | In progress. | The implementation of the measure is interrelated with the implementation of the "34.1" measure | The implementation of the measure depends on the results of the implementation of the measure mentioned in points 55.1. | Depending on the course of the measure referred to in point 55.1, submit a proposal as necessary to review the timing of the measure
17. Procurement Appeal System | 36. Improving the procurement appeal system | 36.1 Making changes in the RA Law "On Procurement" | MoF | - | December, 2021 |  | Functional and independent appeal system | The RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Amendments to the RA Law on State Duty", "On Making Amendments and supplements to the RA Civil Procedure Code" have been elaborated and submitted to public government bodies, international donor organizations and civil society for consideration. Discussions with the EU SIGMA Program Expert Group are ongoing. | The RA draft Laws "On Making Amendments and Addenda to the RA Law on Procurement", "On Making Amendments to the RA Law on Public Administration System Bodies", "On Making Amendments to the RA Law on State Duty", "On Making Amendments and supplements to the RA Civil Procedure Code" have been elaborated by the RA MoF and submitted to the RA Prime Minister's office. The mentioned drafts were discussed on 15.06.2021. at the sitting of the Ministerial Committee on Finance and Economy. It was decided to discuss the drafts with the RA Ministry of Justice once again. |  | In Progress | After the discussions with the RA Ministry of Justice, the drafts will be submitted to the RA Government for approval. | None
10. PUBLIC INTERNAL FINANCIAL CONTROL AND FINANCIAL-BUDGETARY OVERSIGHT
18. Financial management and control | 37. Ensuring the introduction of financial management and control system | 37․1 Testing of FMS system methodology | MoF | - | December, 2020 | December, 2021 | · Piloted methodology of FMS | As of 2019, there are still draft legal acts for the introduction of the FMS, which need to be reviewed once again, considering them from the point of view of the implementation of the PB system, discussing them with the Civil Service Office. In order to test the FMS system, an agreement was reached in 2019 with the RA Ministry of Education and Science (there is an official letter from the Ministry of Finance and an agreement with the pilot ministry) to pilot the above methodology. The second state body that was selected and an agreement reached with the latter's representatives is the RA Ministry of Labor and Social Affairs. | As a result of the work with the development partner organizations, an agreement was reached with the GIZ to carry out the work with its financial and technical support. In order to support the RA Ministry of Finance in the introduction of the financial management system, drafts of relevant technical specifications have been developed. Within the support, it is planned to update the Financial Management and Supervision manual in the public sector. |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building | GIZ
|  | 37․2 Adoption of FMS Concept and FMS Legislative Acts |  |  | 2021-2022 | 2022-2023 | · FMS adopted concept and legislation | During 2018-2019 the FMC draft concept has been elaborated with the support of GIZ. | It is related to the results of the measure 37.1 |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building | GIZ
|  | 37․3 Introduction of FMS system in public sector organizations | MoF | SB | Since 2022 |  | · The process of introducing the FMS system is carried out according to the set schedule | As the measure is related to event 37.1, the work related to this event will start after the testing of the FMS system methodology and adoption of FMS concept and relevant legislation | It is related to the results of the measure 37.1 and 37.2 |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building | GIZ
19. Public sector internal audit | 38․ Carrying out external evaluation of the quality of internal audit | 38․1 Approval of the external audit quality assessment methodology | MoF | - | December, 2019 | December, 2021 | Order approved by the RA Minister of Finance "On approving the procedure for conducting external evaluation of the internal audit quality | In the context of this measure, with the support of the World Bank, an external quality assessment manual was developed, which was piloted in 2 organizations of the RA public sector. RA Minister of Finance draft order has been elaborated. The draft order was discussed with the representatives of state bodies, was finalized and is ready for approval. | The measure is planned to be implemented with the support of development partner organizations. As a result of discussions with development partner organizations, a proposal was received from the World Bank to support the implementation of the measure, the scope of which is being adjusted. |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building | (GIZ)
|  | 38․2 Carrying out external evaluation of the quality of internal audit in public sector organizations |  |  | 2020-2022 | 2021-2023 | All public sector organizations where an internal audit system is in place will be subject to external evaluation by the MoF. |  |  |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building
Report on the quality of internal audit of the RA public sector
| 39․ Ensuring Internal Audit and External Audit Cooperation | 39․1 Define internal audit and external audit cooperation procedures | MoF | AC (by agreement) | December, 2023 |  | Joint order of the RA Minister of Finance and the Chairman of the RA Audit Chamber "On approving the order of internal-external audit cooperation" | The procedure for internal-external audit cooperation has been under development since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version and after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. | The procedure for internal-external audit cooperation has been under development since 2019, the work of which was supported by the World Bank. The draft document is available in a preliminary version and after some revisions it should have been discussed jointly with the RA Audit Chamber and PBs. |  | In progress | Make the document complete, submit to the RA Audit Chamber and Sbsfor consideration and submit the revised document for approval as a result of discussions | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building
| 40. Emphasis on Performance Audit Capability and Provide practical application of 30% of the annual plan | 40․1 Approval of performance audit methodology | MoF | - | 2019-2020 | 2021-2022 | Approved order of the RA Minister of Finance "On approving the performance audit manual" | RA Minister of Finance draft order "On approving the performance audit manual" has been developed, which is in the process of revision, within the framework of which it is necessary to ensure the connection of the performance audit with the embedded PB system, which which will provide an opportunity to comprehensively assess the results of the programs of the PBs implementing budget programs considering it not only in the context of financial but also in the context of non-financial performance indicators. | RA Minister of Finance draft order "On approving the performance audit manual" has been developed, which is in the process of revision, within the framework of which it is necessary to ensure the connection of the performance audit with the embedded PB system, which which will provide an opportunity to comprehensively assess the results of the programs of the PBs implementing budget programs considering it not only in the context of financial but also in the context of non-financial performance indicators. |  | Not started. |  |  | Recruit the resonsible unit staff and ensure their capacity building
|  | 40․2 Increasing the role of performance auditing in internal audit legislation |  |  | December, 2020 | December, 2022 | Requirement stipulated in the internal audit legislation, according to which the performance audit will make up 30% of the annual internal audit plan |  |  |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building
|  | 40.3 Development of performance auditing skills of internal auditors operating in RA public sector organizations |  |  | 2020-2023 | 2022-2023 | Internal auditors in RA public sector organizations trained in performance auditing |  | The measure is planned to be implemented with the support of development partner organizations. As a result of discussions with development partner organizations, a proposal was received from GIZ to support the implementation of the measure, the scope of which is being adjusted. With the support of the IAEGIZA, it is planned to review the general methodological and legal procedures of internal audit, to update the capacity building mechanisms of the IA, which will be acceptable at both central and community levels, introduction of modern mechanisms for IA certification in accordance with international standards, guarantee of independence of IA units in local self-government bodies, development of standard approaches and tools of IA at the local government level. |  | Not started. |  |  | Continue negotiations with PIOs. The measure was included in the draft decision of the RA Government on making changes in the decision 1716-L of the RA Government, envisaging extension of the term for 1 year | (GIZ)
| 41. Development of professional knowledge and skills of internal auditors | 41․1 Elaborating a program for developing the professional knowledge and skills of internal auditors | MoF | - | December, 2020 | December, 2021 | Internal auditors' professional knowledge and capacity are assessed, needs identified, development plan approved |  |  |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building | (GIZ)
|  | 41․2 Optimization of continuous professional training courses for internal auditors |  |  | 2020-2022 | 2021-2023 | The internal auditors have the requirements of the RA legislation on internal audit, international advanced experience, theoretical knowledge of internal audit and practical skills. |  |  |  | Not started. |  |  | Recruit the resonsible unit staff and ensure their capacity building | (GIZ)
|  | 41․3. Elaboration of an online information system for the continuous professional training of internal auditors |  |  | 2020-2021 | 2021-2022 | Internal auditors undergo an annual continuous professional training program through an online information system |  |  |  | Not started. |  | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building | (GIZ)
|  | 41․4 Review of the Public Sector Internal Auditor Qualification Procedure |  |  | December, 2021 | December, 2022 | Internal auditor qualification system based on relevant international approaches |  |  |  | Not started. |  |  | Recruit the resonsible unit staff and ensure their capacity building | (GIZ)
20. Central harmonization unit (CHU) | 42. CHU personnel recruitment and capacity building | 42․1 CHU personnel recruitment and capacity building | MoF | - | 2019-2021 |  | Necessary capacities are available in CHU | The relevant unit which was carrying out the functions of the CHU, was dissolved on February 24 of this year and the functions were transferred to the Financial-Budgetary Control Department of the RA Ministry of Finance, as a result of which it is necessary to recruit specialists with relevant capacities in the CHU. | The relevant unit which was carrying out the functions of the CHU, was dissolved on February 24, 2020 and the functions were transferred to the Financial-Budgetary Supervision Department of the RA Ministry of Finance. To date, the unit has not been recruited with relevant specialists. |  | In progress | Recruitment of CHU staff and organizing training courses for staff capacity building | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building
21. Financial and budgetary control | 43․ Ensuring effective financial and budgetary control activities | 43․1․ Review of financial-budgetary control legislation, update, development of new methodology for implementation of financial-budgetary control | MoF | - | 2020-2021 |  | By-laws defining the modern methodology of financial and budgetary control | In the context of this group of measures, the main problems in the system of financial-budgetary control were formulated in 2018-2019. The RA Government decision "On defining the procedure of financial and budgetary control of the Republic of Armenia" and declaring null and void the RA Government decisions dated July 11, 2002 N 1112 N and February 23, 2012 N 207 " has been elaborated which is under discussion | An agenda has been developed within the European Union TAIEX instrument with the support of European experts to review and update the RA financial-budgetary supervision legislation. |  | In progress | Financial-budgetary supervision legislation will be reviewed and updated. | There are problems with the recruitment of the responsible unit staff and professional capacity | Recruit the resonsible unit staff and ensure their capacity building
|  | 43.2 Capacity building of specialists in the field of financial-budgetary control |  |  | 2022-2023 |  | Specialists in the field of financial-budgetary control have professional skills and have relevant knowledge |  |  |  | Not started. |  |  | Recruit the resonsible unit staff and ensure their capacity building
|  | 43․3 Availability of necessary databases for risk assessment |  |  | 2020-2023 |  | Introduction of a new risk system based on complete, substantiated and justified information analysis | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. | Work is underway to clarify the priorities for updating the legal framework, in parallel with the development of human resources and, if possible, the introduction of a qualification system. |  | In progress |  |  | Recruit the resonsible unit staff and ensure their capacity building
11. PUBLIC ASSETS AND PUBLIC INVESTMENT MANAGEMENT
22. Public assets management | 44. Ensure monitoring of government financial and non-financial assets | 44.1․Elaboration and approval of the methodology of public asset management and legal acts necessary for its introduction | MoF | - | 2020-2022 |  | Existing methodology on management of financial and non-financial assets of the Government, and legal acts approved in accordance with the RA legislation | An agreement was reached on the provision of IMF technical assistance for the implementation of the measure, within the framework of which the report "Program Budgeting and Management of Public Assets" was submitted to RA the Ministry of Finance for consideration. | In the framework of IMF technical assistance, the conceptual and methodological approaches to the public asset managementwere elaborated and submitted to the position of the RA Ministry of Finance. The remarks and suggestions of the RA Ministry of Finance were presented on the latter, on the basis of which the experts were offered to review the report. |  | In progress | Review of the document of conceptual and methodological approaches to public asset management, ensuring further work related to its application | The role of the MoF in terms of elaboration and monitoring of public asset management methodology, distribution of those roles among the subdivisions of the Ministry needs to be clarified. In particular, there are potential crossings in these functions to the functions of the Ministry's budget process organization, budget execution reports, as well as the functions of accounting auditing activities regulating and reporting monitoring departments. The staff responsible for monitoring the budget asset management methodology of the Budget Process Management Department of the RA Ministry of Finance is not staffed; the existing capacities are not sufficient to ensure the implementation of the measure. |  | (GIZ/IMF/RD MOF)
|  | 44.2 Implementation of trainings on asset management techniques in accordance with the approved legislation | MoF | SB |  |  | Specialists trained in accordance with the law on public assets | .The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  | Not started. |  | The implementation of the measure depends on the results of the measure mentioned in point 44.1. | Depending on the course of the measure referred to in point 44.1, submit a proposal as necessary to review the timing of the measure | (GIZ)
|  | 44.3 Preparation and monitoring of financial and non-financial asset registers | SB | - |  |  | Asset Monitoring Report | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  | Not started. |  | The implementation of the measure depends on the results of the measure mentioned in point 44.1. | Depending on the course of the measure referred to in point 44.1, submit a proposal as necessary to review the timing of the measure
| 45. Ensuring transparency of the sale, transfer, alienation process and the right to use non-financial assets | 45.1 definition of procedures for the sale, transfer, alienation process and the right to use non-financial assets will be reviewed. | MoF | MoTAI | 2022-2023 |  | Procedures for the sale, transfer, alienation process and the right to use non-financial assets are approved. | The activities to be carried out within this measure are the introduction of a public asset management methodology to be developed under measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure | The activities to be carried out within this measure are the introducyion activities of the public asset management methodology to be elaborated within the framework of measure 44.1. The latter is a logical continuation of the above-mentioned measure it will be implemented based on the results of that measure. |  | Not started. |  | The implementation of the measure depends on the results of the measure mentioned in point 44.1. | Depending on the course of the measure referred to in point 44.1, submit a proposal as necessary to review the timing of the measure | IMF
23. Public Investment Management | 46․ Creating a Legislative Basis: Public Investment Management Methodology | 46.1․ Elaboration of a public investment management manual | MoF | - | December, 2019 |  | Public Investment Management Manual has been developed and is ready for testing | 1. Within the framework of the works aimed at the introduction of the public investment program management system, in particular, the elaboration of a methodology for identifying, elaborating, evaluating and setting priorities of public investment programs the draft Public Investment Management Manual (hereinafter the Manual) was developed jointly with the experts of the World Bank (hereinafter the WB). According to the appendix approved by the RA Prime Minister's decision N 5-A of January 9, 2020 "On starting the budget process of 2021" of the RA Prime Minister, for the latter’s testing the RA Ministry of Economy has provided to the RA Ministry of Healthcare, Ministry of Education, Science, Culture, Sports, Ministry of territorial administration and infrastructure, in the defined timeframe "The form for the investment project concept and quality assessment" (the standard form) to present the new projects in excess of 70 million drams in the standard form. The pilot stages of the manual have passed 8 investment projects provided by the mentioned agencies. 2. The testing of the manual with the agencies was carried out in stages, by sectors. In this regard, in the first phase, from January 29 to February 14, 2020, 6 meetings and discussions were held, during which the information on the Manual was provided to the representatives of the relevant agencies, as well as consultancy on the completion of the Form per the Manual. 3. In the second stage, on February 24-28, 2020, a seminar-discussion was held with the participation of WB experts, experimentally selected ministries, representatives of the RA Ministries of Finance, Economy and the Office of the RA Deputy Prime Minister Tigran Avinyan, during which the WB experts gave a detailed reference to the principles of identifying problems within the framework of investment projects, setting goals, and action-intermediate result-end-impact-benefit "logical chain formation. Based on the relevant examples, the mechanisms for calculating the demand-risk analysis, as well as the financial-economic analysis of investment projects were presented. 8 new investment projects submitted by the RA Ministry of Health, the RA Ministry of Education and Science and the RA Ministry of TAI were studied. During the discussions, observations and proposals were submitted for all the projects, as a result of which the representatives of the ministries were offered to amend the provided investment project applications based on the submitted considerations and submit the revised version to the RA Ministry of Economy. 3․ In the 3rd stage, on March 12, 2020, and March 13, a video conference was held at the RA Ministry of Economy with the participation of the staff of the RA Ministry of Health, the RA Ministry of Education and Science and the WB experts. During the video conference, the considerations on the investment projects submitted in accordance with the Standard Form, provided by the agencies, were further discussed, on the basis of which it is planned to finalize the revision of the projects. As a result of the implemented works, the strengths and weaknesses of the Manual were identified, as well as the shortcomings were registered, localizing the Manual as much as possible, taking into account the situation in the Republic of Armenia. The above-mentioned works were summarized in April 2020. | 1. Within the framework of the works aimed at the introduction of the public investment projects management system, in particular, the elaboration of a methodology for identifying, elaborating, evaluating and setting priorities of public investment projects the draft Public Investment Management Manual (hereinafter the Manual) was developed jointly with the experts of the World Bank (hereinafter the WB). For its piloting purposes, according to the appendix approved by the RA Prime Minister's decision N 5-A of January 9, 2020 "On starting the budget process of 2021", the RA Ministry of Economy has provided to the RA Ministry of Healthcare, Ministry of Education, Science, Culture, Sports, Ministry of territorial administration and infrastructure, in the defined timeframe "The model form for the investment project concept and quality assessment" to present the new projects in excess of 70 million drams in the model form. The pilot stages of the manual have passed 8 investment projects provided by the mentioned agencies. 2. The testing of the manual with the agencies was carried out in stages, by sectors. In this regard, in the first phase, from January 29 to February 14, 2020, 6 meetings and discussions were held, during which the information on the Manual was provided to the representatives of the relevant bodies, as well as consultancy on the completion of the Model Form per the Manual. 3. In the second stage, on February 24-28, 2020, a seminar-discussion was held with the participation of WB experts, experimentally selected ministries, representatives of the RA Ministries of Finance, Economy and the Office of the RA Deputy Prime Minister Tigran Avinyan, during which the WB experts gave a detailed reference to the principles of identifying problems within the framework of investment projects, setting goals, and action-intermediate result-end-impact-benefit "logical chain formation. Based on the relevant examples, the mechanisms for calculating the demand-risk analysis, as well as the financial-economic analysis of investment projects were presented. 8 new investment projects submitted by the RA Ministry of Health, the RA Ministry of Education and Science and the RA Ministry of TAI were studied. During the discussions, observations and proposals were submitted for all the projects, as a result of which the representatives of the ministries were offered to amend the provided investment project applications based on the submitted considerations and submit the revised version to the RA Ministry of Economy. 4․ In the 3rd stage, on March 12, 2020, and March 13, a video conference was held at the RA Ministry of Economy with the participation of the staff of the RA Ministry of Health, the RA Ministry of Education and Science, RA TAI and the WB experts. During the video conference, the considerations on the investment projects submitted in accordance with the Model Form, provided by the agencies, were further discussed, on the basis of which it is planned to finalize the revision of the projects. As a result of the implemented works, the strengths and weaknesses of the Manual were identified, as well as the shortcomings were registered, localizing the Manual as much as possible, taking into account the situation in the Republic of Armenia. |  | Completed |  |  |  | WB
|  | 46.2․ Testing the Public Investment Management Manual and identifying deficiencies. |  |  | december, 2020 |  | Report on testing results and existing deficiencies. | The manual was tested in the following phases Phase 1 1. From January 28 to February 14, 2020 , meetings and discussions were held with the representatives of the RA Ministry of Health, the RA Ministry of Education, Science, Culture and Sport the RA TAI within the introduction of the Public Investment Management System on completing investment projects according to the Model in the framework of the manual test. 2. On February 24-28, 2020, with the participation of representatives of interested state agencies, in particular the RA Ministry of Territorial Administration, the Ministry of Health, the Ministry of ESCS, the Ministry of Finance, the Ministry of Economy, and the Office of the Deputy Prime Minister Tigran Avinyan, 5 seminars-discussions on the new initiatives completed by the relevant agencies in accordance with the form within the framework of the public investment management system implementation. 3. Given the coronavirus situation, further manual testing was performed online. Preliminary evaluation of investment projects has been carried out. 4. Taking into account that as a result of the study of investment projects the indicators of investment projects were not provided with sufficient accuracy, on the initiative of the RA Ministry of Economy organized on June 23, 2020 a remote workshop was organized and held the WB experts, within which the necessary indicators were discussed for each investment project, as a result of which it was decided that the "Human Life Value" indicator is missing in Armenia, while it is necessary for evaluating public investment, in particular, social programs. In this context, a working group has been set up to recruit relevant specialists to calculate this indicator. 5. As a result of the discussions with the selected pilot agencies, the investment project provided by the RA Ministry of Health was selected, additional work was done to include new indicators for the evaluation of the project. ։ The indicators of the considered project of a similar program provided by the WB experts were studied, within the framework of which the indicators became almost 75% comparable. In terms of 25% incomparable indicators ․ Preliminary feasibility study is planned to be carried out on August 3, 2020 with WB expertsto identify the missing indicators, but due to martial law, this process has been postponed to early 2021. In case of absence of "Human Life Value" index for Armenia in the mentioned period, the index calculated by the WB for Armenia will be taken into account ։ 6. As a result of the preliminary feasibility study carried out jointly with the WB experts, the practical testing phase of the Manual will be summarized, the results of which will be included in the Manual (as mentioned in point 46.1). ։ In the context of the above, it will be possible to fully assess the Manual, as a result of which it is planned to carry out the work of circulating the Manual among the relevant departments, summarizing and approving the considerations on the latter. Phase 2 On September 25, 2020, the RA Prime Minister held a consultation, during which the draft concept of public investment management was presented, and as a result the Prime Minister proposed to take note of the draft and instructed to continue the work on strategy revision and finalize the document. In continuation of the work on the introduction of the public investment management system launched in the first half of 2020, the scope of the agencies previously involved in the work on the introduction of the public investment management system has been expanded. In this context, an online discussion was held on November 4, 2020, chaired by the RA Deputy Minister of Economy Avag Avanesyan with the participation of the representatives of the relevant agencies and the second phase of the manual testing works has started During the discussion, the Deputy Minister provided details, in particular, on the purpose of the introduction of the public investment management system, features, provisions of the draft, as well as programs financed from the consolidated budget, the economic profitability of the latter. During the online discussion, clarifications were provided on the methodology of evaluation criteria for public investment programs stipulated by the Project, as well as the scope of competence of each department within the Project, project identification, project evaluation, prioritization and evaluation procedures. The role of the RA Ministry of Finance in the framework of the introduction and operation of the public investment management system was especially emphasized. In this regard, the representative of the RA Ministry of Finance was offered to present the problems and risks that are visible in the Sample and may hinder the budget process. The representative of the RA Ministry of Finance emphasized the process of public investment management, but the latter registered the issue of implementing the budget process on the basis of the Manual as a methodological guide. In this regard, the RA Deputy Minister of Economy pointed out that it can be stated that the process of public investment management is an adjunct to the budget process, does not imply a change in the budget process and the only change is the International Monetary Fund requirement that the list of planned programs be included in the 2022 budget documents. The process of public investment management is regular throughout the year and the identified projects can be included in the list of projects at any time, after passing the relevant procedures. During the online meeting, they also touched upon the issues to be further discussed by the RA Ministry of Finance, in particular, the issue of codes given to the programs at the planning stage (the application submitted to the RA Ministry of Finance and the program that went through the process of public investment management should have the same code, so that in the future they can be easily identified. As a result of the discussion, an agreement was reached between the participants to identify at least three project ideas for each agency on which joint work on the development of exemplary model forms will be carried out. In connection with the above, the RA Ministry of Economy has initiated separate meetings in each agency with the participation of the Deputy Ministers and employees of the relevant units during which the RA Ministry of Economy has presented and continues a detailed information on the introduction of public investment management system. In this regard, a schedule of preliminary meetings has been set for each agency. As of December 2020, separate meetings-discussions were organized with the representatives of the RA Ministry of Education, Science, Culture and Sport, the RA TAI, the RA TAI Water Committee, the RA Ministry of Justice, the RA Ministry of Emergency Situations As a result of these discussions, the mentioned ministries have already provided drafts of public investment programs, relevant lists, around which online substantive discussions have taken place, and provided consulting proposals. It should be noted that the work on the introduction of a public investment management system is ongoing; in 2021, separate meetings with other agencies are also planned. | In 2020 The RA Ministry of Economy, , carried out pilot works (workshops, seminars, trainings, including online) of the draft PIM manual elaborated jointly with World Bank experts within introduction of the PIM system, with the participation of the representatives of the RA Ministry of Health, RA Ministry of Education, Science, Culture and Sport, RA Territorial Administration and Infrastructure The testing of the manual with the departments was carried out in stages by sectors. Works for testing the manual and identification of possible shortcomings were carried out in 2021 with the participation of representatives of all interested bodies. As a result of the above-mentioned works, shortcomings were identified, and appropriate works were carried out to solve them. In particular, during the testing of the PIM manual, there was a need to create a legal basis for the introduction of the PIM system. As a result, the RA Prime Minister Decision N 472-L, dated May 4, 2021 "On Approving Procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project" was elaborated and adopted. Based on the considerations presented as a result of the manual testing, the PIM manual was also amended in parallel. At present, the drafts of public investment projects are collected from all interested bodies, monitored (pre) evaluated according to the procedure defined by the mentioned decision. Ongoing work is being done to review and finalize the manual, taking into account the sequential implementation of all stages and components of the testing, summarization of the results, and making appropriate amendments. The final summary of the manual is planned to be carried out by the second ten days of December 2021. |  | In progress | Ongoing work is being done to review and finalize the manual, taking into account the sequential implementation of all stages and components of the testing, summarization of the results, and making appropriate amendments. The final summary of the manual is planned to be carried out by the second ten days of December 2021. |  |  | WB
|  | 46.3․ Review and approval of the Public Investment Management Manual |  |  | December, 2020 | December, 2021 | The Public Investment Management Manual is approved by the RA Government | 1․ As a result of the discussions on the project, as well as the experimental work, it was necessary to amend the Manual. Relevant work is currently underway in the direction of the latter, with the aim of creating an effective system for multifactorial evaluation of public investment programs, based on which the cross-sectoral priorities of those programs are determined. 2. Work has been underway for about 6 months to review the manual, taking into account the sequential implementation of all stages and components of the test, summarizing the results, and making appropriate amendments. The final summarization of the manual is planned to be held by 2nd ten days of Decemeber, 2021 During the testing of the manual, shortcomings were identified, which are being addressed, in particular:  During the testing of the public investment management manual, there was a need to create a legal basis for the introduction of a public investment management system. As a result the RA Prime Minister draft decision "On approving the Procedure for Identifying, elaborating and Evaluating and Determining Priorities of Public Investment Programs in the Republic of Armenia, Methodology for Evaluating Public Investment Programs, and Model form for Elaboration and Evaluation of Public Investment Program" has been elaborated. (hereinafter the Draft).  It is necessary to carry out harmonization and compliance of legislation and legal acts related to the introduction of public investment management system.  In addition to the single Public Investment Management Manual, it is necessary to develop brief methodological manuals / guides for each stage of the Public Investment management process, which will be useful to both public and private sector representatives.  Ensuring the involvement of relevant units of ministries, including financial departments, in training / retraining processes and the continuity of these courses  Establishment of relevant professional sectoral target groups to promote the effective implementation of public investment and to ensure the public investment management process.  In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the performance of statistical work aimed at increasing the accountability of public investments within the framework of the manual. | In the scope of PIM system introduction the RA Prime Minister Decision N 472-L, dated May 4, 2021 "On Approving Procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project" was elaborated by the RA Ministry of Economy and adopted. Work is currently underway to finalize the revision of the PIM manual, taking into account the results of the sequential implementation of all stages and components of the manual, as well as the provisions and procedure set out in the PIM decision. |  | In progress. | 1. Finalization of the review of the PIM manual jointly with the RA Ministry of Finance. |  |  | WB
| 47. Capacity building of public investment specialists | 47․1․ Elaboration of a capacity building program for public investment specialists for the training on public investment management manual | MoE | - | December, 2020 | December, 2022 | The Public Investment Management Manual is approved by the RA Government | 1․In the framework of the introduction of the Public Investment Management System, during the first half of 2020 seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy After the seminars / trainings aimed at capacity building, the needs of public investment specialists were assessed in the framework of which the needs of specialists have been identified, particularly in the component of financial calculations. In this regard, the RA Ministry of Finance is expected to be more actively involved in the implementation of the mentioned event. 2.In order to carry out a complete assessment of the applicability of the manual (100%), it is necessary to ensure the accountability and statistics of the public investments carried out within the framework of the manual, without which it is possible to record a 70% assessment. 3․in the framework of the introduction of the Public Investment Management System, seminars-discussionsand workshops aimed at capacity building of public investment specialists were carried out by the agenda and program developed by the WB experts and agreed with the relevant representatives of the RA Ministry of Economy | Within the introduction of the PIM system, as well as in terms of the procedure defined by the PIM decision and completing the Model Form, in the first half of 2021, the Public Investment Policy Department of the RA Ministry of Economy conducted workshops and work discussions on capacity building with the participation of representatives of all interested bodies, including local self government bodies according to the agreed program and agenda. In particular, the Public Investment Policy Department of the RA Ministry of economy conducted online trainings on public-private partnership in the framework of the Commercial Law Development Program under the United States Department of Commerce with the participation of relevant bodies (RA Ministry of TAI, RA Ministry of High-Tech Industry, RA Ministry of Education, Science, Culture and Sport, RA MoF, Road Department SNCO, City of Yerevan) |  | In progress. | 1․ Development of methodology and training program aimed at capacity building of public investment specialists jointly with the RA Ministry of Economy and the RA Ministry of Finance to conduct once again trainings for the representatives of the interested agencies within the framework of the Model form. |  |  | WB
|  | 47.2 Capacity building |  |  | 2020-2021 |  | The capacity of public investment specialists is sufficient | Within the framework of the introduction of the Public Investment Management System, the testing of the Public Investment Management Manual, activities aimed at developing the capacity and training of public sector specialists are carried out, which are of a continuous nature and are envisaged during 2021. Taking into account the working meetings held in the agencies, as well as the subsequent discussions, responsible representatives from each agency are invited to participate in the professional training courses. Phase 1․ 1 A total of 40 public sector specialists (RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office) were trained and capacity building workshops were held with them within the framework of introduction of public investment management system. 2․ During the first half of 2020, 16 seminars-discussions / workshops were organized jointly with the RA Ministry of Economy and WB  This year from January 28 to February 14, 6 working discussions were held in the RA Ministry of Economy with the representatives of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI on the completion of a common model form (hereinafter referred to as the Model Form) quality assessment concept of the investment project in the framework of the introduction of the Public Investment Management System From February 24 to 28, this year 5 seminars-discussions on new initiatives completed by the relevant agencies related to the Model form within the framework introduction of the Public Investment Management System were organized and held in the WB Armenia Office with the participation of the representatives of the interested state agencies, in particular, RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA TAI, RA Ministry of Finance, RA Ministry of Economy, RA Deputy Prime Minister Tigran Avinyan's office  On March 12 and 13, 2020, 2 video conferences were held at the RA Ministry of Economy with the participation of the WB experts, with the participation of the employees of the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, with the WB experts.  On June 23, 2020 organizing 1 online workshop on economic and financial evaluation of investment projects for the RA Ministry of Health, RA Ministry Education, Science, Culture and Sport, RA MTAI with the initiative of the RA MoE and by the WB experts  Conducting a separate remote discussion with the representative of the RA Ministry of Health, during which the indicators of the investment project provided by the RA Ministry of Health were observed, as well as they were compared with the indicators of a similar program.  An online discussion was held with the relevant representatives of the Ministry of Education and Science of the Republic of Armenia, within the framework of which the investment projects with a large social component were considered in detail, peculiarities of applying the standards applicable to them and elaboration/drafting of these projects. In this context, within the framework of the already established experience, work is being done on the evaluation criteria of large social components - programs that do not have primary economic benefits, but provide secondary benefits. Phase 2  During the second phase of the manual testing, 18 discussions were held with the involvement of representatives of about 100 public investment sectors, in particular, representatives of the RA TAI the RA TAI Water Committee, the RA MOESCS, the RA Ministry of Emergency Situations and the Ministry of Justice. | 1. In the first half of 2021, a total of 9 meetings, including online, about 120 public sector specialists (representatives of the public administration system, local self-government bodies) were trained, capacity building workshops were held with the latter in the framework of meetings-discussions on the introduction of the PIM system, as well as the awareness of the procedure stipulated by the PIM decision completion of model form. The mentioned meetings-discussions were conducted both online and in the format of local meetings in the sectorial ministries during which detailed presentation on the information related to procedure for revealing, elaborating, evaluating, compiling and defining the list of priorities, the methodology for evaluating public investment projects, approving the model form of drafting and evaluating the public investment project was presented. 2. Within the framework of the USAID program, the Public Investment Policy Department of the RA Ministry of Economy in cooperation with the International Republican Institute conducted seminars, working discussions on financial modeling and financial analysis, with an agreed program and agenda with the participation of representatives of all interested bodies. |  | In progress | Regular capacity building meetings and ensuring its continuity. |  |  | WB
| 48. The public investment projects included in the 2023 annual budget are prepared in accordance with the requirements of the defined PIM manual | 48.1. Practical application PIM manual in the budget process | MoF | MoE | December, 2021 | December, 2022 | The public investment projects included in the 2023 approved budget have been developed in accordance with the requirements of the PIM manual | An agreement has been reached with the IMF for assistance, under which work has begun since October, in 2020. and are under discussion. The measure was included in the draft decision of the RA Government on making changes in the decision 1716-L of the RA Government, within which the term was extended for 1 year and corresponding changes have been made in the titles of the target name and result evaluation indicators. The extension of the term of the measure is conditioned by the one-year extension of the implementation period of the measure "46.3 ․ Review and approval of the Public Investment Management Manual, as well as with the deadlines for organizing the budget process. | The deadline of the measure was extended by the RA Government Decision 283 -Լ, dated 04․03․2021 |  | Not started. |  |  |  | (GIZ/IMF/ADB/WB/AFD)
| 49.Monitoring of public investment projects | 49.1 Monitoring of public investment projects | MoF | MoE | 2022-2023 |  | Published report on the results of the monitoring of public investment projects | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and Therefore, in the case of this measure, there may be a need to review the deadlines. | The implementation of this measure is closely linked to the outcome of the measure set out in paragraph 48.1 and therefore, will launch after the implementation of measure 48.1 |  | Not started |  |  |  | (GIZ/IMF/ADB/WB)
12․FINANCIAL MANAGEMENT IN SELF LOCAL GOVERNMENT BODIES
24. Efficiency of financial management in local self-government bodies | 50. Development of capacities and professional skills of the administrative staff of local self-government bodies | 50.1․ Implementation of public finance management reform program in local self-government bodies | MoF | MoTAI | 2020-2023 |  | Study reports | Within the framework of this measure, the work on PFM reforms in local self-government bodies is currently carried out directly by the RA Ministry of Territorial Administration, which is the coordinator of the measure. Harmonization of program budgeting methodologies of community and national level. 2017 Elaboration of a program budgeting training program . Availability of the 2015 PB curriculum. Organizing and holding training on program budgeting methodology, its application and PB awareness for the administrative staff of the local self-government bodies of the enlarged communities in 2014-2020. 2014-2020 Development of competencies and professional skills of the administrative staff of local self-government bodies. Providing technical assistance, advice to financial managers of municipalities, staff members involved in the process of preparing the annual program budget for 2015 to 2020. 2015-2020 Availability of annual program budgets for large communities Providing technical assistance and consulting on community annual program budget development and holding public hearings in 52 enlarged communities for 2016 to 2020. 2016-2020 Existence of brief program budgets for the mentioned years for all the communities enlarged during those years. Providing technical assistance and consulting on quarterly and annual monitoring and evaluation of community annual program budget plans in enlarged communities for 2016 to 2020 . 2016-2020 Availability of program budget monitoring quarterly and annual plans for all communities enlarged during those years. Implementation of the "Citizen Participation in Community Budgeting" program in 10 pilot communities within the framework of the regional program funded by the Eastern Partnership Regional Public Administration Reform Fund. 2018-2020 May Development of competencies and professional skills of the administrative staff of local self-government bodies with knowledge and experience necessary for the further application of active methods of civic participation in budgeting processes. -Elaboration and publication of a "Participation of Residents in the Local Budgeting Process" participatory budgeting manual. June, 2019-2020 the manual is available Elaboration of "Gender-sensitive budgeting at the community level", GIZ, UNDP 2019-2020 the draft manual is available | 1. Summary of the results of the "baseline study of the current system of internal financial control in local self-government bodies" conducted in September-December, 2020 and discussion of further steps 2. PB budget approval in 52 unified communities, budget drafting in PB format, public discussions on them 3. Integration of gender sensitive budgeting approaches in 20 community budgets 4. Study on the application of APSAS in 52 merged communities, as well as the applicability of the APSAS developed handbook for communities 5. Summary of the results of the "baseline study of the current status of public investment management in local self-government bodies" conducted in September-December, 2020 and discussion of further steps |  | In progress | 1. Increasing the effectiveness and independence of internal audit in communities, as well as elaborating standardization templates for internal audit. 2. Ensuring the introduction of mandatory format of Program Budgeting as a community budget in communities by law 3. Introduction of Gender sensitive budgeting in 10 unified communities 4. Approval of the annual plan for the management of lands, buildings considered to be community property 5. Elaboration, piloting and final introduction of PIM concept and manual 6. Amending the relevant legal framework for the introduction of PIM system |  |  | GIZ
Transparent and participatory budget process plans at the local self government bodies
|  | 50.2․ Monitoring of the public financial management reform program in local self-government bodies and full implementation |  |  |  |  | Employees of local self government bodies capable of implementing public finance management reforms | Elaboration of an IPSAS-based accounting manual based on International Public Sector Accounting Standards. Providing the manual to all enlarged communities and interested structures. Preliminary study of the use of IPSAS-based accounting manual and standards in enlarged communities, identification of gaps and submission of recommendations for improving the system operation. Study of the preliminary situation of the property management process of enlarged communities, identification of gaps and submission of proposals for the improvement of the system. Preliminary study of the functions, rights and scope of responsibilities of the administrative heads of the settlements of the enlarged communities and submission of proposals for the improvement of the activities. | 1. Implementation of capacity building activities for the preparation of community budgets, public discussion, approval, implementation and approval of reports in 52 enlarged communities in the PB format including through online training modules (placed in community management information system) 2. Elaboration of a database of emergency interventions developed for the administrative leaders of 52 unified communities, based on real experience and cases 3. Implementation of capacity building activities for the implementation of APSAS in the communities, including through online training modules (placed in community management information system) |  | In progress | 1. support to 52 enlarged communities for elaboration of next year budget programs and summary budets through intensive implementation of capacity building measures. 2. Improvement of APSAS system in 10 unified communities 3. Development of consolidated financial reporting methodology and piloting in 2 advanced large communities. 4. Development of a public service cost formula: 5. Implementation of recommendations based on the baseline study of the property management situation in the communities: 6. Improving Community Property Management and Standardization on Legal Framework Analysis and Mandatory Annual Inventory of Community Assets through Development of 2 Sample Horsemodule forms 7. Development and implementation of capacity building measures necessary for the implementation of the PIM |  |  | GIZ
13. EXTERNAL CONTROL AND LEGISLATIVE CONTROL
25. Control of the financial-budgetary sphere by the National Assembly | 51. Provide external control (Reports of annual budget and AC ) | 51.1 Review of annual draft budgets | NA (with agreement) | AC (with agreement) | 2019-2023 |  | · More effective study of the draft annual budget | In the RA NA Standing Committees and their joint sittings, the preliminary version of the RA 2021 state budget and later on the Draft was discussed | In the RA NA Standing Committees and their joint sittings, the preliminary version of the RA 2021 state budget and later on the Draft was discussed | 2020 | It is a periodic process (Planned actions for 2020: for draft budget 2021 have been implemented) | In the RA NA Standing Committees, in their joint sittings, discussions of the preliminary version of the RA 2022 state budget, later also the Draft, are envisaged.
|  | 51.2 Study of the annual report on the execution of the state budget and AC conclusion on the latter and organizing hearings with audited state bodies |  |  |  |  | · More Effective Study of AC reports on annual financial statements | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2020 state budget execution process. The monitoring was carried out on the basis of inquiries from the Budget Office commission, each month, through the study and analysis of references with comparative analysis. • The annual report on the execution of the RA 2019 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly. • studied the references provided by the Government on the execution of the quarterly, semi-annual and nine months of the state budget of the Republic of Armenia for 2020 (also discussed at the sitting of the commission), as well as 28 current conclusions of the Audit Chamber on the execution of the first quarter semi-annual of the state budget of the Republic of Armenia 2020, • cooperates with non-governmental organizations ։ | RA National Assembly Standing Committee on Financial-Credit and Budgetary Affairs • monitored the 2021 state budget execution process. The monitoring was carried out on the basis of inquiries from the Budget Office commission, each month, through the study and analysis of references with comparative analysis. The Budget Office has prepared and provided the Commission with references with comparative analysis on the collection of state budget revenues in 2021, the process of expenditures according to expenditure directions, the RA public debt in 2021 and the main socio-economic indicators; • The annual report on the execution of the RA 2020 state budget was discussed at the joint sittings of the committee, as well as with the sectoral committees of the National Assembly, which was also approved by the National Assembly. • The commission discussed the information on the execution of the state budget for the first half and nine months of 2020. | 2020 | It is a periodic process (Planned actions for 2021 for the annual report on the implementation of the state budget for 2020 have been completed) | The Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly envisages discussions on the execution of the first quarter , the first half of and nine months of 2021 state budget
|  | 51.3 Exercising post-audit control by the Committee |  |  |  |  | Exercising post-audit control by the Committee | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, which convened 2 sittings during 2020 and studied 36 current conclusions of the Audit Chamber. of which 28 on the execution of the first quarter and semi-annual of the RA 2020 state budget | By the decision of the Standing Committee on Financial-Credit and Budgetary Affairs of the RA National Assembly, on March 9, 2019, a subcommittee on audit issues was established, which convened 3 sittings in the reporting period and studied 46 current conclusions of the Audit Chamber |  | It is a periodic process (The actions planned for the first half of 2021 have been carried out)
| 52. Capacity building of the Budget Office, NA deputies and experts of committees | 52.1 Institutional-internal capacity building of the budget office | NA (with agreement) | - | 2019-2023 |  | The budget office has the necessary tools to carry out its functions | On September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, the 2020-2023 development strategy of the Budget Office of the RA National was approved, according to which in the context of institutional capacity building of the Budget Office it is planned to expand the functions. In particular, 1. Providing information on the observance of fiscal rules defined by the Government in accordance with parts 8.2 and 8.4 of Article 21 of the Law on the Budget System of the Republic of Armenia and Part 7 of Article 5 of the Law of the Republic of Armenia "on Public Debt" 2. Providing information on the inconsistencies, elimination of distortions, implementation of recommendations in the current conclusions submitted by the Audit Chamber to the National Assembly, 3. Providing opinions to the deputies and factions of the National Assembly - the authors of the draft laws on the significant reduction of the state budget revenues or the increase of expenditures 4. Preparation of references on gender sensitivity of state budget expenditures In order to implement the changes defined by the strategy, a legal package of changes has been developed, according to which corresponding changes and additions are envisaged in the RA Constitutional Law "On Rules of Procedure of the National Assembly" and In the Rules of Procedure of the National Assembly. It was discussed by the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs, the staff of the National Assembly and other specialists. | For the purpose of implementation of changes defined by the 2020-2023 development strategy of the Budget Office of the RA National approved on September 24, 2019, at the sitting of the Standing Committee on Financial-Credit and Budgetary Affairs of the National Assembly, a legal package of amendments has been developed, according to which corresponding changes and supplements are envisaged in the RA Constitutional Law “Rules of Procedure of the National Assembly” and in the working procedure of the National Assembly The package was submitted to the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs for discussion ։ For the capacity building of the staff of the Budget Office, the experts participated in professional development courses |  | In progress | The legal package envisaging changes and supplements in the RA Constitutional Law “Rules of Procedure of the National Assembly” and in the working procedure of the National Assembly shall be put into circulation by the deputies of the NA Standing Committee on Financial-Credit and Budgetary Affairs with the expectation of approval by the National Assembly However, in order to make the most of these changes, it is necessary to study international best practices (for example, Austria, Scotland, Canada, USA) in order to introduce the appropriate set of tools in parallel with the definition of functions. The study of international experience should be carried out through reciprocal visits and the invitation of highly qualified international consultants. In parallel with the expansion of functions, it is necessary to develop the internal capacity of the budget office. In particular, it is needed: 1․ Acquisition or development of models for analysis, 2․ Staff training, including participation in trainings organized by the best international specialists and leading organizations, study visits and exchange of experience, 3․ Participation in international networks, including the OECD of Parliamentary Budget Offices and the Global and Regional Networks, 4. Assistance to the work of the Budget Office by a highly qualified international expert, including the involvement of that expert in the work process (Preparation of opinions on significant reduction of state budget revenues in draft laws, increase of expenditures, as well as analytical references on gender sensitivity of state budget expenditures).
|  | 52.2 Capacity building of NA deputies and experts of committees |  |  | 2020-2023 |  | The NA deputies and the experts of the committees effectively carry out the study of the draft annual budget, as well as the control over the execution of the state budget |  | Within the framework of the capacity building function of the National Assembly the Budget Office organized a seminar for the experts of the faction of the National Assembly and the assistants of the deputies on the topic "The RA budget process - the program budgeting in the RA". |  | In progress | The Budget Office of the National Assembly of the Republic of Armenia, within the framework of its continuous capacity building function of the National Assembly, envisages seminars, workshops on public finance management, including program budgeting, gender-sensitive budgeting for NA deputies, their assistants, NA staff, standing committees and factions. Within the framework of the UN Development Program "New Armenia - Modern Parliament", trainings are planned for the NA deputies and experts of the committees.
26. Independence of the Audit Chamber and external audit of the government's annual financial statements | 53. Defining and implementing 2020-2023 strategic goals of Audit Chamber ․ | 53.1 Strategy of the RA Audit Chamber and elaboration and approval of action plan for its implementation | AC (by agreement) | - | 2019-2020 |  | Audit Chamber 2020-2023 ․ Strategy and Action Plan Approved in accordance with ISSAI | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop and approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation. The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed (basis RA Audit Chamber Decision 150-Լ, dated August 7, 2020). | By the Action plan of the Audit chamber approved by the RA Audit Chamber N 25/1 Decision, dated November 26, 2019, it was planned to develop and approve the Strategic Development Plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation. The Audit Chamber has worked closely with EU / OECD SIGMA project experts to develop these documents in line with INTOSAI standards (in accordance with the INTOSAI IDI Strategic Development Manual). With the professional support of SIGMA program, during the reporting period, the drafts of the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation were developed | The second quarter of 2020 | Completed | It was enviaged to submit to the RA Audit Chamber the strategic development plan of the RA Audit Chamber for 2020-2023 and action plan for its implementation, which is fully completed. | Delays in the adoption of the legal reform package. Delays in the process of external assistance and the reduction of state budget funds due to pandemic and other force majeure situations. | Ongoing cooperation with external (donor organizations, partners, supreme audit bodies) and internal (key players of RA PFM system) stakeholders, timely and proper response to the problems
|  | 53.2 implementation of measures approved by the Audit Chamber strategy for 2020-2023 |  |  | 2020-2023 |  | The objectives set by the strategy are implemented in accordance with the defined schedule | The Strategic Development Plan of the Audit Chamber of the Republic of Armenia for 2020-2023, the action plan for its implementation approved by the RA Audit Chamber Decision 150-Լ , dated August 7, 2020 includes all the defined indicators. The Audit Chamber for the implementation of indicators, held an online presentation on the strategy for the external and internal stakeholders of the Audit Chamber (including the Ministry of Finance, the National Assembly, donor organizations, partner accounting bodies) on December 20, 2020. | The drafts of The Strategic Development Plan of the RA Audit Chamber for 2020-2023, the action plan for its implementation include the targets defined by the measures |  | In progress | After the approval of the strategic development plan, the annual plan of measures for the implementation of the strategy will be drawn up, which will clarify the terms of implementation of these points. | Risks of retaining and attracting low-quality resources. Delays in the process of external assistance and the reduction of state budget funds due to pandemic and other force majeure situations. |  | (GIZ)
| 54. Capacity building of AC staff and Improving professional skills | 54.1 Development and approval of the capacity building program of the AC staff |  |  | 2022-2023 |  | AC auditors perform audits in accordance with ISSAI standards | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFC strategy. | Measure 54.2 is included in the draft of the Strategic Development Program of the RA Audit Chamber for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFM strategy. |  | In progress | Preparations are being made to ensure these indicators within the set timeframe within the framework of the implementation of the Strategy |  |  | (GIZ)
|  | 54.2 Capacity building of AC staff and improvement of professional skills |  |  |  |  | Qualified External Auditors | Measure 54.2 is included in the draft of the Strategic Development Program of the Audit Chamber of the Republic of Armenia for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFC strategy. There are preliminary agreements for providing external support to this measure | Measure 54.2 is included in the draft of the Strategic Development Program of the RA Audit Chamber for 2020-2023, the draft of the action plan of which defines the terms of implementation of the measure envisaged by the PFM strategy. |  | In progress | Preparations are being made to ensure these indicators within the set timeframe within the framework of the implementation of the Strategy |  |  | (GIZ)
14. GOVERNMENT FINANCIAL MANAGEMENT INFORMATION SYSTEM (GFMIS)
27. Government Financial Management Information System (GFMIS) | 55. Introduction of the main components of the GFMIS - Phase 1 | 55.1 Revision of GFMIS tender documents | MoF | MoHTI | December, 2020 |  | he complete set of tender documents for the development of the GFMIS tender implementation package has been revised and made complete. | On May 7, 2020 the first stage of the two-stage procurement process for the selection of a consultant assisting the Ministry of Finance in the process of introduction of the GFMIS was organized. 7 organizations applied for pre-qualification, of which 5 became pre-qualified participants, "Harmony" Foundation, Ernst & Young CJSC, AAM Management Information Consulting Ltd., Deloitte Armenia CSJC, Moore Management Consulting Ltd. Further on, the negotiation phase has started. From now on, the stage of negotiations has begun. On 5․11․2020, the pre-qualified participants were provided the invitation of second phase tender. Deadline for submitting bids is set 25.01.2021 by invitation. and as of that day, one of the 5 pre-qualified organizations, the "Harmony" Foundation, has submitted a bid. The latter's bid is under evaluation. | January-April, 2021 sums up the results of the two-stage procurement process for the selection of a consultant assisting the Ministry of Finance. On 20.04.2021 a contract was signed with the winning company for the provision of consulting services within the framework of the GFMIS introduction project. Within the contract, the elaboration of the report of the first stage of the project introduction defined by the contract terms of reference schedule, within the framework of which the consultant submitted the management manual of the GFMIS introduction project for discussion by the consultant. | The first round of the two-stage tender for the selection of a consultant in the process of introduction of the GFMIS took place on 07-05-2020. The second stage, on 05.11.2020 | In progress | Study, discussion of the management manual of the GFMIS introduction project submitted by the consultant, implementation of further works envisaged by the contract | The date of the measure was adjusted in the contract signed with the consultant providing assistance to the Ministry of Finance. The implementation of this measure can last up to first quarter of 2023. | Review the timing of the event, matching the schedule with the consultant. | WB/RF/Mof
|  | 55.2 GFMIS acquirement |  |  | 2020-2021 |  | The complete package of documents for the implementation of the GFMIS tender has been drawn up, the tender has been held | Will be implemented 55.1. after the selection of the Consultant presented by the measure within the established timeframe. | Will be implemented after the selection of the Consultant presented by the measure 55.1. within the established timeframe. |  | Not started |  | It is necessary to reconsider the timing of the measure, as the contract with the consultant was signed on 20.04.2021 within the measures defined by point 55.1 and the deadline for the implementation of this measure is expected to be maximum by the beginning of 2023. | Review the timing of the event, matching the schedule with the consultant. | WB/RF/Mof
|  | 55.3 GFMIS introduction testing |  |  | December, 2021 |  | GFMIS embedded in accordance with terms of reference | [5 empty] | It is necessary to reconsider the timing of the measure, as the contract with the consultant was signed on 20.04.2021 within the measures defined by point 55.1 and the deadline for the implementation of this measure is expected to be maximum by second ten days of 2023. | Review the timing of the event, matching the schedule with the consultant. | WB/RF/Mof
| 56. Introduction of the main components of the GFMIS - Phase 2 | 56.1 Full introduction of GFMIS |  |  | December, 2022 |  | GFMIS embedded in accordance with terms of reference | [5 empty] | It is necessary to reconsider the timing of the measure, as the contract with the consultant was signed on 20.04.2021 within the measures defined by point 55.1 and the deadline for the implementation of this measure is expected to be maximum by December of 2023. | Review the timing of the event, matching the schedule with the consultant. | WB/RF/Mof
|  | 56.2 Training of GFMIS users |  |  | December, 2022 |  | GFMIS users are trained | [5 empty] | It is necessary to reconsider the timing of the measure, as the contract with the consultant was signed on 20.04.2021 within the measures defined by point 55.1 and the deadline for the implementation of this measure is expected to be maximum by December of 2023. | Review the timing of the event, matching the schedule with the consultant. | WB/RF/Mof
|  | 56.3 GFMIS service |  |  | December, 2023 |  | availability of a properly functioning GFMIS automated system | [7 empty] | WB/RF/Mof

## Used terms
Terms used in the column "Status" of the Report
Completed | The measure is completely done.
In Progress | The works on the implementation of the measure have started,considered to be in progress. The works envisaged within the framework of the measure have not been completed yet.
Not started | The works on the implementation of the measure have not started yet, mainly due to depending on the results of other measures.
It is a periodic process | The actions defined by the measure are periodic processes, which are an integral part of the ongoing functions of the state body. The results of these measures do not have a clear beginning or end.
Not started | No information was provided on the progress of the measure.
Risky | There are risks associated with the on time implemention of the mesaure.